## Master Drawing Register
Master Drawing Register
Sr # | Project Package | Building | Discipline | Drawing Number | Drawing Title | Drawing Type | Consultant Name | Revision Number | Revision Date | Revision Description | Latest Revision | Planned Submission Date | Actual Submission Date | Submission Delay (Days) | Delay Responsibility | Issued To | Issue Date | No. of Copies | Critical Drawing | Remarks
1 | Package A | Tower 1 | Architecture | AR-101 | Typical Floor Plan | Good For Construction (GFC) | Design Consultants Ltd | R2 | 2025-01-10 | Revised layout as per client comments | Yes | 2025-01-03 | 2025-01-05 | -2 | Strcutural Consultant | Main Contractor | 2025-01-16 | 2 | Yes | Issued to site
2 | Package A | Tower 1 | Structural | ST-201 | Footing Layout Basement | Tender Drawings | Structural Consultants Ltd | R1 | 2025-01-12 | Initial submission | Yes | 2025-01-08 | 2025-01-10 | -2 | Architecture Consultant | PMC / Client |  | 0 | Yes | Critical for foundation work
3 | Package A | Tower 1 | Architecture | AR-103 | Staircase Details | Shop Drawing | Design Consultants Ltd | R0 | 2025-01-12 | Initial submission | Yes | 2025-01-10 | 2025-01-12 | -2 | Consultant | PMC / Client | 2025-01-18 | 0 | No | Under review earlier
4 | Package A | Tower 1 | Structural | ST-201 | Footing Layout Basement | Detailed Design (DD) Drawings | Structural Consultants Ltd | R1 | 2025-01-12 | Initial submission | Yes | 2025-01-08 | 2025-01-10 | -2 | Consultant | PMC / Client |  | 0 | Yes | Critical for foundation work
5 | Package A | Tower 1 | Structural | ST-202 | Column Layout Basement | Concept Drawings | Structural Consultants Ltd | R2 | 2025-01-15 | Revised grid alignment | Yes | 2025-01-10 | 2025-01-13 | -3 | Consultant | Main Contractor | 2025-01-20 | 2 | Yes | —
6 | Package A | Tower 1 | Structural | ST-203 | Beam Reinforcement Details | Detailed Design (DD) Drawings | Structural Consultants Ltd | R0 | 2025-01-18 | Initial submission | Yes | 2025-01-15 | 2025-01-18 | -3 | Consultant | PMC / Client |  | 0 | Yes | Under approval
7 | Package A | Tower 1 | MEPF | MEP-301 | HVAC Layout Typical Floor | Good For Construction (GFC) | MEP Design Associates | R1 | 2025-01-14 | Revised routing | Yes | 2025-01-10 | 2025-01-14 | -4 | Consultant | Main Contractor | 2025-01-22 | 2 | Yes | —
8 | Package A | Tower 1 | MEPF | MEP-302 | Electrical Lighting Layout | Detailed Design (DD) Drawings | MEP Design Associates | R2 | 2025-01-16 | Revised lighting levels | Yes | 2025-01-12 | 2025-01-15 | -3 | Consultant | Main Contractor | 2025-01-24 | 2 | No | —
9 | Package A | Tower 1 | MEPF | MEP-303 | Plumbing Typical Floor | Tender Drawings | MEP Design Associates | R1 | 2025-01-18 | Initial issue | Yes | 2025-01-15 | 2025-01-18 | -3 | Consultant | Main Contractor | 2025-01-25 | 2 | No | —
10 | Package A | Tower 2 | Architecture | AR-201 | Typical Floor Plan | Tender Drawings | Design Consultants Ltd | R1 | 2025-01-20 | Initial submission | Yes | 2025-01-18 | 2025-01-20 | -2 | Consultant | PMC / Client |  | 0 | Yes | Under review
11 | Package A | Tower 2 | Architecture | AR-202 | Elevation North Side | Schematic Drawings | Design Consultants Ltd | R2 | 2025-01-25 | Revised façade treatment | Yes | 2025-01-22 | 2025-01-24 | -2 | Consultant | Main Contractor | 2025-01-30 | 2 | No | —
12 | Package A | Tower 2 | Structural | ST-301 | Foundation Layout | Good For Construction (GFC) | Structural Consultants Ltd | R1 | 2025-01-22 | Initial submission | Yes | 2025-01-20 | 2025-01-22 | -2 | Consultant | PMC / Client |  | 0 | Yes | Critical activity
13 | Package A | Tower 2 | Structural | ST-302 | Slab Reinforcement | Tender Drawings | Structural Consultants Ltd | R0 | 2025-01-26 | Initial submission | Yes | 2025-01-25 | 2025-01-26 | -1 | Consultant | PMC / Client |  | 0 | Yes | —
14 | Package A | Tower 2 | MEPF | MEP-401 | Fire Fighting Layout | Shop Drawing | MEP Design Associates | R1 | 2025-01-24 | Initial issue | Yes | 2025-01-22 | 2025-01-24 | -2 | Consultant | Main Contractor | 2025-01-30 | 2 | Yes | Fire NOC related
15 | Package B | Tower 3 | Architecture | AR-301 | Typical Floor Plan | Detailed Design (DD) Drawings | Design Consultants Ltd | R3 | 2025-02-01 | Revised after site feedback | Yes | 2025-01-28 | 2025-01-30 | -2 | Consultant | Main Contractor | 2025-02-05 | 2 | Yes | —
16 | Package B | Tower 3 | Architecture | AR-302 | Staircase Details | Concept Drawings | Design Consultants Ltd | R0 | 2025-02-03 | Initial submission | Yes | 2025-02-01 | 2025-02-03 | -2 | Consultant | PMC / Client |  | 0 | No | —
17 | Package B | Tower 3 | Structural | ST-401 | Column Layout Typical | Detailed Design (DD) Drawings | Structural Consultants Ltd | R1 | 2025-02-02 | Initial issue | Yes | 2025-01-30 | 2025-02-02 | -3 | Consultant | Main Contractor | 2025-02-08 | 2 | Yes | —
18 | Package B | Tower 3 | Structural | ST-402 | Beam Layout Typical | Good For Construction (GFC) | Structural Consultants Ltd | R0 | 2025-02-05 | Initial submission | Yes | 2025-02-03 | 2025-02-05 | -2 | Consultant | PMC / Client |  | 0 | Yes | —
19 | Package B | Tower 3 | MEPF | MEP-501 | Electrical Riser Diagram | Detailed Design (DD) Drawings | MEP Design Associates | R1 | 2025-02-04 | Initial issue | Yes | 2025-02-02 | 2025-02-04 | -2 | Consultant | Main Contractor | 2025-02-10 | 2 | No | —
20 | Package B | Tower 3 | MEPF | MEP-502 | Plumbing Riser Diagram | Tender Drawings | MEP Design Associates | R1 | 2025-02-06 | Initial issue | Yes | 2025-02-04 | 2025-02-06 | -2 | Consultant | Main Contractor | 2025-02-12 | 2 | No | —
21 | Package B | Tower 3 | MEPF | MEP-503 | HVAC Shaft Layout | Tender Drawings | MEP Design Associates | R0 | 2025-02-07 | Initial submission | Yes | 2025-02-05 | 2025-02-07 | -2 | Consultant | PMC / Client |  | 0 | Yes | Coordination required
22 | Package C | Tower 1 | Architecture | AR-401 | Typical Floor Plan | Schematic Drawings | Design Consultants Ltd | R4 | 2025-02-10 | Revised after coordination | Yes | 2025-02-03 | 2025-02-06 | -3 | Architecture Consultant | Main Contractor | 2025-02-15 | 2 | Yes | Delayed due to coordination changes
23 | Package C | Tower 1 | Structural | ST-501 | Foundation Layout | Good For Construction (GFC) | Structural Consultants Ltd | R3 | 2025-02-12 | Revised footing sizes | Yes | 2025-02-05 | 2025-02-09 | -4 | Structural Consultant | PMC / Client |  | 0 | Yes | Critical foundation drawing
24 | Package C | Tower 1 | MEPF | MEP-601 | HVAC Typical Floor | Tender Drawings | MEPF Design Associates | R2 | 2025-02-14 | Revised duct routing | Yes | 2025-02-08 | 2025-02-10 | -2 | MEPF Consultant | Main Contractor | 2025-02-18 | 2 | Yes | Coordination driven delay
25 | Package C | Tower 2 | Architecture | AR-402 | Elevation East Side | Shop Drawing | Design Consultants Ltd | R5 | 2025-02-18 | Facade design updated | Yes | 2025-02-10 | 2025-02-14 | -4 | Architecture Consultant | Main Contractor | 2025-02-22 | 2 | No | Client-driven revision
26 | Package C | Tower 2 | Structural | ST-502 | Column Layout Basement | Detailed Design (DD) Drawings | Structural Consultants Ltd | R4 | 2025-02-20 | Grid updated as per arch | Yes | 2025-02-12 | 2025-02-17 | -5 | Structural Consultant | PMC / Client |  | 0 | Yes | Delay due to arch inputs
27 | Package C | Tower 2 | MEPF | MEP-602 | Electrical Layout Typical | Concept Drawings | MEPF Design Associates | R3 | 2025-02-21 | Load recalculation done | Yes | 2025-02-15 | 2025-02-18 | -3 | MEPF Consultant | Main Contractor | 2025-02-25 | 2 | No | —
28 | Package C | Tower 3 | Architecture | AR-403 | Staircase Details | Detailed Design (DD) Drawings | Design Consultants Ltd | R2 | 2025-02-22 | Minor detailing changes | Yes | 2025-02-18 | 2025-02-20 | -2 | Architecture Consultant | PMC / Client |  | 0 | No | —
29 | Package C | Tower 3 | Structural | ST-503 | Beam Reinforcement | Good For Construction (GFC) | Structural Consultants Ltd | R1 | 2025-02-23 | Initial submission | Yes | 2025-02-20 | 2025-02-23 | -3 | Structural Consultant | PMC / Client |  | 0 | Yes | Delayed reinforcement inputs
30 | Package C | Tower 3 | MEPF | MEP-603 | Plumbing Layout Typical | Detailed Design (DD) Drawings | MEPF Design Associates | R2 | 2025-02-25 | Revised pipe routing | Yes | 2025-02-20 | 2025-02-24 | -4 | MEPF Consultant | Main Contractor | 2025-02-28 | 2 | No | —
31 | Package C | Tower 4 | Architecture | AR-404 | Refuge Floor Plan | Tender Drawings | Design Consultants Ltd | R6 | 2025-02-28 | Code compliance update | Yes | 2025-02-20 | 2025-02-26 | -6 | Architecture Consultant | Main Contractor | 2025-03-02 | 2 | Yes | Statutory driven delay
32 | Package D | Tower 1 | Structural | ST-601 | Foundation Layout | Tender Drawings | Structural Consultants Ltd | R5 | 2025-03-02 | Revised soil parameters | Yes | 2025-02-22 | 2025-02-27 | -5 | Structural Consultant | PMC / Client |  | 0 | Yes | Soil report revision
33 | Package D | Tower 1 | MEPF | MEP-701 | Fire Fighting Layout | Schematic Drawings | MEPF Design Associates | R3 | 2025-03-03 | Revised fire zoning | Yes | 2025-02-25 | 2025-02-28 | -3 | MEPF Consultant | Main Contractor | 2025-03-06 | 2 | Yes | Fire NOC comments
34 | Package D | Tower 2 | Architecture | AR-501 | Typical Floor Plan | Good For Construction (GFC) | Design Consultants Ltd | R4 | 2025-03-05 | Updated flat layouts | Yes | 2025-02-26 | 2025-03-02 | -4 | Architecture Consultant | Main Contractor | 2025-03-08 | 2 | Yes | Client revision impact
35 | Package D | Tower 2 | Structural | ST-602 | Slab Reinforcement | Tender Drawings | Structural Consultants Ltd | R2 | 2025-03-06 | Initial submission | Yes | 2025-03-01 | 2025-03-05 | -4 | Structural Consultant | PMC / Client |  | 0 | Yes | Delayed due to load changes
36 | Package D | Tower 3 | MEPF | MEP-702 | HVAC Shaft Layout | Shop Drawing | MEPF Design Associates | R1 | 2025-03-08 | Initial submission | Yes | 2025-03-04 | 2025-03-07 | -3 | MEPF Consultant | PMC / Client |  | 0 | Yes | Coordination pending
37 | Package D | Tower 3 | Architecture | AR-502 | Elevation West Side | Detailed Design (DD) Drawings | Design Consultants Ltd | R6 | 2025-03-10 | Facade redesign | Yes | 2025-03-01 | 2025-03-07 | -6 | Architecture Consultant | Main Contractor | 2025-03-12 | 2 | No | Major design change
38 | Package D | Tower 4 | Structural | ST-603 | Column Layout Typical | Concept Drawings | Structural Consultants Ltd | R4 | 2025-03-12 | Grid revised | Yes | 2025-03-05 | 2025-03-10 | -5 | Structural Consultant | Main Contractor | 2025-03-15 | 2 | Yes | Coordination delay
39 | Package D | Tower 4 | MEPF | MEP-703 | Electrical Riser Diagram | Detailed Design (DD) Drawings | MEPF Design Associates | R2 | 2025-03-14 | Load balancing update | Yes | 2025-03-08 | 2025-03-12 | -4 | MEPF Consultant | Main Contractor | 2025-03-18 | 2 | No | —
40 | Package D | Tower 5 | Architecture | AR-503 | Refuge Area Details | Good For Construction (GFC) | Design Consultants Ltd | R5 | 2025-03-16 | Code update applied | Yes | 2025-03-10 | 2025-03-15 | -5 | Architecture Consultant | Main Contractor | 2025-03-20 | 2 | Yes | Fire authority driven
41 | Package D | Tower 5 | Structural | ST-604 | Beam Layout Roof | Detailed Design (DD) Drawings | Structural Consultants Ltd | R3 | 2025-03-18 | Revised reinforcement | Yes | 2025-03-12 | 2025-03-17 | -5 | Structural Consultant | PMC / Client |  | 0 | Yes | Roof load revision

## Site Drawing Register
Site Drawing Register
SR. NO | DETAILS OF DRAWING | Descipline | DRAWING NOMBER | RECEIVE & ISSUE DETAILS | DRAWING REVISION | [6 empty] | Date | Remarks
[5 empty] | RO | R1 | R2 | R3 | R4 | R5 | R6
1 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE

## Hinderance Register
Hinderance Register
Sr. No | Description of Hindrance | Location | Critical Activity affected | Correspondence | Category | Type of Hindrance | Date of Occurrence | Date Resolved | No. of Days | Baseline Start Date | Schedule Impact | Delay Type | Accountable | Status | Description of Resolution | Remarks
1 | Staircase work | Building A | Shutterting | 2026-12-26 | Design & Technical | Storage and handling constraints | 2026-11-19 | 2026-11-22 | 4 | 2026-11-13 | 10 | Overlapping Delay | Architecture Consultant | Resolved | drawing was given on 22-11-2026 |  | #REF! | #REF!
2 | Column reinforcement and formwork for part 1A | Building B | Casting | 2026-12-26 | Approval | Delay in mock-up / sample approvals | 2026-12-24 | 2026-12-28 | 5 | 2026-12-24 | 5 | Non-overlapping Delay | Contractor | Resolved | drawing was given on 28-12-2027
3 | basement 1 slab for Part 1B,1C | Building C | Reinforcement | 2027-01-12 | Execution | Variation / change order approval delays | 2027-01-05 | 2027-01-17 | 13 | 2027-01-06 | 12 | Non-overlapping Delay | Structure Consultant | Resolved | drawing was given on 17-1-23
4 | Basement 1 slab for Part 1D | Building D | Excavation | 2027-01-12 | Material Procurement | Work front not available / handed over | 2027-01-12 | 2027-01-17 | 6 | 2026-12-31 | 18 | Overlapping Delay | PMC | Resolved | drawing was given on 17-1-23
5 | Ground floor slab for Block A | Building E | Shutterting | 2026-12-26 | Material Procurement | Import / logistics clearance delays | 2027-01-20 | 2027-02-08 | 20 | 2027-01-20 | 20 | Non-overlapping Delay | Structure Consultant | Resolved | drawing was given on 8-2-23 for shuttering
6 | Basement 3 slab for Part 2 | Building A | Casting | 2026-12-26 | Approval | Delay in statutory approvals (Fire, Local Authority, Utilities) | 2027-01-20 | 2027-02-07 | 19 | 2027-01-15 | 24 | Overlapping Delay | Client | Resolved | drawing was given on 7-2-23 for shuttering
7 | Lift 4 | Building B | Reinforcement | 2027-01-28 | Execution | Vendor / supplier non-performance | 2027-01-18 | 2027-01-31 | 14 | 2027-01-07 | 25 | Non-overlapping Delay | Contractor | Open | drawing was given on 24-1-23 and hold decision was given on 31-1-23
8 | Stair 5,6,2 - Part 2 | Building C | Excavation | 2027-02-22 | Design & Technical | Insufficient skilled manpower | 2027-02-10 | 2027-03-01 | 20 | 2027-01-15 | 46 | Non-overlapping Delay | Architecture Consultant | Open | drawing was given on 8-2-23 for shuttering
9 | Block B & C - ground floor slab | Building D | Reinforcement | 2026-12-26 | Approval | Constructability issues at site | 2027-02-15 | 2027-02-19 | 5 | 2027-01-31 | 20 | Overlapping Delay | Contractor | Resolved | drawing was given on 19-2-23 for shuttering
10 | Block A - ground floor | Building E | Excavation | 2026-12-26 | Execution | Delay in issue of GFC / IFC drawings | 2027-02-20 | 2027-02-23 | 4 | 2027-02-07 | 17 | Overlapping Delay | Structure Consultant | Resolved | drawing was given on 8-2-23 for shuttering
11 | Block C - ground floor | Building A | Shutterting | 2027-02-27 | Design & Technical | Delay in issue of GFC / IFC drawings | 2027-02-26 | 2027-02-28 | 3 | 2027-02-04 | 25 | Overlapping Delay | PMC | Resolved
12 | Block A - ground floor | Building B | Casting | 2026-12-26 | Execution | Delay in design clarifications (RFIs) | 2027-02-27 | 2027-03-02 | 4 | 2027-02-07 | 24 | Non-overlapping Delay | Structure Consultant | Resolved | casting done on 2/3/23
13 | Part 2- ramp work | Building C | Excavation | 2027-02-27 | Material Procurement | Delay in approval from Client / PMC | 2027-02-17 | 2027-03-04 | 16 | 2027-01-16 | 48 | Non-overlapping Delay | Client | Resolved
14 | Part 1- Stair 1,9 | Building D | Shutterting | 2026-12-26 | Approval | Delay in statutory approvals (Fire, Local Authority, Utilities) | 2027-03-05 | 2027-04-04 | 31 | 2027-01-31 | 64 | Overlapping Delay | Contractor | Open
15 | Part 2A- basement 2 | Building E | Reinforcement | 2027-03-14 | Execution | Delay in issue of GFC / IFC drawings | 2027-03-16 | 2027-03-21 | 6 | 2027-02-10 | 40 | Non-overlapping Delay | Client | Resolved | drawing was given on 21-3-23 for shuttering
0

## Legal Approval Tracker
Legal Approval Tracker - Week #
Approval ID | Approval Category | Authority Name | Approval Description | Applicable Building / Package | Submission Date | Required By | Approval Received Date | Status | Delay (Days) | Responsible Party | Remarks
LA-01 | Labour Compliance | Labour Department | BOCW Registration – Building & Other Construction Works | All Towers | 2025-01-05 | 2025-01-20 | 2025-01-22 | Approved | 2 | Client | Approved with minor delay
LA-02 | Insurance | Insurance Company | CAR Policy – Contractor All Risk | All Packages | 2025-01-02 | 2025-01-10 | 2025-01-09 | Approved | -1 | Contractor | Submitted on priority
LA-03 | Labour Compliance | Labour Department | CLRA Registration – Contract Labour Regulation Act | All Towers | 2025-01-06 | 2025-01-25 |  | Submitted |  | Contractor | Under review by department
LA-04 | Labour Compliance | Labour Department | Labour License | Tower 1 | 2025-01-08 | 2025-01-20 |  | Delayed |  | Contractor | Inspection pending
LA-05 | Statutory | EPFO | PF Registration Documents | All Packages | 2025-01-03 | 2025-01-15 | 2025-01-14 | Approved | -1 | Contractor | -
LA-06 | Statutory | ESIC | ESI Registration Documents | All Packages | 2025-01-03 | 2025-01-15 | 2025-01-16 | Approved | 1 | Contractor | One day delay
LA-07 | Tax | State Tax Department | Professional Tax Registration | All Packages | 2025-01-04 | 2025-01-18 | 2025-01-17 | Approved | -1 | Contractor | -
LA-08 | Labour Compliance | Labour Department | LWF – Labour Welfare Fund Registration | All Towers | 2025-01-05 | 2025-01-18 |  | Submitted |  | Contractor | Follow-up required
LA-09 | Health & Safety | Government Hospital | Worker Medical Fitness Certification | All Towers | 2025-01-07 | 2025-01-14 | 2025-01-13 | Approved | -1 | Contractor | -
LA-10 | Police Clearance | Local Police Department | Worker Police Verification | All Towers | 2025-01-07 | 2025-01-21 |  | Delayed |  | Contractor | Police clearance pending
LA-11 | Safety | Third Party Agency | Test Certificate – Lifting Tools & Tackles | All Towers | 2025-01-09 | 2025-01-19 | 2025-01-18 | Approved | -1 | Contractor | -
LA-12 | Safety | Third Party Agency | Pressure Vessel Test Certificate | All Towers | 2025-01-09 | 2025-01-19 |  | Submitted |  | Contractor | Inspection scheduled
LA-13 | Fire | Fire Department | Fire NOC – Temporary Site Office | Site Area | 2025-01-10 | 2025-01-25 |  | In Progress |  | Client | Documents submitted
LA-14 | Environment | Pollution Control Board | Consent to Establish (CTE) | Project Site | 2025-01-12 | 2025-02-05 |  | Submitted |  | Client | Under scrutiny
LA-15 | Environment | Pollution Control Board | Consent to Operate – DG Set | Project Site | 2025-01-15 | 2025-02-10 |  | Not Submitted |  | Contractor | DG set not installed
LA-16 | Local Authority | Municipal Corporation | Building Plan Approval | Tower 1 | 2024-12-15 | 2025-01-30 | 2025-01-28 | Approved | -2 | Client | -
LA-17 | Local Authority | Municipal Corporation | Commencement Certificate | Tower 2 | 2025-01-05 | 2025-01-25 |  | Delayed |  | Client | Resubmission required
LA-18 | Utility | Electricity Board | Temporary Power Connection | Site | 2025-01-06 | 2025-01-20 | 2025-01-21 | Approved | 1 | Contractor | -
LA-19 | Utility | Water Supply Department | Temporary Water Connection | Site | 2025-01-06 | 2025-01-20 |  | Submitted |  | Contractor | Pipeline work pending
LA-20 | Traffic | Traffic Police Department | Traffic Diversion Permission | Main Road | 2025-01-10 | 2025-01-18 | 2025-01-17 | Approved | -1 | Client | -
LA-21 | Safety | Factory Inspectorate | Site Safety Registration | All Towers | 2025-01-11 | 2025-01-22 |  | In Progress |  | Contractor | Inspection awaited
LA-22 | Insurance | Insurance Company | Workmen Compensation Policy | All Labour | 2025-01-05 | 2025-01-12 | 2025-01-11 | Approved | -1 | Contractor | -
LA-23 | Labour Compliance | Labour Department | Inter-State Migrant Workmen Registration | All Towers | 2025-01-08 | 2025-01-25 |  | Submitted |  | Contractor | Documents under review
LA-24 | Environment | Local Authority | Tree Cutting Permission | Site Boundary | 2025-01-15 | 2025-02-01 |  | Not Submitted |  | Client | Tree survey pending
LA-25 | Safety | Fire Department | Fire Safety Equipment Approval | Site | 2025-01-16 | 2025-01-30 |  | In Progress |  | Contractor | Partial installation completed
LA-26 | Utility | Telecom Authority | Internet / Telecom Permission | Site Office | 2025-01-14 | 2025-01-28 | 2025-01-27 | Approved | -1 | Contractor | -
LA-27 | Local Authority | Municipal Corporation | Hoarding Permission | Site Boundary | 2025-01-18 | 2025-01-28 |  | Submitted |  | Client | Approval awaited
LA-28 | Environment | Local Authority | Debris Disposal Permission | Project Site | 2025-01-20 | 2025-02-05 |  | Not Submitted |  | Contractor | Vendor finalisation pending
LA-29 | Safety | Lift Inspector | Temporary Construction Lift Approval | Tower 1 | 2025-01-22 | 2025-02-10 |  | In Progress |  | Contractor | Inspection scheduled
LA-30 | Statutory | Explosives Department | Diesel Storage License | Project Site | 2025-01-25 | 2025-02-15 |  | Not Submitted |  | Contractor | Tank installation pending

## Milestone Dashboard
Milestone ID | Phase | Milestone Name | Planned Start | Planned End | Planned Days | Actual Start | Actual End | Actual Days | Weightage | % Complete | Stakeholder | Zone | Status2 | Delays
M01 | Pre-Construction | Site Mobilization | 2026-01-01 | 2026-01-05 | 4 | 2026-01-01 | 2026-01-05 | 4 | 5 | 100% | ABC Infra | A | Completed | 0
M02 | Excavation | Excavation Work | 2026-01-06 | 2026-01-15 | 9 | 2026-01-07 | 2026-01-17 | 10 | 5 | 100% | ABC Infra | A | Delayed | 1
M03 | Foundation | PCC Work | 2026-01-16 | 2026-01-20 | 4 | 2026-01-16 | 2026-01-20 | 4 | 5 | 100% | XYZ Con | A | Completed | 0
M04 | Foundation | Footing RCC | 2026-01-21 | 2026-01-30 | 9 | 2026-01-21 | 2026-02-02 | 12 | 10 | 100% | XYZ Con | B | Delayed | 3
M05 | Structure | Column RCC | 2026-02-01 | 2026-02-10 | 9 | 2026-02-01 | 2026-03-12 | 39 | 15 | 100% | XYZ Con | B | Delayed | 30
M06 | Structure | Slab Casting | 2026-02-11 | 2026-02-20 | 9 | 2026-02-11 | 2026-03-13 | 30 | 15 | 100% | LMN Build | B | Delayed | 21
M07 | Masonry | Block Work | 2026-02-21 | 2026-03-05 | 30 | 2026-01-08 |  | 0 | 15 | 100% | LMN Build | C | In Progress | 0
M08 | Finishing | Plastering | 2026-03-06 | 2026-03-20 | 14 | 1900-01-07 |  | -8 | 10 | 20% | LMN Build | C | In Progress | 0
M09 | Finishing | Flooring | 2026-03-21 | 2026-04-05 | 15 |  |  | 0 | 10 | 0% | PQR Works | C | Not Started | 0
M10 | Handover | Final Inspection | 2026-04-06 | 2026-04-10 | 4 |  |  |  | 10 | 0% | PQR Works | C | Not Started | 0
0
| 10 | [7 empty] | 72%

## SOR Log
Sr.no. | Observation | Total | Open | Close | Closure Rate | Sr. No. | Name of Equipment | Unit | Total Number
1 | Site Observation | 75 | 10 | 65 | 86.67% | 1 | Compression Testing Machine | No | 1
2 | Site Instruction | 75 | 5 | 70 | 93.33% | 2 | Slump Cone Test Apparatus | Set | 1
3 | NCR | 1 | 0 | 1 | 100% | 3 | Steel Moulds | No | 25
|  |  |  | Average | 93.33% | 4 | Digital Moisture Meter | No | 1
[6 empty] | 5 | Weighing Balance | No | 1
[6 empty] | 6 | Thermometer | No | 1
Sr.no. | Observation | Open | Close
1 | Site Observation | 10 | 65
Sr.no. | Observation | Open | Close
2 | Site Instruction | 5 | 70
Sr.no. | Observation | Open | Close
3 | NCR | 0 | 1

## Cube Test
Sample # | Compressive strength at 7 days | IS code lower limit
1 | 19.07 | 17
2 | 23 | 17
3 | 22.24 | 17
4 | 18.03 | 17
5 | 18.24 | 17
6 | 19.16 | 17

## CAR register
NON CONFORMANCE AND CORRECTIVE ACTION REQUEST (CAR ) REGISTER
No. | NCR / CAR Issue Date | Type | Contractor | Brief Description of Non Conformance | Location | Planned Closure Date | Actual Closure Date | Status
1 | 2024-05-10 | Quality | RIAD | According to the drawing of the UG Tank (Job: 35/2023, Drawing No: 1, Date: 05-02-2024), note point 8 specifies the requirement for a water stopper to be installed at the construction joint of the water tank. The water stopper should be 150 mm wide and 5 mm thick, made of PVC material. However, despite this specification, the contractor, project manager, and client have disagreed on the provision of this water stopper. If the water stopper is not installed at the joint as per the drawing, there is a risk of water leakage occurring at the joint. Therefore, it's essential to adhere to the specified requirements to prevent potential water leakages and ensure the integrity of the construction. | India | 2024-05-12 |  | Open
Health and Safety
Environmental
| Quality |  |  |  | Australia
China
Hong Kong
India
Indonesia
Japan
Korea
Philippines
Singapore
Taiwan
Thailand
Vietnam

## Weekly Manpower
Type of Manpower | Required Manpower for week | Available | Shortage | % Shortage | Rank | [14 empty] | Safety NCR |  |  | Unsafe Act |  |  | Condition
Reinforcement work | 120 | 65 | 55 | 45.83% | 1 | [14 empty] | Total | Open | Close | Total | Open | Close | Total | Open | Close
Carpenter | 125 | 100 | 25 | 20% | 9 | [14 empty] | 2 | 1 | 2 | 10 | 0 | 10 | 10 | 1 | 9
Mason | 105 | 79 | 26 | 24.76% | 8
Helper | 116 | 83 | 33 | 28.45% | 7
Unskilled Worker | 315 | 203 | 112 | 35.56% | 4 | [14 empty] | NCR |  |  | Site Observation |  |  | Site Instructions
Drivers | 13 | 13 | 0 | 0% | 10 | [14 empty] | Total | Open | Close | Total | Open | Close | Total | Open | Close
Staff | 33 | 33 | 0 | 0% | 10 | [14 empty] | 1 | 0 | 1 | 38 | 2 | 36 | 41 | 2 | 39
Plumbing | 10 | 6 | 4 | 40% | 2
Tiles Work | 48 | 30 | 18 | 37.5% | 3
Painter | 21 | 15 | 6 | 28.57% | 6
Electric Work | 32 | 22 | 10 | 31.25% | 5
Total of Above | 938 | 649 | 289
Available | [11 empty] | Available
Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff | Plumbing | Tiles | Painter | Ele. | Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff
2025-12-11 | 12 | 10 | 12 | 14 | 28 | 1 | 5 | 2 | 5 | 2 | 3 | 2025-10-23 | 0 | 5 | 0 | 3 | 1 | 0 | 0
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-12 | 10 | 7 | 11 | 8 | 29 | 1 | 5 | 2 | 5 | 2 | 5 | 2025-10-24 | 0 | 5 | 0 | 3 | 1 | 0 | 1
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-13 | 3 | 14 | 12 | 8 | 29 | 1 | 5 | 2 | 5 | 2 | 2 | 2025-10-25 | 0 | 10 | 0 | 8 | 14 | 1 | 2
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-14 | 2 | 14 | 12 | 7 | 28 | 1 | 3 | 0 | 3 | 3 | 2 | 2025-10-26 | 0 | 10 | 0 | 8 | 5 | 1 | 0
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-15 | 14 | 25 | 12 | 11 | 28 | 1 | 5 | 0 | 3 | 3 | 3 | 2025-10-27 | 0 | 5 | 0 | 4 | 3 | 1 | 4
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-16 | 14 | 15 | 10 | 16 | 30 | 4 | 6 | 0 | 3 | 3 | 3 | 2025-10-28 | 3 | 5 | 1 | 8 | 3 | 1 | 6
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-17 | 10 | 15 | 10 | 19 | 31 | 4 | 4 | 0 | 6 | 0 | 4 | 2025-10-29 | 3 | 5 | 1 | 8 | 12 | 1 | 5
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 65 | 100 | 79 | 83 | 203 | 13 | 33 | 6 | 30 | 15 | 22 | Total | 6 | 45 | 2 | 42 | 39 | 5 | 18
Required | [11 empty] | Required
Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff | Plumbing | Tiles | Painter | Ele | Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff
2025-12-04 | 20 | 15 | 15 | 15 | 45 | 1 | 5 | 2 | 5 | 3 | 4 | 2025-10-23 | 10 | 8 | 2 | 4 | 6 | 5 | 6
2025-12-05 | 15 | 15 | 15 | 16 | 45 | 1 | 5 | 2 | 5 | 3 | 4 | 2025-10-24 | 10 | 8 | 2 | 4 | 6 | 4 | 5
2025-12-06 | 15 | 15 | 15 | 15 | 45 | 1 | 5 | 2 | 6 | 3 | 4 | 2025-10-25 | 10 | 8 | 2 | 4 | 6 | 4 | 5
2025-12-07 | 15 | 20 | 15 | 16 | 45 | 1 | 3 | 2 | 8 | 3 | 4 | 2025-10-26 | 10 | 8 | 2 | 4 | 6 | 4 | 5
2025-12-08 | 15 | 20 | 15 | 18 | 45 | 1 | 5 | 2 | 8 | 3 | 4 | 2025-10-27 | 10 | 8 | 2 | 4 | 6 | 2 | 6
2025-12-09 | 20 | 20 | 15 | 18 | 45 | 4 | 6 | 0 | 8 | 3 | 6 | 2025-10-28 | 10 | 8 | 2 | 4 | 6 | 2 | 7
2025-12-10 | 20 | 20 | 15 | 18 | 45 | 4 | 4 | 0 | 8 | 3 | 6 | 2025-10-29 | 10 | 8 | 2 | 4 | 6 | 2 | 6
Total | 120 | 125 | 105 | 116 | 315 | 13 | 33 | 10 | 48 | 21 | 32 | Total | 70 | 56 | 14 | 28 | 42 | 5 | 40

## Project Cashflow
Month |  | Budgeted work | Planned Work | Actual Work
August | RA 01 |  | 5000000 | 1063955
September | RA 02 |  | 7200000 | 7797193
October | RA 03 |  | 5000000 | 168333
November | RA 04 |  | 7500000 | 2376171
December | RA 05 |  | 8000000 | 11104853
January | RA 06 |  | 9000000
February | RA 07 |  | 8000000
March | RA 08 |  | 8000000
57700000
Month |  |  | January
Planned
Actual

## Planned Vs Actual
Planned Vs Actual Previous Week to Current Week (Date: 11-12-2025 to 17-12-2025)
Description | [5 empty] | Qty Planed | [6 empty] | Against GFC | Agianst Weekly Planed |  | Cumlative | Cumlative
Sr.No. | Tower | Activity | Planned Start Date by Contractor | Planned End Date by Contractor | Unit | As per BOQ total Quantity | Total GFC Qty | Executed qty till 15-10-2025 | Balance Qty. | Weekly planned Qty. | Weekly actual Qty. | Cumulative Qty. | % Balance Qty ( Remaining ) Against GFC Qty | % Planned Against Balance Qty | % Achieved Against Actual Qty | % Completed (Total against the GFC ) | % Completed (Total against the GFC )
1 | Upto Plinth | Excavation | 2025-12-11 | 2025-12-17 | CUM | 3925 | 1826 | 1826.2 | -0.2 | 0 | 0 | 1826.2 | -0.01095% | 0% | 0% | Delay | 100%
2 |  | Footing PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 91.31 | 91.31 | 0 | 0 | 0 | 91.31 | 0% | 0% | 0% | On time | 100%
3 |  | Yellow Soil Filling | 2025-12-11 | 2025-12-17 | CUM | 10000 | 1123.22 | 1123.22 | 0 | 0 | 0 | 1123.22 | 0% | 0% | 0% |  | 100%
4 |  | Rubble Soling | 2025-12-11 | 2025-12-17 | CUM | 195.5 | 173.81 | 173.81 | 0 | 0 | 0 | 173.81 | 0% | 0% | 0% |  | 100%
5 |  | Footing Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 441.908 | 441.91 | -0.002 | 0 | 0 | 441.91 | -0.0004526% | 0% | 0% |  | 100%
6 |  | Footing RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 292.764 | 292.76 | 0.004 | 0 | 0 | 292.76 | 0.001366% | 0% | 0% | On time | 100%
7 |  | Padestal Upto Plinth Top Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 664 | 664 | 0 | 0 | 0 | 664 | 0% | 0% | 0% |  | 100%
8 |  | Padestal Upto Plinth Top RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 62.65 | 62.65 | 0 | 0 | 0 | 62.65 | 0% | 0% | 0% |  | 100%
9 |  | GB Excavation | 2025-12-11 | 2025-12-17 | CUM | 3925 | 11.795 | 11.795 | 0 | 0 | 0 | 11.795 | 0% | 0% | 0% |  | 100%
10 |  | GB PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 7.944 | 7.944 | 0 | 0 | 0 | 7.944 | 0% | 0% | 0% |  | 100%
11 |  | GB Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 142.938 | 142.85 | 0.088 | 0 | 0 | 142.85 | 0.06157% | 0% | 0% |  | 99.94%
12 |  | GB RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 23.994 | 23.98 | 0.014 | 0 | 0 | 23.98 | 0.05835% | 0% | 0% |  | 99.94%
13 |  | Masonry Above GB | 2025-12-11 | 2025-12-17 | CUM | 130 | 86.294 | 86.294 | 0 | 0 | 0 | 86.294 | 0% | 0% | 0% |  | 100%
14 |  | Plinth Beam PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 18.07 | 18.07 | 0 | 0 | 0 | 18.07 | 0% | 0% | 0% |  | 100%
15 |  | Plinth Beam Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 387.1 | 387.1 | 0 | 0 | 0 | 387.1 | 0% | 0% | 0% |  | 100%
16 |  | Plinth Beam RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 45.72 | 45.72 | 0 | 0 | 0 | 45.72 | 0% | 0% | 0% |  | 100%
17 |  | Plinth Plaster | 2025-12-11 | 2025-12-17 | SMT | 5235 | 92.29 | 59.5 | 32.79 | 32.79 | 15 | 74.5 | 35.53% | 100% | 45.75% |  | 80.72%
18 |  | Masonry above PB | 2025-12-11 | 2025-12-17 | CUM | 130 | 16.168 | 16.17 | -0.002 | 0 | 0 | 16.17 | -0.01237% | 0% | 0% |  | 100%
19 |  | Floor PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 86.9 | 86.9 | 0 | 0 | 0 | 86.9 | 0% | 0% | 0% |  | 100%
20 |  | Floor RCC Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 15.3 | 15.3 | 0 | 0 | 0 | 15.3 | 0% | 0% | 0% |  | 100%
21 |  | Floor RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 88.03 | 88.03 | 0 | 0 | 0 | 88.03 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 4.762% | 2.178% | #DIV/0! | 99.08%
22 | Ground Floor | Plinth to GF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 427.55 | 427.554 | -0.004 | 0 | 0 | 427.554 | -0.0009356% | 0% | 0% |  | 100%
23 |  | GF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
24 |  | GF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 664.23 | 0.03 | 0 | 0 | 664.23 | 0.004516% | 0% | 0% |  | 100%
25 |  | GF staircase shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
26 |  | GF lintel shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 67.99 | 56 | 11.99 | 0 | 0 | 56 | 17.63% | 0% | 0% |  | 82.37%
27 |  | Plinth to GF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 32.82 | 0.002 | 0 | 0 | 32.82 | 0.006093% | 0% | 0% |  | 99.99%
28 |  | GF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 61.75 | 0.01 | 0 | 0 | 61.75 | 0.01619% | 0% | 0% |  | 99.98%
29 |  | GF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 101.98 | 0.01 | 0 | 0 | 101.98 | 0.009805% | 0% | 0% |  | 99.99%
30 |  | GF staircase concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 8.52 | 0.01 | 0 | 0 | 8.52 | 0.1172% | 0% | 0% |  | 99.88%
31 |  | GF lintel Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 3.91 | 2 | 1.91 | 0 | 0 | 2 | 48.85% | 0% | 0% |  | 51.15%
32 |  | Brick masonary GF (230 mm) | 2025-12-11 | 2025-12-17 | CUM | 80 | 73.48 | 36.86 | 36.62 | 20 | 7 | 43.86 | 49.84% | 54.61% | 19.12% |  | 59.69%
33 |  | Brick masonary GF (115 mm) | 2025-12-11 | 2025-12-17 | SMT | 1170 | 768 | 346.26 | 421.74 | 100 | 10 | 356.26 | 54.91% | 23.71% | 2.371% |  | 46.39%
34 |  | Internal Plaster | 2025-12-11 | 2025-12-17 | SMT | 1591.21 | 1733.79 | 362 | 1371.79 | 600 | 301 | 663 | 79.12% | 43.74% | 21.94% |  | 38.24%
35 |  | Flooring | 2025-12-11 | 2025-12-17 | SMT | 830 | 841.16 | 0 | 841.16 | 100 | 55.15 | 55.15 | 100% | 11.89% | 6.556% |  | 6.556%
36 |  | Skirting | 2025-12-11 | 2025-12-17 | RMT | 1865 | 1859.2 | 0 | 1859.2 | 100 | 45 | 45 | 100% | 5.379% | 2.42% |  | 2.42%
Avreage Achivement : - | [13 empty] | 9.289% | 3.494% | #DIV/0! | 72.44%
37 | First Floor | GF to FF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 439.913 | 315 | 124.913 | 100 | 21.32 | 336.32 | 28.39% | 80.06% | 17.07% |  | 76.45%
38 |  | FF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 701 | -0.41 | 0 | 0 | 701 | -0.05852% | 0% | 0% |  | 100.1%
39 |  | FF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 664.26 | 0 | 0 | 0 | 664.26 | 0% | 0% | 0% |  | 100%
40 |  | FF Staircase Shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
41 |  | FF lintel shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 67.99 | 0 | 67.99 | 60 | 29 | 29 | 100% | 88.25% | 42.65% |  | 42.65%
42 |  | GF to FF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 25.81 | 7.012 | 0 | 0 | 25.81 | 21.36% | 0% | 0% |  | 78.64%
43 |  | FF Staircase Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
44 |  | FF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
45 |  | FF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
46 |  | FF lintel Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 3.91 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0%
47 |  | Brick masonary FF (230 mm) | 2025-12-11 | 2025-12-17 | CUM | 80 | 73.48 | 0 | 73.48 | 20 | 28.63 | 28.63 | 100% | 27.22% | 38.96% |  | 38.96%
48 |  | Brick masonary FF (115 mm) | 2025-12-11 | 2025-12-17 | SMT | 1170 | 768 | 0 | 768 | 300 | 174.55 | 174.55 | 100% | 39.06% | 22.73% |  | 22.73%
49 |  | Internal Plaster | 2025-12-11 | 2025-12-17 | SMT | 1591.21 | 1733.79 | 0 | 1733.79 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
50 |  | Flooring | 2025-12-11 | 2025-12-17 | SMT | 830 | 841.16 | 0 | 841.16 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
51 |  | Skirting | 2025-12-11 | 2025-12-17 | RMT | 1865 | 1859.2 | 0 | 1859.2 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
Avreage Achivement : - | [13 empty] | 15.64% | 8.094% | #DIV/0! | 57.3%
52 | Second Floor | FF to SF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 439.913 | 310.94 | 128.973 | 0 | 0 | 310.94 | 29.32% | 0% | 0% |  | 70.68% | 0.06
53 |  | SF Staircase Shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
54 |  | SF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
55 |  | SF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 664.26 | 0 | 0 | 0 | 664.26 | 0% | 0% | 0% |  | 100%
56 |  | FF to SF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 25.415 | 7.407 | 0 | 0 | 25.415 | 22.57% | 0% | 0% |  | 77.43%
57 |  | SF Staircase Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
58 |  | SF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
59 |  | SF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 93.51%
60 | Third Floor | SF to TF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 439.913 | 98 | 341.913 | 212 | 188.42 | 286.42 | 77.72% | 62% | 55.11% |  | 65.11% | 213
61 |  | TF Staircase Shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 0 | 57.39 | 30 | 30 | 30 | 100% | 52.27% | 52.27% |  | 52.27%
62 |  | TF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 0 | 700.59 | 400 | 350 | 350 | 100% | 57.09% | 49.96% |  | 49.96%
63 |  | TF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 0 | 664.26 | 400 | 180 | 180 | 100% | 60.22% | 27.1% |  | 27.1%
64 |  | SF to TF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 2.58 | 30.242 | 30 | 18 | 20.58 | 92.14% | 99.2% | 59.52% |  | 62.7%
65 |  | TF Staircase Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 0 | 8.53 | 5 | 2.1 | 2.1 | 100% | 58.62% | 24.62% |  | 24.62%
66 |  | TF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 0 | 61.76 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
67 |  | TF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 0 | 101.99 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
Avreage Achivement : - | [13 empty] | 48.68% | 33.57% | #DIV/0! | 35.22%
Cumulative Avreage Achivement : - | [13 empty] | 15.67% | 9.468% | #DIV/0! | 71.51%

## As per drawing status
Weekly Executed Plan
Sr.No. | Tower | Activity | Unit | As per BOQ total Quantity | As per GFC total Quantity | Weekly planned Qty. | Weekly actual Qty. | Total Achieved Qty.
1 | Worker Dormitory | Footing Excavation | CUM | 3925 | 1826 | 0 | 0 | 1826.2
2 | Worker Dormitory | GB Excavation | CUM |  | 11.795 | 0 | 0 | 11.795
3 | Worker Dormitory | Yellow Soil Filling | CUM | 10000 | 1123.22 | 0 | 0 | 1123.22
4 | Worker Dormitory | Rubble Soling | CUM | 195.5 | 173.81 | 0 | 0 | 173.81
5 | Worker Dormitory | Footing PCC | CUM | 265 | 91.31 | 0 | 0 | 91.31
6 | Worker Dormitory | GB PCC | CUM |  | 7.944 | 0 | 0 | 7.944
7 | Worker Dormitory | Floor PCC | CUM |  | 86.9 | 0 | 0 | 86.9
8 | Worker Dormitory | Plinth Beam PCC | CUM |  | 18.07 | 0 | 0 | 18.07
9 | Worker Dormitory | Footing RCC | CUM | 380 | 292.764 | 0 | 0 | 292.76
10 | Worker Dormitory | Pedestal RCC | CUM |  | 62.65 | 0 | 0 | 62.65
11 | Worker Dormitory | GB RCC | CUM |  | 23.994 | 0 | 0 | 23.98
12 | Worker Dormitory | Plinth Beam RCC | CUM |  | 45.72 | 0 | 0 | 45.72
13 | Worker Dormitory | Floor RCC | CUM |  | 88.03 | 0 | 0 | 88.03
14 | Worker Dormitory | Masonry Above GB | CUM | 130 | 86.294 | 0 | 0 | 86.294
15 | Worker Dormitory | Masonry above PB | CUM |  | 16.168 | -0.002 | 0 | 16.17
16 | Worker Dormitory | Plinth Plaster | SMT | 5235 | 92.29 | 32.79 | 15 | 74.5
17 | Worker Dormitory | Footing Shuttering | SMT | 1075 | 441.908 | 0 | 0 | 0
18 | Worker Dormitory | Padestal Upto Plinth Top Shuttering | SMT |  | 664 | 0 | 0 | 664
19 | Worker Dormitory | GB Shuttering | SMT |  | 142.938 | 0 | 0 | 142.85
20 | Worker Dormitory | Plinth Beam Shuttering | SMT |  | 387.1 | 0 | 0 | 387.1
21 | Worker Dormitory | Floor RCC Shuttering | SMT |  | 15.3 | 0 | 0 | 15.3
22 | Worker Dormitory | Plinth to GF slab column shuttering | SQM | 1680 | 427.55 | 0 | 0 | 427.554
23 | Worker Dormitory | GF beam shuttering | SQM |  | 700.59 | 0 | 0 | 700.59
24 | Worker Dormitory | GF Slab shuttering | SQM |  | 664.26 | 0 | 0 | 664.23
25 | Worker Dormitory | GF staircase shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
26 | Worker Dormitory | GF lintel shuttering | SQM |  | 67.99 | 0 | 0 | 56
27 | Worker Dormitory | Plinth to GF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 32.82
28 | Worker Dormitory | GF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.75
29 | Worker Dormitory | GF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.98
30 | Worker Dormitory | GF staircase concrete | CUM |  | 8.53 | 0 | 0 | 8.52
31 | Worker Dormitory | GF lintel Concrete | CUM |  | 3.91 | 0 | 0 | 2
32 | Worker Dormitory | Brick masonary GF (230 mm) | CUM | 80 | 73.48 | 20 | 7 | 43.86
33 | Worker Dormitory | Brick masonary GF (115 mm) | SMT | 1170 | 768 | 100 | 10 | 356.26
34 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 1733.79 | 600 | 301 | 663
35 | Worker Dormitory | Flooring | SMT | 830 | 841.16 | 100 | 55.15 | 55.15
36 | Worker Dormitory | Skirting | RMT | 1865 | 1859.2 | 100 | 45 | 45
37 | Worker Dormitory | GF to FF slab column shuttering | SQM | 1680 | 439.913 | 100 | 21.32 | 336.32
38 | Worker Dormitory | FF beam shuttering | SQM |  | 700.59 | 0 | 0 | 701
39 | Worker Dormitory | FF Slab shuttering | SQM |  | 664.26 | 0 | 0 | 664.26
40 | Worker Dormitory | FF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
41 | Worker Dormitory | FF lintel shuttering | SQM |  | 67.99 | 60 | 29 | 29
42 | Worker Dormitory | GF to FF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 25.81
43 | Worker Dormitory | FF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
44 | Worker Dormitory | FF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
45 | Worker Dormitory | FF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
46 | Worker Dormitory | FF lintel Concrete | CUM |  | 3.91 | 0 | 0 | 0
47 | Worker Dormitory | Brick masonary FF (230 mm) | CUM | 80 | 73.48 | 0 | 28.63 | 20
48 | Worker Dormitory | Brick masonary FF (115 mm) | SMT | 1170 | 768 | 0 | 174.55 | 300
49 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 1733.79 | 0 | 0 | 0
50 | Worker Dormitory | Flooring | SMT | 830 | 841.16 | 0 | 0 | 0
51 | Worker Dormitory | Skirting | RMT | 1865 | 1859.2 | 0 | 0 | 0
52 | Worker Dormitory | FF to SF slab column shuttering | SQM | 1680 | 439.913 | 0 | 0 | 101.99
53 | Worker Dormitory | SF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 310.94
54 | Worker Dormitory | SF beam shuttering | SQM |  | 700.59 | 0 | 0 | 57.39
55 | Worker Dormitory | SF Slab shuttering | SQM |  | 664.26 | 0 | 0 | 57.39
56 | Worker Dormitory | FF to SF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 25.415
57 | Worker Dormitory | SF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
58 | Worker Dormitory | SF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
59 | Worker Dormitory | SF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
60 | Worker Dormitory | SF to TF slab column shuttering | SQM | 1680 | 439.913 | 212 | 188.42 | 286.42
61 | Worker Dormitory | TF Staircase Shuttering | SQM |  | 57.39 | 30 | 30 | 30
62 | Worker Dormitory | TF beam shuttering | SQM |  | 700.59 | 400 | 350 | 350
63 | Worker Dormitory | TF Slab shuttering | SQM |  | 664.26 | 400 | 180 | 180
64 | Worker Dormitory | SF to TF slab column concrete | CUM | 210 | 32.822 | 30 | 18 | 20.58
65 | Worker Dormitory | TF Staircase Concrete | CUM |  | 8.53 | 5 | 2.1 | 2.1
66 | Worker Dormitory | TF beam Concrete | CUM |  | 61.76 | 0 | 0 | 0
67 | Worker Dormitory | TF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 0
Weekly planned Qty. | (Multiple Items)
Weekly actual Qty. | (Multiple Items)
Activity | Sum of Weekly planned Qty. | Sum of Weekly actual Qty. | Sum of Total Achieved Qty. |  | Row Labels | Sum of Weekly planned Qty. | Sum of Weekly actual Qty.
Brick masonary GF (115 mm) | 100 | 10 | 356.26 |  | CUM | 54.998 | 55.73
Brick masonary GF (230 mm) | 20 | 7 | 43.86 |  | RMT | 100 | 45
FF lintel shuttering | 60 | 29 | 29 |  | SMT | 832.79 | 555.7
Flooring | 100 | 55.15 | 55.15 |  | SQM | 1202 | 798.74
GF to FF slab column shuttering | 100 | 21.32 | 336.32 |  | Grand Total | 2189.788 | 1455.17
Internal Plaster | 600 | 301 | 663
Plinth Plaster | 32.79 | 15 | 74.5
SF to TF slab column concrete | 30 | 18 | 20.58
SF to TF slab column shuttering | 212 | 188.42 | 286.42
Skirting | 100 | 45 | 45
TF beam shuttering | 400 | 350 | 350
TF Slab shuttering | 400 | 180 | 180
TF Staircase Concrete | 5 | 2.1 | 2.1
TF Staircase Shuttering | 30 | 30 | 30
Grand Total | 2189.79 | 1251.99 | 2472.19
Manually
Activity | Sum of Weekly planned Qty. | Sum of Weekly actual Qty. | % Completed
Brick masonary GF (115 mm) | 100 | 10 | 10%
Brick masonary GF (230 mm) | 20 | 7 | 35%
FF lintel shuttering | 60 | 29 | 48.33%
Flooring | 100 | 55.15 | 55.15% |  | Row Labels | Sum of As per GFC total Quantity | Sum of Total Achieved Qty.
GF to FF slab column shuttering | 100 | 21.32 | 21.32% |  | CUM | 4929.857 | 4644.248
Internal Plaster | 600 | 301 | 50.17% |  | RMT | 3718.4 | 45
Plinth Plaster | 32.79 | 15 | 45.75% |  | SMT | 8429.436 | 2658.16
SF to TF slab column concrete | 30 | 18 | 60% |  | SQM | 7572.229 | 5067.864
SF to TF slab column shuttering | 212 | 188.42 | 88.88% |  | Grand Total | 24649.922 | 12415.272
Skirting | 100 | 45 | 45%
TF beam shuttering | 400 | 350 | 87.5%
TF Slab shuttering | 400 | 180 | 45%
TF Staircase Concrete | 5 | 2.1 | 42%
TF Staircase Shuttering | 30 | 30 | 100%
Manually
Type | Sum of As per GFC total Quantity | Sum of Total Achieved Qty.
CUM | 4929.857 | 4644.248
Weekly planned Qty. | (Multiple Items)
Activity | Planned Start Date by Contractor | Sum of % Planned Against Balance Qty | Sum of % Achieved Against Actual Qty | Sum of % Completed (Total against the GFC )2
Brick masonary FF (115 mm) | 2025-12-11 | 39.06% | 22.73% | 22.73%
Brick masonary FF (230 mm) | 2025-12-11 | 27.22% | 38.96% | 38.96%
Brick masonary GF (115 mm) | 2025-12-11 | 23.71% | 2.371% | 46.39%
Brick masonary GF (230 mm) | 2025-12-11 | 54.61% | 19.12% | 59.69%
FF lintel shuttering | 2025-12-11 | 88.25% | 42.65% | 42.65%
Flooring | 2025-12-11 | 11.89% | 6.556% | 6.556%
GF to FF slab column shuttering | 2025-12-11 | 80.06% | 17.07% | 76.45%
Internal Plaster | 2025-12-11 | 43.74% | 21.94% | 38.24%
Plinth Plaster | 2025-12-11 | 100% | 45.75% | 80.72%
SF to TF slab column concrete | 2025-12-11 | 99.2% | 59.52% | 62.7%
SF to TF slab column shuttering | 2025-12-11 | 62% | 55.11% | 65.11%
Skirting | 2025-12-11 | 5.379% | 2.42% | 2.42%
TF beam shuttering | 2025-12-11 | 57.09% | 49.96% | 49.96%
TF Slab shuttering | 2025-12-11 | 60.22% | 27.1% | 27.1%
TF Staircase Concrete | 2025-12-11 | 58.62% | 24.62% | 24.62%
TF Staircase Shuttering | 2025-12-11 | 52.27% | 52.27% | 52.27%
Grand Total |  | 863.3% | 488.1% | 696.6%

## Quality SOR Log
Sr.no. | Observation | Total | Open | Close | Closure Rate | Sr. No. | Name of Equipment | Unit | Total Number
1 | Site Observation | 75 | 10 | 65 | 86.67% | 1 | Compression Testing Machine | No | 1
2 | Site Instruction | 75 | 5 | 70 | 93.33% | 2 | Slump Cone Test Apparatus | Set | 1
3 | NCR | 1 | 0 | 1 | 100% | 3 | Steel Moulds | No | 25
|  |  |  | Average | 93.33% | 4 | Digital Moisture Meter | No | 1
[6 empty] | 5 | Weighing Balance | No | 1
[6 empty] | 6 | Thermometer | No | 1
Sr.no. | Observation | Open | Close
1 | Site Observation | 10 | 65
Sr.no. | Observation | Open | Close
2 | Site Instruction | 5 | 70
Sr.no. | Observation | Open | Close
3 | NCR | 0 | 1

## Risk Register
Step 1: Risk Identification | [5 empty] | Step 2: Risk Assessment | [5 empty] | Step 3: Risk Response |  |  |  | Step 4: Monitor & Control
# | Category | Opportunity / Threat | Risk Name | Detailed Description | Probability (1 - 5) | Consequence (1-5) | Severity (Priority) | Probability (%) | Cost Impact (₹) | Most Likely (no. of weeks) | Urgency | Response Category | Impact | Risk Owner | Contingency Plan | Status | Date Last Updated | Tracking Comments
R1 | Execution | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 1000 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-02-27 | NA
R2 | Planning/ Scope | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 3 | 2 | 6 | 30% | 2000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-04 | NA
R3 | Communications | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 1 | 5 | 40% | 3000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-22 | NA
R4 | Schedule | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 3 | 12 | 50% | 100 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-02-27 | NA
R5 | Estimating | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 2 | 5 | 10 | 10% | 5000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-04 | NA
R6 | Controlling | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 2 | 10 | 20% | 6000 | 1 | Medium | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-22 | NA
R7 | Planning/ Scope | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 4 | 16 | 30% | 10000 | 1 | High | Share | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-27 | NA
R8 | Communications | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 2000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-03-04 | NA
R9 | Schedule | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 50% | 8000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-02-22 | NA
R10 | Esxecution | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 20% | 3000 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-27 | NA
R11 | Controlling | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 30% | 3500 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-03-04 | NA
R12 | Planning/ Scope | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 40% | 6480 | 1 | Medium | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-02-22 | NA
R13 | Communications | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 3 | 3 | 50% | 6500 | 1 | High | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-02-27 | NA
R14 | Schedule | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 4 | 20 | 20% | 9000 | 1 | Low | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-04 | NA
R15 | Estimating | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 3 | 12 | 30% | 8750 | 1 | Medium | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-22 | NA
R16 | Controlling | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 250 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-02-27 | NA
R17 | Planning/ Scope | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 100 | 1 | Low | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-04 | NA
R18 | Communications | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 600 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-22 | NA
R19 | Schedule | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 4 | 20 | 30% | 13000 | 1 | High | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-27 | NA
R20 | Esxecution | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 26000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-03-04 | NA
R21 | Controlling | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 14500 | 1 | Medium | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-02-22 | NA
R22 | Planning/ Scope | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 18000 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-27 | NA
R23 | Communications | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 30% | 21500 | 1 | Low | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-03-04 | NA
R24 | Schedule | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 1450 | 1 | Medium | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-02-22 | NA
R25 | Esxecution | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 1000 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-02-27 | NA
R26 | Controlling | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 6200 | 1 | Low | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-04 | NA
R27 | Planning/ Scope | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 30% | 1000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-22 | NA
R28 | Communications | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 1000 | 1 | High | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-02-27 | NA
R29 | Schedule | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 1000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-04 | NA
R30 | Esxecution | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 1000 | 1 | Medium | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-22 | NA

## Site Instruction
Site Instruction Report
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. | [6 empty] | Updated On:
Report No |  | Safari-Safety Instruction-Sharnam-001 | [5 empty] | Total Open | 6 | Total Closed | 17
S. No | Location | Issued by | Issued to | Issued on | Brief Description | category | Action taken | Status | Time Impact (Y/N) | Cost Impact (Y/N) | Remarks | Yes | Open
1 | Building A | Sharnam PMC | Shapoorji | 2025-12-15 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-18 | Closed | Yes | Yes |  | No | Closed
2 | Building B | Sharnam PMC | Shapoorji | 2025-12-16 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-19 | Closed | Yes | Yes
3 | Building A | Sharnam PMC | Shapoorji | 2025-12-17 | Material is not stacked properly itemwise. | Material | 2024-12-20 | Closed | Yes | Yes
4 | Building B | Sharnam PMC | Shapoorji | 2025-12-18 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
5 | Building A | Sharnam PMC | Shapoorji | 2025-12-19 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-21 | Closed | Yes | Yes
6 | Building B | Sharnam PMC | Shapoorji | 2025-12-20 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-22 | Open | Yes | Yes
7 | Building A | Sharnam PMC | Shapoorji | 2025-12-21 | Material is not stacked properly itemwise. | Material | 2024-12-23 | Closed | Yes | Yes
8 | Building B | Sharnam PMC | Shapoorji | 2025-12-22 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
9 | Building A | Sharnam PMC | Shapoorji | 2025-12-23 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-24 | Closed | Yes | Yes
10 | Building B | Sharnam PMC | Shapoorji | 2025-12-24 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-25 | Closed | Yes | Yes
11 | Building A | Sharnam PMC | Shapoorji | 2025-12-25 | Material is not stacked properly itemwise. | Material | 2024-12-26 | Closed | Yes | Yes
12 | Building B | Sharnam PMC | Shapoorji | 2025-12-26 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
13 | Building A | Sharnam PMC | Shapoorji | 2025-12-27 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-27 | Closed | Yes | Yes
14 | Building B | Sharnam PMC | Shapoorji | 2025-12-28 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-28 | Closed | Yes | Yes
15 | Building A | Sharnam PMC | Shapoorji | 2025-12-29 | Material is not stacked properly itemwise. | Material | 2024-12-29 | Closed | Yes | Yes
16 | Building B | Sharnam PMC | Shapoorji | 2025-12-30 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
17 | Building A | Sharnam PMC | Shapoorji | 2025-12-31 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-30 | Closed | Yes | Yes
18 | Building B | Sharnam PMC | Shapoorji | 2026-01-01 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-31 | Closed | Yes | Yes
19 | Building A | Sharnam PMC | Shapoorji | 2026-01-02 | Material is not stacked properly itemwise. | Material | 2025-01-01 | Closed | Yes | Yes
20 | Building B | Sharnam PMC | Shapoorji | 2026-01-03 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
21 | Building A | Sharnam PMC | Shapoorji | 2026-01-04 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2025-01-02 | Closed | Yes | Yes
22 | Building B | Sharnam PMC | Shapoorji | 2026-01-05 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2025-01-03 | Closed | Yes | Yes
23 | Building A | Sharnam PMC | Shapoorji | 2026-01-06 | Material is not stacked properly itemwise. | Material | 2025-01-04 | Closed | Yes | Yes

## Unsafe Act Summary
Unsafe Act Summary
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. | [6 empty] | Updated On:
Report No |  | Safari-Safety Observation Unsafe Act-Sharnam-001 | [5 empty] | Total Open | 39 | Total Closed | 43
S. No | Location | Issued By | Issued To | Issued On | Brief Description | Category | Action Taken | Status | Time Impact (Y/N) | Cost Impact (Y/N) | Remarks
1 | Building A | Sharnam PMC | Shapoorji | 2025-12-15 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
2 | Building B | Sharnam PMC | Shapoorji | 2025-12-16 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
3 | Building A | Sharnam PMC | Shapoorji | 2025-12-17 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
4 | Building B | Sharnam PMC | Shapoorji | 2025-12-18 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
5 | Building A | Sharnam PMC | Shapoorji | 2025-12-19 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
6 | Building B | Sharnam PMC | Shapoorji | 2025-12-20 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
7 | Building A | Sharnam PMC | Shapoorji | 2025-12-21 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
8 | Building B | Sharnam PMC | Shapoorji | 2025-12-22 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
9 | Building A | Sharnam PMC | Shapoorji | 2025-12-23 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
10 | Building B | Sharnam PMC | Shapoorji | 2025-12-24 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Open | Yes | Yes
11 | Building A | Sharnam PMC | Shapoorji | 2025-12-25 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
12 | Building B | Sharnam PMC | Shapoorji | 2025-12-26 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Open | Yes | Yes
13 | Building A | Sharnam PMC | Shapoorji | 2025-12-27 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
14 | Building B | Sharnam PMC | Shapoorji | 2025-12-28 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Open | Yes | Yes
15 | Building A | Sharnam PMC | Shapoorji | 2025-12-29 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
16 | Building B | Sharnam PMC | Shapoorji | 2025-12-30 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
17 | Building A | Sharnam PMC | Shapoorji | 2025-12-31 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
18 | Building B | Sharnam PMC | Shapoorji | 2026-01-01 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
19 | Building A | Sharnam PMC | Shapoorji | 2026-01-02 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
20 | Building B | Sharnam PMC | Shapoorji | 2026-01-03 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
21 | Building A | Sharnam PMC | Shapoorji | 2026-01-04 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
22 | Building B | Sharnam PMC | Shapoorji | 2026-01-05 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
23 | Building A | Sharnam PMC | Shapoorji | 2026-01-06 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
24 | Building B | Sharnam PMC | Shapoorji | 2026-01-07 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
25 | Building A | Sharnam PMC | Shapoorji | 2026-01-08 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
26 | Building B | Sharnam PMC | Shapoorji | 2026-01-09 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
27 | Building A | Sharnam PMC | Shapoorji | 2026-01-10 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
28 | Building B | Sharnam PMC | Shapoorji | 2026-01-11 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
29 | Building A | Sharnam PMC | Shapoorji | 2026-01-12 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
30 | Building B | Sharnam PMC | Shapoorji | 2026-01-13 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
31 | Building A | Sharnam PMC | Shapoorji | 2026-01-14 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
32 | Building B | Sharnam PMC | Shapoorji | 2026-01-15 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
33 | Building A | Sharnam PMC | Shapoorji | 2026-01-16 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
34 | Building B | Sharnam PMC | Shapoorji | 2026-01-17 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
35 | Building A | Sharnam PMC | Shapoorji | 2026-01-18 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
36 | Building B | Sharnam PMC | Shapoorji | 2026-01-19 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
37 | Building A | Sharnam PMC | Shapoorji | 2026-01-20 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
38 | Building B | Sharnam PMC | Shapoorji | 2026-01-21 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
39 | Building A | Sharnam PMC | Shapoorji | 2026-01-22 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
40 | Building B | Sharnam PMC | Shapoorji | 2026-01-23 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
41 | Building A | Sharnam PMC | Shapoorji | 2026-01-24 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
42 | Building B | Sharnam PMC | Shapoorji | 2026-01-25 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
43 | Building A | Sharnam PMC | Shapoorji | 2026-01-26 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
44 | Building B | Sharnam PMC | Shapoorji | 2026-01-27 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
45 | Building A | Sharnam PMC | Shapoorji | 2026-01-28 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
46 | Building B | Sharnam PMC | Shapoorji | 2026-01-29 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
47 | Building A | Sharnam PMC | Shapoorji | 2026-01-30 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
48 | Building B | Sharnam PMC | Shapoorji | 2026-01-31 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
49 | Building A | Sharnam PMC | Shapoorji | 2026-02-01 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
50 | Building B | Sharnam PMC | Shapoorji | 2026-02-02 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
51 | Building A | Sharnam PMC | Shapoorji | 2026-02-03 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
52 | Building B | Sharnam PMC | Shapoorji | 2026-02-04 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
53 | Building A | Sharnam PMC | Shapoorji | 2026-02-05 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
54 | Building B | Sharnam PMC | Shapoorji | 2026-02-06 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
55 | Building A | Sharnam PMC | Shapoorji | 2026-02-07 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
56 | Building B | Sharnam PMC | Shapoorji | 2026-02-08 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
57 | Building A | Sharnam PMC | Shapoorji | 2026-02-09 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
58 | Building B | Sharnam PMC | Shapoorji | 2026-02-10 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
59 | Building A | Sharnam PMC | Shapoorji | 2026-02-11 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
60 | Building B | Sharnam PMC | Shapoorji | 2026-02-12 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
61 | Building A | Sharnam PMC | Shapoorji | 2026-02-13 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
62 | Building B | Sharnam PMC | Shapoorji | 2026-02-14 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
63 | Building A | Sharnam PMC | Shapoorji | 2026-02-15 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
64 | Building B | Sharnam PMC | Shapoorji | 2026-02-16 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
65 | Building A | Sharnam PMC | Shapoorji | 2026-02-17 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
66 | Building B | Sharnam PMC | Shapoorji | 2026-02-18 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
67 | Building A | Sharnam PMC | Shapoorji | 2026-02-19 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
68 | Building B | Sharnam PMC | Shapoorji | 2026-02-20 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
69 | Building A | Sharnam PMC | Shapoorji | 2026-02-21 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
70 | Building B | Sharnam PMC | Shapoorji | 2026-02-22 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
71 | Building A | Sharnam PMC | Shapoorji | 2026-02-23 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
72 | Building B | Sharnam PMC | Shapoorji | 2026-02-24 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
73 | Building A | Sharnam PMC | Shapoorji | 2026-02-25 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
74 | Building B | Sharnam PMC | Shapoorji | 2026-02-26 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
75 | Building A | Sharnam PMC | Shapoorji | 2026-02-27 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
76 | Building B | Sharnam PMC | Shapoorji | 2026-02-28 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
77 | Building A | Sharnam PMC | Shapoorji | 2026-03-01 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
78 | Building B | Sharnam PMC | Shapoorji | 2026-03-02 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
79 | Building A | Sharnam PMC | Shapoorji | 2026-03-03 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
80 | Building B | Sharnam PMC | Shapoorji | 2026-03-04 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
81 | Building A | Sharnam PMC | Shapoorji | 2026-03-05 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
82 | Building B | Sharnam PMC | Shapoorji | 2026-03-06 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes

## NCR Summary
NCR Summary
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. | [6 empty] | Updated On:
Report No |  | Safari-Safety Observation Unsafe Act-Sharnam-001 | [5 empty] | Total Open | 11 | Total Closed | 5
S. No | Location | Issued By | Issued To | Issued On | Brief Description | NC Category | Action Taken by PMC | Status | Time Impact (Days) | Cost Impact (INR) | Remarks
1 | Building A | Sharnam PMC | Shapoorji | 2025-12-15 | Unsafe Act at Excavation | Near Miss | Closed the work | Open | No | No
2 | Building B | Sharnam PMC | Shapoorji | 2025-12-16 | Unsafe Act at 5th floor | Harassment | Provided PPE kit to Worker | Closed | Yes | Yes
3 | Building A | Sharnam PMC | Shapoorji | 2025-12-17 | Unsafe Act at Excavation | Psychological | Closed the work | Open | No | No
4 | Building B | Sharnam PMC | Shapoorji | 2025-12-18 | Unsafe Act at 5th floor | Illness | Provided PPE kit to Worker | Closed | Yes | Yes
5 | Building A | Sharnam PMC | Shapoorji | 2025-12-19 | Unsafe Act at Excavation | Injury | Closed the work | Open | No | No
6 | Building B | Sharnam PMC | Shapoorji | 2025-12-20 | Unsafe Act at 5th floor | Near Miss | Provided PPE kit to Worker | Closed | Yes | Yes
7 | Building A | Sharnam PMC | Shapoorji | 2025-12-21 | Unsafe Act at Excavation | Harassment | Closed the work | Open | No | No
8 | Building B | Sharnam PMC | Shapoorji | 2025-12-22 | Unsafe Act at 5th floor | Psychological | Provided PPE kit to Worker | Closed | Yes | Yes
9 | Building A | Sharnam PMC | Shapoorji | 2025-12-23 | Unsafe Act at Excavation | Illness | Closed the work | Open | No | No
10 | Building B | Sharnam PMC | Shapoorji | 2025-12-24 | Unsafe Act at 5th floor | Injury | Provided PPE kit to Worker | Open | Yes | Yes
11 | Building A | Sharnam PMC | Shapoorji | 2025-12-25 | Unsafe Act at Excavation | Near Miss | Closed the work | Open | No | No
12 | Building B | Sharnam PMC | Shapoorji | 2025-12-26 | Unsafe Act at 5th floor | Harassment | Provided PPE kit to Worker | Open | Yes | Yes
13 | Building A | Sharnam PMC | Shapoorji | 2025-12-27 | Unsafe Act at Excavation | Psychological | Closed the work | Open | No | No
14 | Building B | Sharnam PMC | Shapoorji | 2025-12-28 | Unsafe Act at 5th floor | Illness | Provided PPE kit to Worker | Open | Yes | Yes
15 | Building A | Sharnam PMC | Shapoorji | 2025-12-29 | Unsafe Act at Excavation | Injury | Closed the work | Open | No | No
16 | Building B | Sharnam PMC | Shapoorji | 2025-12-30 | Unsafe Act at 5th floor | Near Miss | Provided PPE kit to Worker | Closed | Yes | Yes

## Safety Hours
Safe Hours Summary
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. |  |  |  | Updated On:
Report No |  | Safari-Safety Observation Unsafe Act-Sharnam-001 |  |  | Project Start Date | 2025-12-01 | Last Accident Date | 2025-12-28 | 27
Sr.No | HSE indicators | Up to Previous Week (PW) | Current Week (CW) | Cumulative
1 | Safe-manhours | 7670 | 1350 | 9020
2 | Safe-man-days | 20 | 7 | 27
3 | Toolbox Talk | 32 | 7 | 39
4 | HSE induction | 17 | 2 | 19
5 | HSE trainings | 4 | 0 | 4
6 | Reported Incident/Accident | 1 | 0 | 1
7 | Site safety Instructions | 91 | 5 | 96
8 | NCN Raised | 2 | 0 | 2
9 | SOR Raised | 0 | 0 | 0
10 | FAC | 0 | 0 | 0
11 | Near Miss | 2 | 0 | 2
Sr.No | HSE indicators | Up to Previous Week (PW) | Current Week (CW) | Cumulative
1 | Safe-manhours | 76704 | 5192 | 81896
2 | Safe-man-days | 140 | 7 | 147
3 | Toolbox Talk | 32 | 2 | 34
4 | HSE induction | 17 | 0 | 17
5 | HSE trainings | 4 | 0 | 4
6 | Reported Incident/Accident | 0 | 0 | 0
7 | Site safety Instructions | 91 | 5 | 96
8 | NCN Raised | 2 | 0 | 2
9 | SOR Raised | 0 | 0 | 0
10 | FAC | 0 | 0 | 0
11 | Near Miss | 2 | 0 | 2
Sr.No | HSE indicators | Up to Previous Week (PW) | Current Week (CW) | Cumulative

## NCR
Site Safety Non Conformity Report
Name of Project | Safari Industrial Project at Halol GIDC
Name of Client | Safari India Pvt. Ltd.
Principle Consultant | Sharnam Project Development Consultant
PMC | Sharnam Project Development Consultant
Vendor | Shapoorji Pallonji Construction Pvt. Ltd. |  |  |  |  | Updated On:
NCR No | Safari-Safety NCR-Sharnam-001
Non-Conformity Safety Details
Activity/Task | [E.g., Excavation, Lifting, Electrical Work]
Non-Conformity Description | [Detailed explanation of the unsafe condition or action observed]
Category | [E.g., Working at Heights, PPE Non-Compliance, Housekeeping, Electrical Hazard, etc.]
Observed Risk Level | FALSE | Low | FALSE | Medium | FALSE | High
Photos/Attachments | [Attach relevant photos, sketches, or supporting documents]
Root Cause Analysis
Root Cause | [E.g., Lack of training, inadequate supervision, poor planning, defective equipment, etc.]
Contributing Factors | [Other issues that may have led to the non-conformity]
Corrective Actions
Immediate Action Taken | [Steps taken immediately to mitigate the risk or resolve the issue]
Long-Term Corrective Action | [Preventive measures to ensure the issue doesn’t reoccur]
Responsible Party | [Name or department responsible for corrective actions]
Target Completion Date | [DD/MM/YYYY]
Impact Assessment
Time Impact (Y/N) | [Yes/No, specify the extent of delay if applicable]
Cost Impact (Y/N) | [Yes/No, specify the estimated cost impact if applicable]
Follow-Up and Close-Out
Follow-Up Date | [DD/MM/YYYY]
Status | FALSE | Open
| FALSE | In Progress
| FALSE | Closed
Prepared By | Name: ______________
Signature: ____________
Reviewed By | Name: ______________
Signature: ____________ (Safety Officer)
Approved By | Name: ______________
Signature: ____________ (Project Manager)

## Observation - Unsafe Act
Site Unsafe Act Report
Name of Project | Safari Industrial Project at Halol GIDC
Name of Client | Safari India Pvt. Ltd.
Principle Consultant | Sharnam Project Development Consultant
PMC | Sharnam Project Development Consultant
Vendor | Shapoorji Pallonji Construction Pvt. Ltd. |  | Updated On:
Report No | Safari-Safety Observation Unsafe Act-Sharnam-001
Unsafe Act Details
Type of Unsafe Act | FALSE | Working at height
| FALSE | Improper tool use
| FALSE | Non-compliance with PPE
| FALSE | Poor housekeeping
| FALSE | Electrical hazards
| FALSE | Others: [Specify]
Description | [Brief details of the unsafe act, including location and task being performed.]
Location | Building A
Actions & Evidence
Immediate Action Taken | [E.g., Stopped work, provided PPE, isolated the hazard.]
Responsible Person | [Name & Role]
Photos/Sketches | [Attach if available]
Witnesses | [List of any witnesses with roles]
Risk & Recommendations
Risk Level | FALSE | Low
| FALSE | Medium
| FALSE | High
Consequences | [Injury, fatality, equipment damage, project delay, etc.]
Corrective Measures | [Long-term actions like training, new procedures, or equipment repair.]
Responsible Person/Dept. | [Name or department]
Deadline | [Specify timeline for rectification]
Follow-Up & Approvals
Follow-Up Date | [DD/MM/YYYY]
Status | FALSE | Open
| FALSE | In Progress
| FALSE | Closed
Prepared By | Name: ______________
Signature: ____________
Reviewed By | Name: ______________
Signature: ____________ (Safety Officer)
Approved By | Name: ______________
Signature: ____________ (Project Manager)

## HIRA
#VALUE! |  | Hazard Identification & Risk Assessment
|  | Sharnam Project Development Consultants | [10 empty] | ID No :
Revision :
Name of Project: Safari Industrial Plant |  |  | Location: Halol GIDC |  | Activity: Execution |  |  |  | Approved By: |  |  |  | Date:
Sr. No. | Activity | Risk ID | Hazard | Consequence | Legal Concerns (Y/N) | Risk Analysis |  |  | Control Measure | Residual Risk |  |  | Remarks if any
[6 empty] | Probability | Impact | Severity |  | Probability | Impact | Severity
A | Person working too close to the edge of excavationn | A1 | Fall of person into excavation | Major Injury | Yes | 3 | 3 | 9 | Barricading shall be provided. | 2 | 3 | 6
B | Improper house-keeping | B1 | Injury to personnel working near-by | Minor Injury | No | 3 | 2 | 6 | Proper house keeping shall be maintained | 2 | 2 | 4
C | Concreting | C1 | Earthing of vibrators not done | Can Cause short circuit | No | 3 | 2 | 6 | Ensure earthing of equipment before commencement of work | 1 | 2 | 2
|  | C2 | Continuous pouring by same gang | Cause tiredness of workers and may lead to accident | No | 2 | 3 | 6 | Insist on shift patterns | 1 | 3 | 3
D | Bar Bending & Bar Cutting Machine | D1 | Inexperienced operator | Major Injury | No | 3 | 3 | 9 | Ensure complete trained operator to be deployed. | 1 | 3 | 3
|  | D2 | Defective machine | Major Injury | Yes | 3 | 3 | 9 | Check machine condition before start | 2 | 3 | 6
|  | D3 | Loose Electrical connection | Fire/Short circuit | Yes | 3 | 3 | 9 | Electrical connection should connected with ELCB | 1 | 3 | 3
|  | D4 | Electrical shock | Fire/Short circuit | Yes | 3 | 2 | 6 | Body Earthing provided to machine | 1 | 3 | 3
|  | D5 | Hit by material | Minor Injury | Yes | 2 | 3 | 6 | Trained operator prrovided | 1 | 3 | 3
|  | D6 | Defective blades | Minor Injury | No | 2 | 1 | 2 | Check blade condition | 1 | 1 | 1
E | Reinforcement work | E1 | During unloading rods from truck deck | Injuries to the person due to hit while unloding rods | No | 3 | 2 | 6 | Unload bars from trailers as closer as possible to work area | 2 | 2 | 4
|  | E2 | Cutting of rods | Person may injured his finger or hand | No | 3 | 2 | 6 | Observe careful hand placement | 2 | 2 | 4
|  | E3 | Carrying of rods for long distance | Carrying of rods for short distance | No | 3 | 1 | 3 | Use proper lifting techniques | 1 | 1 | 1
|  | E4 | Bending of rods | Minor Injury | No | 2 | 2 | 4 | Get help with heavy / awkward bars | 1 | 2 | 2
F | Formwork | F1 | Working with cutting tools | May cause hand injury | No | 3 | 2 | 6 | Observe position of machine and work accordingly | 2 | 2 | 4
|  | F2 | Falling of shuttering materials | Major Injury | Yes | 2 | 2 | 4 | Safety net should be provided | 1 | 2 | 2
G | Preparation of shuttering | G1 | Nails not stacked properly | Eye Injury | No | 2 | 3 | 6 | Use magnet for collection of nails | 1 | 3 | 3
|  | G2 | Use of loose hammer | Major Injury | No | 3 | 2 | 6 | Use good condition of hammer | 1 | 2 | 2
H | Erection of shuttering on height | H1 | Fall of person | Major Injury | Yes | 2 | 4 | 8 | Safety belt should be provided | 1 | 4 | 4
|  | H2 | Fall of material | Major Injury | Yes | 2 | 4 | 8 | Safety net should be provided | 1 | 4 | 4
I | Walkway jellies laying/ removing | I1 | Fall of jallies | Major Injury | Yes | 2 | 3 | 6 | Walkway jallies should be bend with bending wires | 1 | 3 | 3
J | Concrete Pumping | J1 | Failure of equipment while working | Injuries/ fatal/ fracture and equipment damage | Yes | 2 | 5 | 10 | Check equipment before commencement of work | 1 | 5 | 5
K | Handling & Stacking of scaffold materia | K1 | Fall of material while loading & unloading | Injuries & fracture | No | 3 | 1 | 3 | Do not lift the materials with bundle ties and to be unloaded with suitablelifting equipments | 2 | 1 | 2
|  | K2 | Improper stacking | Minor Injury | No | 4 | 1 | 4 | Material should be stacked in stable manner and must be barricaded | 1 | 1 | 1
L | Working on scaffolding at height | L1 | Insufficient width of scaffold work platform | Injury/fatal | Yes | 4 | 5 | 20 | Proper width should be provided for working | 2 | 5 | 10
M | Use portable electrical power tools and electrical equipments | M1 | Inexperienced operator | Electrical shock and burn injury | No | 2 | 3 | 6 | Ensure complete trained operator to be deployed. | 1 | 3 | 3
N | Lifting of material | N1 | Failure of lifting gear, improper rigging | Fall of material from height, damages to material, man power | Yes | 2 | 5 | 10 | To ensure safety checklist before commencing work | 1 | 5 | 5
|  | N2 | Hit by object due with rapid speed of lowering hoist/hook. | Major Injury | Yes | 2 | 4 | 8 | Close supervision is required | 1 | 4 | 4
O | Other risk related to project | O1 | Fire Hazard | Major burn injuries | Yes | 1 | 5 | 5 | Fire enstigushier should be provided | 1 | 3 | 3
|  | O2 | Inflation in material rate | Increase cost more than estimated | No | 3 | 2 | 6 | Proper procurement strategy should be provided | 2 | 2 | 4
|  | O3 | Change in scope | Delay in project | No | 3 | 5 | 15 | Changes should be done as per the client's requirements and cost should be revised | 1 | 3 | 3
|  | O4 | Labour shortage | Delay in project | No | 4 | 4 | 16 | More sub contractors should be procured to mitigate labour shortage | 2 | 3 | 6
|  | O5 | Force Majure | Delay in project | No | 2 | 4 | 8 | Various Policies and Insurance should be taken by contractor | 2 | 3 | 6