## Dashboard
Milestone Dashboard - Project # - Week #
| Total Milestone |  | 10
| % Complete |  | 67.5%
| Delayed Milestone |  | 4
| In Progress Milstone |  | 2
| Reason for Milestone Delayed |  | Monsson , Labour Shortage
| Row Labels | Count of Sr. No |  | Row Labels | Sum of Schedule Impact
| Casting | 3 |  | Approval | 113
| Excavation | 4 |  | Design & Technical | 81
| Reinforcement | 4 |  | Execution | 118
| Shutterting | 4 |  | Material Procurement | 86
| Grand Total | 15 |  | Grand Total | 398
| Row Labels | Count of Sr. No |  | Row Labels | Count of Sr. No
| Approval | 4 |  | Non-overlapping Delay | 8
| Design & Technical | 3 |  | Overlapping Delay | 7
| Execution | 5 |  | Grand Total | 15
| Material Procurement | 3
| Grand Total | 15
|  |  |  | Row Labels | Count of Sr. No
|  |  |  | Open | 3
| Row Labels | Sum of Schedule Impact |  | Resolved | 12
| Architecture Consultant | 56 |  | (blank)
| Client | 112 |  | Grand Total | 15
| Contractor | 114
| PMC | 43
| Structure Consultant | 73
(blank)
| Grand Total | 398
| Row Labels | Count of Sr. No
| Open | 3
| Architecture Consultant | 1
| Contractor | 2
| Resolved | 12
| Architecture Consultant | 1
| Client | 3
| Contractor | 2
| PMC | 2
| Structure Consultant | 4
| Grand Total | 15
Client Logo

## Data Input
Milestone ID | Phase | Milestone Name | Planned Start | Planned End | Planned Days | Actual Start | Actual End | Actual Days | Weightage | % Complete | Stakeholder | Zone | Status2 | Delays
M01 | Pre-Construction | Site Mobilization | 2026-01-01 | 2026-01-05 | 4 | 2026-01-01 | 2026-01-05 | 4 | 5 | 100% | ABC Infra | A | Completed | 0
M02 | Excavation | Excavation Work | 2026-01-06 | 2026-01-15 | 9 | 2026-01-07 | 2026-01-17 | 10 | 5 | 100% | ABC Infra | A | Delayed | 1
M03 | Foundation | PCC Work | 2026-01-16 | 2026-01-20 | 4 | 2026-01-16 | 2026-01-20 | 4 | 5 | 100% | XYZ Con | A | Completed | 0
M04 | Foundation | Footing RCC | 2026-01-21 | 2026-01-30 | 9 | 2026-01-21 | 2026-02-02 | 12 | 10 | 100% | XYZ Con | B | Delayed | 3
M05 | Structure | Column RCC | 2026-02-01 | 2026-02-10 | 9 | 2026-02-01 | 2026-03-12 | 39 | 15 | 100% | XYZ Con | B | Delayed | 30
M06 | Structure | Slab Casting | 2026-02-11 | 2026-02-20 | 9 | 2026-02-11 | 2026-03-13 | 30 | 15 | 100% | LMN Build | B | Delayed | 21
M07 | Masonry | Block Work | 2026-02-21 | 2026-03-05 | 30 | 2026-01-08 |  | 0 | 15 | 70% | LMN Build | C | In Progress | 0
M08 | Finishing | Plastering | 2026-03-06 | 2026-03-20 | 14 | 1900-01-07 |  | -8 | 10 | 20% | LMN Build | C | In Progress | 0
M09 | Finishing | Flooring | 2026-03-21 | 2026-04-05 | 15 |  |  | 0 | 10 | 0% | PQR Works | C | Not Started | 0
M10 | Handover | Final Inspection | 2026-04-06 | 2026-04-10 | 4 |  |  |  | 10 | 0% | PQR Works | C | Not Started | 0
0
| 10 | [7 empty] | 67.5%

## Sheet1 (hidden)
Row Labels | Sum of Delays
ABC Infra | 1
LMN Build | 21
PQR Works | 0
XYZ Con | 33
Grand Total | 55

## Pivoit Status (hidden)
Milstone | Count of Milestone ID
Completed | 2
Delayed | 4
In Progress | 2
Not Started | 2
Grand Total | 10

## Sheet3 (hidden)
Row Labels | Average of % Complete
Pre-Construction | 100%
Excavation | 100%
Foundation | 100%
Structure | 100%
Masonry | 70%
Finishing | 50%
Handover | 0%
Grand Total | 77%

## Sheet4 (hidden)
Row Labels | Sum of Delays
Block Work | 0
Column RCC | 30
Excavation Work | 1
Final Inspection | 0
Flooring | 0
Footing RCC | 3
PCC Work | 0
Plastering | 0
Site Mobilization | 0
Slab Casting | 21
Grand Total | 55