## Dashboard
Progress Overview - February Week 2 - 2026
Project Timeline
Project Start Date |  | 2025-06-01
Planned End Date |  | 2026-06-30
Current Date |  | 2026-03-04
Project Progress |  | 70.05% |  |  |  |  | Row Labels | Count of Sr. No
[7 empty] | Casting | 3
[5 empty] | Row Labels | Average of % Complete | Excavation | 4
[5 empty] | Excavation | 100% | Reinforcement | 4
[5 empty] | Finishing | 10% | Shutterting | 4
[5 empty] | Foundation | 100% | Grand Total | 15
|  |  | Row Labels | Count of Approval ID | Handover | 0%
|  |  | Approved | 12 | Masonry | 100%
|  |  | Delayed | 3 | Pre-Construction | 100%
|  |  | In Progress | 4 | Structure | 100%
|  |  | Not Submitted | 4 | Grand Total | 72%
|  |  | Submitted | 7
|  |  | Grand Total | 30
| Row Labels | Count of #
| Active (Ongoing) | 8
| Completed | 7
| Dormant (Not Started) | 7
| Not Started | 8
| Grand Total | 30
Projet Milestone Update
Support Required from Client -
Monthwise Cashflow Update
Cost Performace Index
Poured Concrete
3300 m3
Safe Hours
700 Hours
Total UnSafe Hours
4 Hours
Non - Conformity Report
0
Timeline Status
On Time
Upcoming Major Activities :
Concreting of Floor 2 on 26-02-2026
Safety Awareness Program
Joint Visit on 28-02-2026
Planned Vs Actual

## Legal Approval Tracker
Legal Approval Tracker - Week #
Approval ID | Approval Category | Authority Name | Approval Description | Applicable Building / Package | Submission Date | Required By | Approval Received Date | Status | Delay (Days) | Responsible Party | Remarks
LA-01 | Labour Compliance | Labour Department | BOCW Registration – Building & Other Construction Works | All Towers | 2025-01-05 | 2025-01-20 | 2025-01-22 | Approved | 2 | Client | Approved with minor delay
LA-02 | Insurance | Insurance Company | CAR Policy – Contractor All Risk | All Packages | 2025-01-02 | 2025-01-10 | 2025-01-09 | Approved | -1 | Contractor | Submitted on priority
LA-03 | Labour Compliance | Labour Department | CLRA Registration – Contract Labour Regulation Act | All Towers | 2025-01-06 | 2025-01-25 |  | Submitted |  | Contractor | Under review by department
LA-04 | Labour Compliance | Labour Department | Labour License | Tower 1 | 2025-01-08 | 2025-01-20 |  | Delayed |  | Contractor | Inspection pending
LA-05 | Statutory | EPFO | PF Registration Documents | All Packages | 2025-01-03 | 2025-01-15 | 2025-01-14 | Approved | -1 | Contractor | -
LA-06 | Statutory | ESIC | ESI Registration Documents | All Packages | 2025-01-03 | 2025-01-15 | 2025-01-16 | Approved | 1 | Contractor | One day delay
LA-07 | Tax | State Tax Department | Professional Tax Registration | All Packages | 2025-01-04 | 2025-01-18 | 2025-01-17 | Approved | -1 | Contractor | -
LA-08 | Labour Compliance | Labour Department | LWF – Labour Welfare Fund Registration | All Towers | 2025-01-05 | 2025-01-18 |  | Submitted |  | Contractor | Follow-up required
LA-09 | Health & Safety | Government Hospital | Worker Medical Fitness Certification | All Towers | 2025-01-07 | 2025-01-14 | 2025-01-13 | Approved | -1 | Contractor | -
LA-10 | Police Clearance | Local Police Department | Worker Police Verification | All Towers | 2025-01-07 | 2025-01-21 |  | Delayed |  | Contractor | Police clearance pending
LA-11 | Safety | Third Party Agency | Test Certificate – Lifting Tools & Tackles | All Towers | 2025-01-09 | 2025-01-19 | 2025-01-18 | Approved | -1 | Contractor | -
LA-12 | Safety | Third Party Agency | Pressure Vessel Test Certificate | All Towers | 2025-01-09 | 2025-01-19 |  | Submitted |  | Contractor | Inspection scheduled
LA-13 | Fire | Fire Department | Fire NOC – Temporary Site Office | Site Area | 2025-01-10 | 2025-01-25 |  | In Progress |  | Client | Documents submitted
LA-14 | Environment | Pollution Control Board | Consent to Establish (CTE) | Project Site | 2025-01-12 | 2025-02-05 |  | Submitted |  | Client | Under scrutiny
LA-15 | Environment | Pollution Control Board | Consent to Operate – DG Set | Project Site | 2025-01-15 | 2025-02-10 |  | Not Submitted |  | Contractor | DG set not installed
LA-16 | Local Authority | Municipal Corporation | Building Plan Approval | Tower 1 | 2024-12-15 | 2025-01-30 | 2025-01-28 | Approved | -2 | Client | -
LA-17 | Local Authority | Municipal Corporation | Commencement Certificate | Tower 2 | 2025-01-05 | 2025-01-25 |  | Delayed |  | Client | Resubmission required
LA-18 | Utility | Electricity Board | Temporary Power Connection | Site | 2025-01-06 | 2025-01-20 | 2025-01-21 | Approved | 1 | Contractor | -
LA-19 | Utility | Water Supply Department | Temporary Water Connection | Site | 2025-01-06 | 2025-01-20 |  | Submitted |  | Contractor | Pipeline work pending
LA-20 | Traffic | Traffic Police Department | Traffic Diversion Permission | Main Road | 2025-01-10 | 2025-01-18 | 2025-01-17 | Approved | -1 | Client | -
LA-21 | Safety | Factory Inspectorate | Site Safety Registration | All Towers | 2025-01-11 | 2025-01-22 |  | In Progress |  | Contractor | Inspection awaited
LA-22 | Insurance | Insurance Company | Workmen Compensation Policy | All Labour | 2025-01-05 | 2025-01-12 | 2025-01-11 | Approved | -1 | Contractor | -
LA-23 | Labour Compliance | Labour Department | Inter-State Migrant Workmen Registration | All Towers | 2025-01-08 | 2025-01-25 |  | Submitted |  | Contractor | Documents under review
LA-24 | Environment | Local Authority | Tree Cutting Permission | Site Boundary | 2025-01-15 | 2025-02-01 |  | Not Submitted |  | Client | Tree survey pending
LA-25 | Safety | Fire Department | Fire Safety Equipment Approval | Site | 2025-01-16 | 2025-01-30 |  | In Progress |  | Contractor | Partial installation completed
LA-26 | Utility | Telecom Authority | Internet / Telecom Permission | Site Office | 2025-01-14 | 2025-01-28 | 2025-01-27 | Approved | -1 | Contractor | -
LA-27 | Local Authority | Municipal Corporation | Hoarding Permission | Site Boundary | 2025-01-18 | 2025-01-28 |  | Submitted |  | Client | Approval awaited
LA-28 | Environment | Local Authority | Debris Disposal Permission | Project Site | 2025-01-20 | 2025-02-05 |  | Not Submitted |  | Contractor | Vendor finalisation pending
LA-29 | Safety | Lift Inspector | Temporary Construction Lift Approval | Tower 1 | 2025-01-22 | 2025-02-10 |  | In Progress |  | Contractor | Inspection scheduled
LA-30 | Statutory | Explosives Department | Diesel Storage License | Project Site | 2025-01-25 | 2025-02-15 |  | Not Submitted |  | Contractor | Tank installation pending
Client Logo

## Milestone
Milestone ID | Phase | Milestone Name | Planned Start | Planned End | Planned Days | Actual Start | Actual End | Actual Days | Weightage | % Complete | Stakeholder | Zone | Status2 | Delays
M01 | Pre-Construction | Site Mobilization | 2026-01-01 | 2026-01-05 | 4 | 2026-01-01 | 2026-01-05 | 4 | 5 | 100% | ABC Infra | A | Completed | 0
M02 | Excavation | Excavation Work | 2026-01-06 | 2026-01-15 | 9 | 2026-01-07 | 2026-01-17 | 10 | 5 | 100% | ABC Infra | A | Delayed | 1
M03 | Foundation | PCC Work | 2026-01-16 | 2026-01-20 | 4 | 2026-01-16 | 2026-01-20 | 4 | 5 | 100% | XYZ Con | A | Completed | 0
M04 | Foundation | Footing RCC | 2026-01-21 | 2026-01-30 | 9 | 2026-01-21 | 2026-02-02 | 12 | 10 | 100% | XYZ Con | B | Delayed | 3
M05 | Structure | Column RCC | 2026-02-01 | 2026-02-10 | 9 | 2026-02-01 | 2026-03-12 | 39 | 15 | 100% | XYZ Con | B | Delayed | 30
M06 | Structure | Slab Casting | 2026-02-11 | 2026-02-20 | 9 | 2026-02-11 | 2026-03-13 | 30 | 15 | 100% | LMN Build | B | Delayed | 21
M07 | Masonry | Block Work | 2026-02-21 | 2026-03-05 | 30 | 2026-01-08 |  | 0 | 15 | 100% | LMN Build | C | In Progress | 0
M08 | Finishing | Plastering | 2026-03-06 | 2026-03-20 | 14 | 1900-01-07 |  | -8 | 10 | 20% | LMN Build | C | In Progress | 0
M09 | Finishing | Flooring | 2026-03-21 | 2026-04-05 | 15 |  |  | 0 | 10 | 0% | PQR Works | C | Not Started | 0
M10 | Handover | Final Inspection | 2026-04-06 | 2026-04-10 | 4 |  |  |  | 10 | 0% | PQR Works | C | Not Started | 0
0
| 10 | [7 empty] | 72%

## Risk Register
Step 1: Risk Identification | [5 empty] | Step 2: Risk Assessment | [5 empty] | Step 3: Risk Response |  |  |  | Step 4: Monitor & Control
# | Category | Opportunity / Threat | Risk Name | Detailed Description | Probability (1 - 5) | Consequence (1-5) | Severity (Priority) | Probability (%) | Cost Impact (₹) | Most Likely (no. of weeks) | Urgency | Response Category | Impact | Risk Owner | Contingency Plan | Status | Date Last Updated | Tracking Comments
R1 | Execution | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 1000 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-04 | NA
R2 | Planning/ Scope | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 3 | 2 | 6 | 30% | 2000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-09 | NA
R3 | Communications | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 1 | 5 | 40% | 3000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-27 | NA
R4 | Schedule | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 3 | 12 | 50% | 100 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-03-04 | NA
R5 | Estimating | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 2 | 5 | 10 | 10% | 5000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-09 | NA
R6 | Controlling | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 2 | 10 | 20% | 6000 | 1 | Medium | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-27 | NA
R7 | Planning/ Scope | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 4 | 16 | 30% | 10000 | 1 | High | Share | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-03-04 | NA
R8 | Communications | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 2000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-03-09 | NA
R9 | Schedule | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 50% | 8000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-02-27 | NA
R10 | Esxecution | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 20% | 3000 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-04 | NA
R11 | Controlling | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 30% | 3500 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-03-09 | NA
R12 | Planning/ Scope | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 40% | 6480 | 1 | Medium | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-02-27 | NA
R13 | Communications | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 3 | 3 | 50% | 6500 | 1 | High | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-04 | NA
R14 | Schedule | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 4 | 20 | 20% | 9000 | 1 | Low | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-09 | NA
R15 | Estimating | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 3 | 12 | 30% | 8750 | 1 | Medium | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-27 | NA
R16 | Controlling | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 250 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-03-04 | NA
R17 | Planning/ Scope | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 100 | 1 | Low | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-09 | NA
R18 | Communications | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 600 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-27 | NA
R19 | Schedule | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 4 | 20 | 30% | 13000 | 1 | High | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-03-04 | NA
R20 | Esxecution | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 26000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-03-09 | NA
R21 | Controlling | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 14500 | 1 | Medium | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-02-27 | NA
R22 | Planning/ Scope | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 18000 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-04 | NA
R23 | Communications | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 30% | 21500 | 1 | Low | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-03-09 | NA
R24 | Schedule | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 1450 | 1 | Medium | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-02-27 | NA
R25 | Esxecution | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 1000 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-04 | NA
R26 | Controlling | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 6200 | 1 | Low | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-03-09 | NA
R27 | Planning/ Scope | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 30% | 1000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-02-27 | NA
R28 | Communications | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 1000 | 1 | High | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-03-04 | NA
R29 | Schedule | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 1000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-03-09 | NA
R30 | Esxecution | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 1000 | 1 | Medium | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-02-27 | NA

## Hinderance Register
Hinderance Register
Sr. No | Description of Hindrance | Location | Critical Activity affected | Correspondence | Category | Type of Hindrance | Date of Occurrence | Date Resolved | No. of Days | Baseline Start Date | Schedule Impact | Delay Type | Accountable | Status | Description of Resolution | Remarks
1 | Staircase work | Building A | Shutterting | 2026-12-26 | Design & Technical | Storage and handling constraints | 2026-11-19 | 2026-11-22 | 4 | 2026-11-13 | 10 | Overlapping Delay | Architecture Consultant | Resolved | drawing was given on 22-11-2026 |  | #REF! | #REF!
2 | Column reinforcement and formwork for part 1A | Building B | Casting | 2026-12-26 | Approval | Delay in mock-up / sample approvals | 2026-12-24 | 2026-12-28 | 5 | 2026-12-24 | 5 | Non-overlapping Delay | Contractor | Resolved | drawing was given on 28-12-2027
3 | basement 1 slab for Part 1B,1C | Building C | Reinforcement | 2027-01-12 | Execution | Variation / change order approval delays | 2027-01-05 | 2027-01-17 | 13 | 2027-01-06 | 12 | Non-overlapping Delay | Structure Consultant | Resolved | drawing was given on 17-1-23
4 | Basement 1 slab for Part 1D | Building D | Excavation | 2027-01-12 | Material Procurement | Work front not available / handed over | 2027-01-12 | 2027-01-17 | 6 | 2026-12-31 | 18 | Overlapping Delay | PMC | Resolved | drawing was given on 17-1-23
5 | Ground floor slab for Block A | Building E | Shutterting | 2026-12-26 | Material Procurement | Import / logistics clearance delays | 2027-01-20 | 2027-02-08 | 20 | 2027-01-20 | 20 | Non-overlapping Delay | Structure Consultant | Resolved | drawing was given on 8-2-23 for shuttering
6 | Basement 3 slab for Part 2 | Building A | Casting | 2026-12-26 | Approval | Delay in statutory approvals (Fire, Local Authority, Utilities) | 2027-01-20 | 2027-02-07 | 19 | 2027-01-15 | 24 | Overlapping Delay | Client | Resolved | drawing was given on 7-2-23 for shuttering
7 | Lift 4 | Building B | Reinforcement | 2027-01-28 | Execution | Vendor / supplier non-performance | 2027-01-18 | 2027-01-31 | 14 | 2027-01-07 | 25 | Non-overlapping Delay | Contractor | Open | drawing was given on 24-1-23 and hold decision was given on 31-1-23
8 | Stair 5,6,2 - Part 2 | Building C | Excavation | 2027-02-22 | Design & Technical | Insufficient skilled manpower | 2027-02-10 | 2027-03-01 | 20 | 2027-01-15 | 46 | Non-overlapping Delay | Architecture Consultant | Open | drawing was given on 8-2-23 for shuttering
9 | Block B & C - ground floor slab | Building D | Reinforcement | 2026-12-26 | Approval | Constructability issues at site | 2027-02-15 | 2027-02-19 | 5 | 2027-01-31 | 20 | Overlapping Delay | Contractor | Resolved | drawing was given on 19-2-23 for shuttering
10 | Block A - ground floor | Building E | Excavation | 2026-12-26 | Execution | Delay in issue of GFC / IFC drawings | 2027-02-20 | 2027-02-23 | 4 | 2027-02-07 | 17 | Overlapping Delay | Structure Consultant | Resolved | drawing was given on 8-2-23 for shuttering
11 | Block C - ground floor | Building A | Shutterting | 2027-02-27 | Design & Technical | Delay in issue of GFC / IFC drawings | 2027-02-26 | 2027-02-28 | 3 | 2027-02-04 | 25 | Overlapping Delay | PMC | Resolved
12 | Block A - ground floor | Building B | Casting | 2026-12-26 | Execution | Delay in design clarifications (RFIs) | 2027-02-27 | 2027-03-02 | 4 | 2027-02-07 | 24 | Non-overlapping Delay | Structure Consultant | Resolved | casting done on 2/3/23
13 | Part 2- ramp work | Building C | Excavation | 2027-02-27 | Material Procurement | Delay in approval from Client / PMC | 2027-02-17 | 2027-03-04 | 16 | 2027-01-16 | 48 | Non-overlapping Delay | Client | Resolved
14 | Part 1- Stair 1,9 | Building D | Shutterting | 2026-12-26 | Approval | Delay in statutory approvals (Fire, Local Authority, Utilities) | 2027-03-05 | 2027-04-04 | 31 | 2027-01-31 | 64 | Overlapping Delay | Contractor | Open
15 | Part 2A- basement 2 | Building E | Reinforcement | 2027-03-14 | Execution | Delay in issue of GFC / IFC drawings | 2027-03-16 | 2027-03-21 | 6 | 2027-02-10 | 40 | Non-overlapping Delay | Client | Resolved | drawing was given on 21-3-23 for shuttering
0