## Dashboard
Risk Assessment Dashboard - Project # - Date 31-12-2025
Row Labels | Count of # |  | Row Labels | Count of # |  | Row Labels | Count of #
Controlling | 5 |  | Both | 10 |  | Active (Ongoing) | 8
Planning/ Scope | 6 |  | Opportunity | 10 |  | Completed | 7
Communications | 6 |  | Threat | 10 |  | Dormant (Not Started) | 7
Schedule | 6 |  | Grand Total | 30 |  | Not Started | 8
Esxecution | 5 |  |  |  |  | Grand Total | 30
Execution | 1
Estimating | 1 |  | Row Labels | Count of #
Grand Total | 30 |  | Contractor | 6
Row Labels | Count of # |  | Designer | 6
2 | 4 |  | MEPF Consultant | 6
3 | 1 |  | Owner | 6
5 | 1 |  | PMC | 6
6 | 1 |  | Grand Total | 30
10 | 2
12 | 2
16 | 1
20 | 1
25 | 17
Grand Total | 30 | [8 empty] | Low | Med- Low | Med | Med- High | High
[8 empty] | Probability | 5 | 5 | 10 | 15 | 20 | 25
[9 empty] | 4 | 4 | 8 | 12 | 16 | 20
Urgency | Response Category | Count of # |  | Row Labels | Sum of Severity (Priority) |  |  |  | 3 | 3 | 6 | 9 | 12 | 15
High | Accept | 1 |  | Manpower Opportunity | 277 |  |  |  | 2 | 2 | 4 | 6 | 8 | 10
| Avoid | 3 |  | Manpower Shortage | 250 |  |  |  | 1 | 1 | 2 | 3 | 4 | 5
| Exploit | 2 |  | Grand Total | 527 |  |  |  |  | 1 | 2 | 3 | 4 | 5
| Mitigate | 3 | [7 empty] | Consequence
| Share | 1
Low | Accept | 1
| Avoid | 1
| Enhance | 1
| Mitigate | 6
| Transfer | 1
Medium | Accept | 1
| Avoid | 1
| Enhance | 2
| Exploit | 2
| Transfer | 4

## Risk Register
Step 1: Risk Identification | [5 empty] | Step 2: Risk Assessment | [5 empty] | Step 3: Risk Response |  |  |  | Step 4: Monitor & Control
# | Category | Opportunity / Threat | Risk Name | Detailed Description | Probability (1 - 5) | Consequence (1-5) | Severity (Priority) | Probability (%) | Cost Impact (₹) | Most Likely (no. of weeks) | Urgency | Response Category | Impact | Risk Owner | Contingency Plan | Status | Date Last Updated | Tracking Comments
R1 | Execution | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 1000 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-18 | NA
R2 | Planning/ Scope | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 3 | 2 | 6 | 30% | 2000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-23 | NA
R3 | Communications | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 1 | 5 | 40% | 3000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-01-13 | NA
R4 | Schedule | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 3 | 12 | 50% | 100 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-01-18 | NA
R5 | Estimating | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 2 | 5 | 10 | 10% | 5000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-23 | NA
R6 | Controlling | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 2 | 10 | 20% | 6000 | 1 | Medium | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-13 | NA
R7 | Planning/ Scope | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 4 | 16 | 30% | 10000 | 1 | High | Share | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-01-18 | NA
R8 | Communications | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 2000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-01-23 | NA
R9 | Schedule | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 50% | 8000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-13 | NA
R10 | Esxecution | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 20% | 3000 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-18 | NA
R11 | Controlling | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 30% | 3500 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-01-23 | NA
R12 | Planning/ Scope | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 2 | 2 | 40% | 6480 | 1 | Medium | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-01-13 | NA
R13 | Communications | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 1 | 3 | 3 | 50% | 6500 | 1 | High | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-18 | NA
R14 | Schedule | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 4 | 20 | 20% | 9000 | 1 | Low | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-23 | NA
R15 | Estimating | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 4 | 3 | 12 | 30% | 8750 | 1 | Medium | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-01-13 | NA
R16 | Controlling | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 250 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-01-18 | NA
R17 | Planning/ Scope | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 100 | 1 | Low | Accept | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-23 | NA
R18 | Communications | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 600 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-13 | NA
R19 | Schedule | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 4 | 20 | 30% | 13000 | 1 | High | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-01-18 | NA
R20 | Esxecution | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 26000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-01-23 | NA
R21 | Controlling | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 14500 | 1 | Medium | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-13 | NA
R22 | Planning/ Scope | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 18000 | 1 | High | Avoid | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-18 | NA
R23 | Communications | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 30% | 21500 | 1 | Low | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-01-23 | NA
R24 | Schedule | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 1450 | 1 | Medium | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-01-13 | NA
R25 | Esxecution | Threat | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 1000 | 1 | High | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-18 | NA
R26 | Controlling | Opportunity | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 6200 | 1 | Low | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Designer | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-23 | NA
R27 | Planning/ Scope | Both | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 30% | 1000 | 1 | Medium | Transfer | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Contractor | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Dormant (Not Started) | 2026-01-13 | NA
R28 | Communications | Threat | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 40% | 1000 | 1 | High | Exploit | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | PMC | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Completed | 2026-01-18 | NA
R29 | Schedule | Opportunity | Manpower Shortage | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 50% | 1000 | 1 | Low | Mitigate | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | MEPF Consultant | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Not Started | 2026-01-23 | NA
R30 | Esxecution | Both | Manpower Opportunity | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. Only 6 masons are available on site for masonry work, which is targeted for 10 nos. | 5 | 5 | 25 | 20% | 1000 | 1 | Medium | Enhance | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | Owner | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | Active (Ongoing) | 2026-01-13 | NA

## List
Categories | Risk Type | Response Category | Urgency | Risk Owner | Status | Numbers
PM | Opportunity | Avoid | High | Contractor | Not Started | 1
Estimating | Threat | Transfer | Medium | PMC | Active (Ongoing) | 2
Planning/ Scope | Both | Mitigate | Low | Designer | Dormant (Not Started) | 3
Controlling |  | Share |  | MEPF Consultant | Completed | 4
Communications |  | Accept |  | Owner |  | 5
Schedule
Execution |  | Exploit
Enhance
Opportunity/Threat:
Opportunity | Risk identified as an opportunity in the assessment section of the risk register
Threat | Risk identified as a threat in the assessment section of the risk register
Both | Risk identified as an opportunity and a threat in the assessment section of the risk register
Response Category:
Opportunity or Threat Response - Pick One
Accept | Indicates that the project team has decided not to change the project plan to deal with a risk, or is unable to identify any other suitable response strategy. It should be noted, that mitigation or transference is not necessary for all risk threats, particularly those with a small severity rating. Judgment must be used as to whether a more rigorous (and potentially costly) response should be implemented.
Share | Allocates a portion of ownership of a risk threat to another party who is best able to minimize the impact and/or probability of the risks. Allocates all or a portion of ownership of a risk opportunity to another party who is best able to maximize its probability of occurrence and increase the potential benefits if it does occur. MnDOT and 3rd party share the benefits of the opportunity.
Threat Response
Mitigate | Seeks to reduce the probability and/or impact of a risks threat to below an acceptable threshold.
Transfer | Allocates all ownership of a risk threat to another party who is best able to minimize the impact and/or probability of the risk.
Avoid | Involves changing the project plan to eliminate the risk threat or to protect the project objectives from its impact.
Opportunity Response
Enhance | Seeks to modify the “size” of a risk opportunity by increasing its probability and/or impact thereby maximizing benefits realized for the project.
Exploit | Seeks to eliminate the uncertainty associated with a particular upside risk by making the risk opportunity definitely happen - can be considered a more rigorous response than "enhance".
Status:
Active (Not Started) | Risk is being actively monitored and controlled, but the response plan has not been initiated.
Active (Ongoing) | Risk is being actively monitored and controlled, and the response plan is currently being implemented.
Active (Complete) | The risk is still being being actively monitored and controlled; however all work on the response plan is complete.
Dormant (Not Started) | Risk is not currently a high priority, but may become active in the future
Retired (Complete) | Risk is no longer a threat to project objectives