## One Pager
Safety Dashboard - Week 2 - Date #-#-##
Total Incidents |  |  | Total Unsafe Act | Total NCR | Weekley Safe - Hours |  | Cumulative Safe - Hours
23 |  |  | 82 | 16 | 1350 |  | 7670
Tool Box Talk |  |  | HSE Induction |  |  | Major Safety Incident -This Week
7 |  |  | 2 |  |  | Working without Rope > 3m
This Week |  |  | This Week
39 |  |  | 19
Cumulative |  |  | Cumulative
Safety Mantra - Week #
" No Job is so Difficult that we cannot do it Safely"
Total Site Instruction | 23
Total Unsafe Act | 82
Total NCR | 16
Weekley Safe Man Hours | 1350
Total Safe man Hours | 7670
Sr.No | Observation | Open | Closed
1 | Site instruction | 6 | 17
2 | Unsafe Act | 39 | 43
3 | NCR | 11 | 5
Sr.No | Observation | Open | Closed
1 | Unsafe Act | 39 | 43
Sr.No | Observation | Open | Closed
1 | NCR | 11 | 5
21
Days
Since Last Accident

## Site Instruction
Site Instruction Report
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. | [6 empty] | Updated On:
Report No |  | Safari-Safety Instruction-Sharnam-001 | [5 empty] | Total Open | 6 | Total Closed | 17
S. No | Location | Issued by | Issued to | Issued on | Brief Description | category | Action taken | Status | Time Impact (Y/N) | Cost Impact (Y/N) | Remarks | Yes | Open
1 | Building A | Sharnam PMC | Shapoorji | 2025-12-15 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-18 | Closed | Yes | Yes |  | No | Closed
2 | Building B | Sharnam PMC | Shapoorji | 2025-12-16 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-19 | Closed | Yes | Yes
3 | Building A | Sharnam PMC | Shapoorji | 2025-12-17 | Material is not stacked properly itemwise. | Material | 2024-12-20 | Closed | Yes | Yes
4 | Building B | Sharnam PMC | Shapoorji | 2025-12-18 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
5 | Building A | Sharnam PMC | Shapoorji | 2025-12-19 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-21 | Closed | Yes | Yes
6 | Building B | Sharnam PMC | Shapoorji | 2025-12-20 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-22 | Open | Yes | Yes
7 | Building A | Sharnam PMC | Shapoorji | 2025-12-21 | Material is not stacked properly itemwise. | Material | 2024-12-23 | Closed | Yes | Yes
8 | Building B | Sharnam PMC | Shapoorji | 2025-12-22 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
9 | Building A | Sharnam PMC | Shapoorji | 2025-12-23 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-24 | Closed | Yes | Yes
10 | Building B | Sharnam PMC | Shapoorji | 2025-12-24 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-25 | Closed | Yes | Yes
11 | Building A | Sharnam PMC | Shapoorji | 2025-12-25 | Material is not stacked properly itemwise. | Material | 2024-12-26 | Closed | Yes | Yes
12 | Building B | Sharnam PMC | Shapoorji | 2025-12-26 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
13 | Building A | Sharnam PMC | Shapoorji | 2025-12-27 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-27 | Closed | Yes | Yes
14 | Building B | Sharnam PMC | Shapoorji | 2025-12-28 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-28 | Closed | Yes | Yes
15 | Building A | Sharnam PMC | Shapoorji | 2025-12-29 | Material is not stacked properly itemwise. | Material | 2024-12-29 | Closed | Yes | Yes
16 | Building B | Sharnam PMC | Shapoorji | 2025-12-30 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
17 | Building A | Sharnam PMC | Shapoorji | 2025-12-31 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2024-12-30 | Closed | Yes | Yes
18 | Building B | Sharnam PMC | Shapoorji | 2026-01-01 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2024-12-31 | Closed | Yes | Yes
19 | Building A | Sharnam PMC | Shapoorji | 2026-01-02 | Material is not stacked properly itemwise. | Material | 2025-01-01 | Closed | Yes | Yes
20 | Building B | Sharnam PMC | Shapoorji | 2026-01-03 | It has been noted that the scaffolding is not rested on the proper land | Material |  | Open | No | No
21 | Building A | Sharnam PMC | Shapoorji | 2026-01-04 | Unsafe bar bending work observded also working at height, without safety belt, working platform or hand rail. | Working at Height | 2025-01-02 | Closed | Yes | Yes
22 | Building B | Sharnam PMC | Shapoorji | 2026-01-05 | in the pit, this is totally unsafe condition to work for workeres. Injury or incident can be happen. | Working in Pit | 2025-01-03 | Closed | Yes | Yes
23 | Building A | Sharnam PMC | Shapoorji | 2026-01-06 | Material is not stacked properly itemwise. | Material | 2025-01-04 | Closed | Yes | Yes

## Unsafe Act Summary
Unsafe Act Summary
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. | [6 empty] | Updated On:
Report No |  | Safari-Safety Observation Unsafe Act-Sharnam-001 | [5 empty] | Total Open | 39 | Total Closed | 43
S. No | Location | Issued By | Issued To | Issued On | Brief Description | Category | Action Taken | Status | Time Impact (Y/N) | Cost Impact (Y/N) | Remarks
1 | Building A | Sharnam PMC | Shapoorji | 2025-12-15 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
2 | Building B | Sharnam PMC | Shapoorji | 2025-12-16 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
3 | Building A | Sharnam PMC | Shapoorji | 2025-12-17 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
4 | Building B | Sharnam PMC | Shapoorji | 2025-12-18 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
5 | Building A | Sharnam PMC | Shapoorji | 2025-12-19 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
6 | Building B | Sharnam PMC | Shapoorji | 2025-12-20 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
7 | Building A | Sharnam PMC | Shapoorji | 2025-12-21 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
8 | Building B | Sharnam PMC | Shapoorji | 2025-12-22 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
9 | Building A | Sharnam PMC | Shapoorji | 2025-12-23 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
10 | Building B | Sharnam PMC | Shapoorji | 2025-12-24 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Open | Yes | Yes
11 | Building A | Sharnam PMC | Shapoorji | 2025-12-25 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
12 | Building B | Sharnam PMC | Shapoorji | 2025-12-26 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Open | Yes | Yes
13 | Building A | Sharnam PMC | Shapoorji | 2025-12-27 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
14 | Building B | Sharnam PMC | Shapoorji | 2025-12-28 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Open | Yes | Yes
15 | Building A | Sharnam PMC | Shapoorji | 2025-12-29 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
16 | Building B | Sharnam PMC | Shapoorji | 2025-12-30 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
17 | Building A | Sharnam PMC | Shapoorji | 2025-12-31 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
18 | Building B | Sharnam PMC | Shapoorji | 2026-01-01 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
19 | Building A | Sharnam PMC | Shapoorji | 2026-01-02 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
20 | Building B | Sharnam PMC | Shapoorji | 2026-01-03 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
21 | Building A | Sharnam PMC | Shapoorji | 2026-01-04 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
22 | Building B | Sharnam PMC | Shapoorji | 2026-01-05 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
23 | Building A | Sharnam PMC | Shapoorji | 2026-01-06 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
24 | Building B | Sharnam PMC | Shapoorji | 2026-01-07 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
25 | Building A | Sharnam PMC | Shapoorji | 2026-01-08 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
26 | Building B | Sharnam PMC | Shapoorji | 2026-01-09 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
27 | Building A | Sharnam PMC | Shapoorji | 2026-01-10 | Unsafe Act at Excavation | Working in Pit | Closed the work | Closed | No | No
28 | Building B | Sharnam PMC | Shapoorji | 2026-01-11 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
29 | Building A | Sharnam PMC | Shapoorji | 2026-01-12 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
30 | Building B | Sharnam PMC | Shapoorji | 2026-01-13 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
31 | Building A | Sharnam PMC | Shapoorji | 2026-01-14 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
32 | Building B | Sharnam PMC | Shapoorji | 2026-01-15 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
33 | Building A | Sharnam PMC | Shapoorji | 2026-01-16 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
34 | Building B | Sharnam PMC | Shapoorji | 2026-01-17 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
35 | Building A | Sharnam PMC | Shapoorji | 2026-01-18 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
36 | Building B | Sharnam PMC | Shapoorji | 2026-01-19 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
37 | Building A | Sharnam PMC | Shapoorji | 2026-01-20 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
38 | Building B | Sharnam PMC | Shapoorji | 2026-01-21 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
39 | Building A | Sharnam PMC | Shapoorji | 2026-01-22 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
40 | Building B | Sharnam PMC | Shapoorji | 2026-01-23 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
41 | Building A | Sharnam PMC | Shapoorji | 2026-01-24 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
42 | Building B | Sharnam PMC | Shapoorji | 2026-01-25 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
43 | Building A | Sharnam PMC | Shapoorji | 2026-01-26 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
44 | Building B | Sharnam PMC | Shapoorji | 2026-01-27 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
45 | Building A | Sharnam PMC | Shapoorji | 2026-01-28 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
46 | Building B | Sharnam PMC | Shapoorji | 2026-01-29 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
47 | Building A | Sharnam PMC | Shapoorji | 2026-01-30 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
48 | Building B | Sharnam PMC | Shapoorji | 2026-01-31 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
49 | Building A | Sharnam PMC | Shapoorji | 2026-02-01 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
50 | Building B | Sharnam PMC | Shapoorji | 2026-02-02 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
51 | Building A | Sharnam PMC | Shapoorji | 2026-02-03 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
52 | Building B | Sharnam PMC | Shapoorji | 2026-02-04 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
53 | Building A | Sharnam PMC | Shapoorji | 2026-02-05 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
54 | Building B | Sharnam PMC | Shapoorji | 2026-02-06 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
55 | Building A | Sharnam PMC | Shapoorji | 2026-02-07 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
56 | Building B | Sharnam PMC | Shapoorji | 2026-02-08 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
57 | Building A | Sharnam PMC | Shapoorji | 2026-02-09 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
58 | Building B | Sharnam PMC | Shapoorji | 2026-02-10 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
59 | Building A | Sharnam PMC | Shapoorji | 2026-02-11 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
60 | Building B | Sharnam PMC | Shapoorji | 2026-02-12 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
61 | Building A | Sharnam PMC | Shapoorji | 2026-02-13 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
62 | Building B | Sharnam PMC | Shapoorji | 2026-02-14 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
63 | Building A | Sharnam PMC | Shapoorji | 2026-02-15 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
64 | Building B | Sharnam PMC | Shapoorji | 2026-02-16 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
65 | Building A | Sharnam PMC | Shapoorji | 2026-02-17 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
66 | Building B | Sharnam PMC | Shapoorji | 2026-02-18 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
67 | Building A | Sharnam PMC | Shapoorji | 2026-02-19 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
68 | Building B | Sharnam PMC | Shapoorji | 2026-02-20 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
69 | Building A | Sharnam PMC | Shapoorji | 2026-02-21 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
70 | Building B | Sharnam PMC | Shapoorji | 2026-02-22 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
71 | Building A | Sharnam PMC | Shapoorji | 2026-02-23 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
72 | Building B | Sharnam PMC | Shapoorji | 2026-02-24 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
73 | Building A | Sharnam PMC | Shapoorji | 2026-02-25 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
74 | Building B | Sharnam PMC | Shapoorji | 2026-02-26 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
75 | Building A | Sharnam PMC | Shapoorji | 2026-02-27 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
76 | Building B | Sharnam PMC | Shapoorji | 2026-02-28 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
77 | Building A | Sharnam PMC | Shapoorji | 2026-03-01 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
78 | Building B | Sharnam PMC | Shapoorji | 2026-03-02 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
79 | Building A | Sharnam PMC | Shapoorji | 2026-03-03 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
80 | Building B | Sharnam PMC | Shapoorji | 2026-03-04 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes
81 | Building A | Sharnam PMC | Shapoorji | 2026-03-05 | Unsafe Act at Excavation | Working in Pit | Closed the work | Open | No | No
82 | Building B | Sharnam PMC | Shapoorji | 2026-03-06 | Unsafe Act at 5th floor | PPE kit | Provided PPE kit to Worker | Closed | Yes | Yes

## NCR Summary
NCR Summary
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. | [6 empty] | Updated On:
Report No |  | Safari-Safety Observation Unsafe Act-Sharnam-001 | [5 empty] | Total Open | 11 | Total Closed | 5
S. No | Location | Issued By | Issued To | Issued On | Brief Description | NC Category | Action Taken by PMC | Status | Time Impact (Days) | Cost Impact (INR) | Remarks
1 | Building A | Sharnam PMC | Shapoorji | 2025-12-15 | Unsafe Act at Excavation | Near Miss | Closed the work | Open | No | No
2 | Building B | Sharnam PMC | Shapoorji | 2025-12-16 | Unsafe Act at 5th floor | Harassment | Provided PPE kit to Worker | Closed | Yes | Yes
3 | Building A | Sharnam PMC | Shapoorji | 2025-12-17 | Unsafe Act at Excavation | Psychological | Closed the work | Open | No | No
4 | Building B | Sharnam PMC | Shapoorji | 2025-12-18 | Unsafe Act at 5th floor | Illness | Provided PPE kit to Worker | Closed | Yes | Yes
5 | Building A | Sharnam PMC | Shapoorji | 2025-12-19 | Unsafe Act at Excavation | Injury | Closed the work | Open | No | No
6 | Building B | Sharnam PMC | Shapoorji | 2025-12-20 | Unsafe Act at 5th floor | Near Miss | Provided PPE kit to Worker | Closed | Yes | Yes
7 | Building A | Sharnam PMC | Shapoorji | 2025-12-21 | Unsafe Act at Excavation | Harassment | Closed the work | Open | No | No
8 | Building B | Sharnam PMC | Shapoorji | 2025-12-22 | Unsafe Act at 5th floor | Psychological | Provided PPE kit to Worker | Closed | Yes | Yes
9 | Building A | Sharnam PMC | Shapoorji | 2025-12-23 | Unsafe Act at Excavation | Illness | Closed the work | Open | No | No
10 | Building B | Sharnam PMC | Shapoorji | 2025-12-24 | Unsafe Act at 5th floor | Injury | Provided PPE kit to Worker | Open | Yes | Yes
11 | Building A | Sharnam PMC | Shapoorji | 2025-12-25 | Unsafe Act at Excavation | Near Miss | Closed the work | Open | No | No
12 | Building B | Sharnam PMC | Shapoorji | 2025-12-26 | Unsafe Act at 5th floor | Harassment | Provided PPE kit to Worker | Open | Yes | Yes
13 | Building A | Sharnam PMC | Shapoorji | 2025-12-27 | Unsafe Act at Excavation | Psychological | Closed the work | Open | No | No
14 | Building B | Sharnam PMC | Shapoorji | 2025-12-28 | Unsafe Act at 5th floor | Illness | Provided PPE kit to Worker | Open | Yes | Yes
15 | Building A | Sharnam PMC | Shapoorji | 2025-12-29 | Unsafe Act at Excavation | Injury | Closed the work | Open | No | No
16 | Building B | Sharnam PMC | Shapoorji | 2025-12-30 | Unsafe Act at 5th floor | Near Miss | Provided PPE kit to Worker | Closed | Yes | Yes

## Safety Hours
Safe Hours Summary
Name of Project |  | Safari Industrial Project at Halol GIDC
Name of Client |  | Safari India Pvt. Ltd.
Principle Consultant |  | Sharnam Project Development Consultant
PMC |  | Sharnam Project Development Consultant
Vendor |  | Shapoorji Pallonji Construction Pvt. Ltd. |  |  |  | Updated On:
Report No |  | Safari-Safety Observation Unsafe Act-Sharnam-001 |  |  | Project Start Date | 2025-12-01 | Last Accident Date | 2025-12-28 | 27
Sr.No | HSE indicators | Up to Previous Week (PW) | Current Week (CW) | Cumulative
1 | Safe-manhours | 7670 | 1350 | 9020
2 | Safe-man-days | 20 | 7 | 27
3 | Toolbox Talk | 32 | 7 | 39
4 | HSE induction | 17 | 2 | 19
5 | HSE trainings | 4 | 0 | 4
6 | Reported Incident/Accident | 1 | 0 | 1
7 | Site safety Instructions | 91 | 5 | 96
8 | NCN Raised | 2 | 0 | 2
9 | SOR Raised | 0 | 0 | 0
10 | FAC | 0 | 0 | 0
11 | Near Miss | 2 | 0 | 2
Sr.No | HSE indicators | Up to Previous Week (PW) | Current Week (CW) | Cumulative
1 | Safe-manhours | 76704 | 5192 | 81896
2 | Safe-man-days | 140 | 7 | 147
3 | Toolbox Talk | 32 | 2 | 34
4 | HSE induction | 17 | 0 | 17
5 | HSE trainings | 4 | 0 | 4
6 | Reported Incident/Accident | 0 | 0 | 0
7 | Site safety Instructions | 91 | 5 | 96
8 | NCN Raised | 2 | 0 | 2
9 | SOR Raised | 0 | 0 | 0
10 | FAC | 0 | 0 | 0
11 | Near Miss | 2 | 0 | 2
Sr.No | HSE indicators | Up to Previous Week (PW) | Current Week (CW) | Cumulative

## NCR
Site Safety Non Conformity Report
Name of Project | Safari Industrial Project at Halol GIDC
Name of Client | Safari India Pvt. Ltd.
Principle Consultant | Sharnam Project Development Consultant
PMC | Sharnam Project Development Consultant
Vendor | Shapoorji Pallonji Construction Pvt. Ltd. |  |  |  |  | Updated On:
NCR No | Safari-Safety NCR-Sharnam-001
Non-Conformity Safety Details
Activity/Task | [E.g., Excavation, Lifting, Electrical Work]
Non-Conformity Description | [Detailed explanation of the unsafe condition or action observed]
Category | [E.g., Working at Heights, PPE Non-Compliance, Housekeeping, Electrical Hazard, etc.]
Observed Risk Level | FALSE | Low | FALSE | Medium | FALSE | High
Photos/Attachments | [Attach relevant photos, sketches, or supporting documents]
Root Cause Analysis
Root Cause | [E.g., Lack of training, inadequate supervision, poor planning, defective equipment, etc.]
Contributing Factors | [Other issues that may have led to the non-conformity]
Corrective Actions
Immediate Action Taken | [Steps taken immediately to mitigate the risk or resolve the issue]
Long-Term Corrective Action | [Preventive measures to ensure the issue doesn’t reoccur]
Responsible Party | [Name or department responsible for corrective actions]
Target Completion Date | [DD/MM/YYYY]
Impact Assessment
Time Impact (Y/N) | [Yes/No, specify the extent of delay if applicable]
Cost Impact (Y/N) | [Yes/No, specify the estimated cost impact if applicable]
Follow-Up and Close-Out
Follow-Up Date | [DD/MM/YYYY]
Status | FALSE | Open
| FALSE | In Progress
| FALSE | Closed
Prepared By | Name: ______________
Signature: ____________
Reviewed By | Name: ______________
Signature: ____________ (Safety Officer)
Approved By | Name: ______________
Signature: ____________ (Project Manager)

## Observation - Unsafe Act
Site Unsafe Act Report
Name of Project | Safari Industrial Project at Halol GIDC
Name of Client | Safari India Pvt. Ltd.
Principle Consultant | Sharnam Project Development Consultant
PMC | Sharnam Project Development Consultant
Vendor | Shapoorji Pallonji Construction Pvt. Ltd. |  | Updated On:
Report No | Safari-Safety Observation Unsafe Act-Sharnam-001
Unsafe Act Details
Type of Unsafe Act | FALSE | Working at height
| FALSE | Improper tool use
| FALSE | Non-compliance with PPE
| FALSE | Poor housekeeping
| FALSE | Electrical hazards
| FALSE | Others: [Specify]
Description | [Brief details of the unsafe act, including location and task being performed.]
Location | Building A
Actions & Evidence
Immediate Action Taken | [E.g., Stopped work, provided PPE, isolated the hazard.]
Responsible Person | [Name & Role]
Photos/Sketches | [Attach if available]
Witnesses | [List of any witnesses with roles]
Risk & Recommendations
Risk Level | FALSE | Low
| FALSE | Medium
| FALSE | High
Consequences | [Injury, fatality, equipment damage, project delay, etc.]
Corrective Measures | [Long-term actions like training, new procedures, or equipment repair.]
Responsible Person/Dept. | [Name or department]
Deadline | [Specify timeline for rectification]
Follow-Up & Approvals
Follow-Up Date | [DD/MM/YYYY]
Status | FALSE | Open
| FALSE | In Progress
| FALSE | Closed
Prepared By | Name: ______________
Signature: ____________
Reviewed By | Name: ______________
Signature: ____________ (Safety Officer)
Approved By | Name: ______________
Signature: ____________ (Project Manager)

## HIRA
#VALUE! |  | Hazard Identification & Risk Assessment
|  | Sharnam Project Development Consultants | [10 empty] | ID No :
Revision :
Name of Project: Safari Industrial Plant |  |  | Location: Halol GIDC |  | Activity: Execution |  |  |  | Approved By: |  |  |  | Date:
Sr. No. | Activity | Risk ID | Hazard | Consequence | Legal Concerns (Y/N) | Risk Analysis |  |  | Control Measure | Residual Risk |  |  | Remarks if any
[6 empty] | Probability | Impact | Severity |  | Probability | Impact | Severity
A | Person working too close to the edge of excavationn | A1 | Fall of person into excavation | Major Injury | Yes | 3 | 3 | 9 | Barricading shall be provided. | 2 | 3 | 6
B | Improper house-keeping | B1 | Injury to personnel working near-by | Minor Injury | No | 3 | 2 | 6 | Proper house keeping shall be maintained | 2 | 2 | 4
C | Concreting | C1 | Earthing of vibrators not done | Can Cause short circuit | No | 3 | 2 | 6 | Ensure earthing of equipment before commencement of work | 1 | 2 | 2
|  | C2 | Continuous pouring by same gang | Cause tiredness of workers and may lead to accident | No | 2 | 3 | 6 | Insist on shift patterns | 1 | 3 | 3
D | Bar Bending & Bar Cutting Machine | D1 | Inexperienced operator | Major Injury | No | 3 | 3 | 9 | Ensure complete trained operator to be deployed. | 1 | 3 | 3
|  | D2 | Defective machine | Major Injury | Yes | 3 | 3 | 9 | Check machine condition before start | 2 | 3 | 6
|  | D3 | Loose Electrical connection | Fire/Short circuit | Yes | 3 | 3 | 9 | Electrical connection should connected with ELCB | 1 | 3 | 3
|  | D4 | Electrical shock | Fire/Short circuit | Yes | 3 | 2 | 6 | Body Earthing provided to machine | 1 | 3 | 3
|  | D5 | Hit by material | Minor Injury | Yes | 2 | 3 | 6 | Trained operator prrovided | 1 | 3 | 3
|  | D6 | Defective blades | Minor Injury | No | 2 | 1 | 2 | Check blade condition | 1 | 1 | 1
E | Reinforcement work | E1 | During unloading rods from truck deck | Injuries to the person due to hit while unloding rods | No | 3 | 2 | 6 | Unload bars from trailers as closer as possible to work area | 2 | 2 | 4
|  | E2 | Cutting of rods | Person may injured his finger or hand | No | 3 | 2 | 6 | Observe careful hand placement | 2 | 2 | 4
|  | E3 | Carrying of rods for long distance | Carrying of rods for short distance | No | 3 | 1 | 3 | Use proper lifting techniques | 1 | 1 | 1
|  | E4 | Bending of rods | Minor Injury | No | 2 | 2 | 4 | Get help with heavy / awkward bars | 1 | 2 | 2
F | Formwork | F1 | Working with cutting tools | May cause hand injury | No | 3 | 2 | 6 | Observe position of machine and work accordingly | 2 | 2 | 4
|  | F2 | Falling of shuttering materials | Major Injury | Yes | 2 | 2 | 4 | Safety net should be provided | 1 | 2 | 2
G | Preparation of shuttering | G1 | Nails not stacked properly | Eye Injury | No | 2 | 3 | 6 | Use magnet for collection of nails | 1 | 3 | 3
|  | G2 | Use of loose hammer | Major Injury | No | 3 | 2 | 6 | Use good condition of hammer | 1 | 2 | 2
H | Erection of shuttering on height | H1 | Fall of person | Major Injury | Yes | 2 | 4 | 8 | Safety belt should be provided | 1 | 4 | 4
|  | H2 | Fall of material | Major Injury | Yes | 2 | 4 | 8 | Safety net should be provided | 1 | 4 | 4
I | Walkway jellies laying/ removing | I1 | Fall of jallies | Major Injury | Yes | 2 | 3 | 6 | Walkway jallies should be bend with bending wires | 1 | 3 | 3
J | Concrete Pumping | J1 | Failure of equipment while working | Injuries/ fatal/ fracture and equipment damage | Yes | 2 | 5 | 10 | Check equipment before commencement of work | 1 | 5 | 5
K | Handling & Stacking of scaffold materia | K1 | Fall of material while loading & unloading | Injuries & fracture | No | 3 | 1 | 3 | Do not lift the materials with bundle ties and to be unloaded with suitablelifting equipments | 2 | 1 | 2
|  | K2 | Improper stacking | Minor Injury | No | 4 | 1 | 4 | Material should be stacked in stable manner and must be barricaded | 1 | 1 | 1
L | Working on scaffolding at height | L1 | Insufficient width of scaffold work platform | Injury/fatal | Yes | 4 | 5 | 20 | Proper width should be provided for working | 2 | 5 | 10
M | Use portable electrical power tools and electrical equipments | M1 | Inexperienced operator | Electrical shock and burn injury | No | 2 | 3 | 6 | Ensure complete trained operator to be deployed. | 1 | 3 | 3
N | Lifting of material | N1 | Failure of lifting gear, improper rigging | Fall of material from height, damages to material, man power | Yes | 2 | 5 | 10 | To ensure safety checklist before commencing work | 1 | 5 | 5
|  | N2 | Hit by object due with rapid speed of lowering hoist/hook. | Major Injury | Yes | 2 | 4 | 8 | Close supervision is required | 1 | 4 | 4
O | Other risk related to project | O1 | Fire Hazard | Major burn injuries | Yes | 1 | 5 | 5 | Fire enstigushier should be provided | 1 | 3 | 3
|  | O2 | Inflation in material rate | Increase cost more than estimated | No | 3 | 2 | 6 | Proper procurement strategy should be provided | 2 | 2 | 4
|  | O3 | Change in scope | Delay in project | No | 3 | 5 | 15 | Changes should be done as per the client's requirements and cost should be revised | 1 | 3 | 3
|  | O4 | Labour shortage | Delay in project | No | 4 | 4 | 16 | More sub contractors should be procured to mitigate labour shortage | 2 | 3 | 6
|  | O5 | Force Majure | Delay in project | No | 2 | 4 | 8 | Various Policies and Insurance should be taken by contractor | 2 | 3 | 6