## DASHBOARD
SPDC |  |  | DAILY PROGRESS REPORT | [10 empty] | Report Date |  |  | 2026-07-31
[14 empty] | Data Date |  |  | 2026-07-31
|  |  | CIVIL & STRUCTURAL WORKS PACKAGE | [10 empty] | Report No. / Day |  |  | DPR/CIV-027 ¦ Friday | [5 empty] | S-CURVE DATA (not printed)
Project Name |  | <Client / Project Name> | [5 empty] | Contract / PO Ref. |  | <Work Order No. & Date> |  |  |  | PROJECT HEALTH | [8 empty] | DATE | PLANNED CUM % | ACTUAL CUM % | NOTE
Project Manager |  | <PMC Project Manager> | [5 empty] | Contract Completion |  | 2026-09-30 |  |  |  | Overall Status |  |  |  | BEHIND PROGRAMME |  |  |  |  | 2026-07-01 | 0% | 0.1013% | from INPUT sheet section 14
Contractor / Vendor |  | <Executing Agency / PEB Vendor> | [5 empty] | Calendar / Weather |  | 6 Days / Week – 8 hrs ¦ Partly Cloudy, 32 °C |  |  |  | Critical / High issues open |  |  |  | 3 |  |  |  |  | 2026-07-06 | 0.1529% | 0.9988% | from INPUT sheet section 14
Location |  | <Plot / GIDC / District> | [5 empty] | Contract Value (₹ Lakh) |  | 321.064 |  |  |  | Approvals pending > 7 days |  |  |  | 2 |  |  |  |  | 2026-07-11 | 0.9886% | 2.197% | from INPUT sheet section 14
1. KEY PERFORMANCE INDICATORS (all calculated — nothing is typed on this sheet) | [22 empty] | 2026-07-16 | 6.283% | 7% | from INPUT sheet section 14
PLANNED % |  |  | ACTUAL % |  |  | VARIANCE |  |  | SPI |  |  | EARNED VALUE ₹ L |  |  | VALUE DONE TODAY ₹ |  |  | ITEMS DELAYED |  | HRS LOST TODAY |  |  | 2026-07-21 | 16.62% | 16.5% | from INPUT sheet section 14
41.56% |  |  | 37.46% |  |  | -4.105% |  |  | 0.90125 |  |  | 120.267 |  |  | 552400 |  |  | 4 |  | 4.25 |  |  | 2026-07-26 | 29.31% | 28.5% | from INPUT sheet section 14
2. QUANTITY / PHYSICAL PROGRESS — BOQ ITEM-WISE (basis of the % complete above) | [22 empty] | 2026-07-31 | 41.56% | 37.46% | ◄ today – from the quantity table
SL | DESCRIPTION OF ITEM |  |  |  | UNIT | SCOPE QTY | RATE ₹ | WEIGHT-AGE % | START | FINISH | DAYS +/− | PLANNED % | CUM QTY PREV. | QTY TODAY | CUM QTY TO DATE | BALANCE QTY | % COMPL. | EARNED ₹ TODAY | WTD. PLANNED % | WTD. ACTUAL % | STATUS |  | 2026-08-05 | 52.24% |  | from INPUT sheet section 14
1 | Excavation for footings – GL-1 to GL-4 |  |  |  | CUM | 1500 | 180 | 0.841% | 2026-07-05 | 2026-07-15 | -16 | 100% | 1500 | 0 | 1500 | 0 | 100% | 0 | 0.841% | 0.841% | Completed | CIV-10 | 2026-08-10 | 60.95% |  | from INPUT sheet section 14
2 | Excavation for footings – GL-5 to GL-9 |  |  |  | CUM | 1700 | 180 | 0.9531% | 2026-07-12 | 2026-07-23 | -8 | 100% | 1560 | 90 | 1650 | 50 | 97.06% | 16200 | 0.9531% | 0.925% | In Progress | CIV-10 | 2026-08-15 | 65.68% |  | from INPUT sheet section 14
3 | PCC 1:4:8 below footings |  |  |  | CUM | 210 | 5200 | 3.401% | 2026-07-10 | 2026-07-24 | -7 | 100% | 186 | 8 | 194 | 16 | 92.38% | 41600 | 3.401% | 3.142% | In Progress | CIV-10 | 2026-08-20 | 69.13% |  | from INPUT sheet section 14
4 | Reinforcement Fe 500 D – GL-1 to GL-4 |  |  |  | MT | 44 | 82000 | 11.24% | 2026-07-13 | 2026-07-25 | -6 | 100% | 44 | 0 | 44 | 0 | 100% | 0 | 11.24% | 11.24% | Completed | CIV-10 | 2026-08-25 | 72.56% |  | from INPUT sheet section 14
5 | Reinforcement Fe 500 D – GL-5 to GL-9 |  |  |  | MT | 52 | 82000 | 13.28% | 2026-07-20 | 2026-08-05 | 5 | 70.59% | 26.4 | 2.8 | 29.2 | 22.8 | 56.15% | 229600 | 9.375% | 7.458% | Delay | CIV-10 | 2026-08-30 | 75.54% |  | from INPUT sheet section 14
6 | Footing concrete M30 – GL-1 to GL-4 |  |  |  | CUM | 380 | 7400 | 8.758% | 2026-07-18 | 2026-07-29 | -2 | 100% | 372 | 8 | 380 | 0 | 100% | 59200 | 8.758% | 8.758% | Completed | CIV-10
7 | Footing concrete M30 – GL-5 to GL-9 |  |  |  | CUM | 400 | 7400 | 9.219% | 2026-07-27 | 2026-08-10 | 10 | 33.33% | 62 | 14 | 76 | 324 | 19% | 103600 | 3.073% | 1.752% | Delay | CIV-10
8 | Pedestal shuttering & casting |  |  |  | NOS | 56 | 18500 | 3.227% | 2026-07-24 | 2026-08-12 | 12 | 40% | 19 | 2 | 21 | 35 | 37.5% | 37000 | 1.291% | 1.21% | In Progress | CIV-10
9 | Anchor bolt template setting & grouting |  |  |  | NOS | 224 | 2600 | 1.814% | 2026-07-26 | 2026-08-12 | 12 | 33.33% | 58 | 8 | 66 | 158 | 29.46% | 20800 | 0.6047% | 0.5345% | In Progress | CIV-10
10 | Backfilling & compaction in 200 mm layers |  |  |  | CUM | 2400 | 260 | 1.944% | 2026-07-28 | 2026-08-11 | 11 | 26.67% | 440 | 60 | 500 | 1900 | 20.83% | 15600 | 0.5183% | 0.4049% | Delay | CIV-20
11 | Plinth beam RCC M30 with shuttering |  |  |  | CUM | 210 | 9600 | 6.279% | 2026-08-05 | 2026-08-17 | 17 | 0% | 0 | 0 | 0 | 210 | 0% | 0 | 0% | 0% | Not Started | CIV-20
12 | GSB / WMM sub-base under floor |  |  |  | CUM | 1600 | 1450 | 7.226% | 2026-08-14 | 2026-08-29 | 29 | 0% | 0 | 0 | 0 | 1600 | 0% | 0 | 0% | 0% | Not Started | CIV-30
13 | Floor PCC & VDF with hardener topping |  |  |  | SQM | 6400 | 980 | 19.54% | 2026-09-01 | 2026-09-26 | 57 | 0% | 0 | 0 | 0 | 6400 | 0% | 0 | 0% | 0% | Not Started | CIV-30
14 | Block masonry & plaster – office block |  |  |  | SQM | 2800 | 860 | 7.5% | 2026-08-20 | 2026-09-20 | 51 | 0% | 0 | 0 | 0 | 2800 | 0% | 0 | 0% | 0% | Not Started | CIV-40
15 | U/G drainage lines & chambers |  |  |  | RM | 640 | 2400 | 4.784% | 2026-07-26 | 2026-08-13 | 13 | 31.58% | 148 | 12 | 160 | 480 | 25% | 28800 | 1.511% | 1.196% | Delay | CIV-50
TOTAL / OVERALL PACKAGE PROGRESS |  |  |  |  | ₹ 321.1 Lakh |  |  | 100% | PROGRAMME |  |  | 41.56% |  |  |  |  | 37.46% | 552400 | 41.56% | 37.46% | BEHIND
3. PROGRESS SUMMARY BY GROUP (value weighted) | [9 empty] | 4. PROGRESS S-CURVE (PLANNED vs ACTUAL)
GROUP |  | DESCRIPTION |  |  | WEIGHTAGE |  | PLANNED % | ACTUAL % | SPI
CIV-10 |  | Substructure – Excavation, PCC, Footings, Pedestals |  |  | 52.73% |  | 74.97% | 68% | 0.90701
CIV-20 |  | Superstructure RCC – Backfill, Plinth Beams |  |  | 8.223% |  | 6.303% | 4.924% | 0.78125
CIV-30 |  | Flooring – Sub-base, PCC, VDF |  |  | 26.76% |  | 0% | 0%
CIV-40 |  | Masonry, Plaster & Finishing |  |  | 7.5% |  | 0% | 0%
CIV-50 |  | External – Drainage, Sump, Paving |  |  | 4.784% |  | 31.58% | 25% | 0.79167
TOTAL |  |  |  |  | 100% |  | 41.56% | 37.46% | 0.90125
5. EARNED VALUE / COMMERCIAL SNAPSHOT (₹ in Lakh)
BAC – Contract value of package | [6 empty] | 321.064
PV – Planned Value (BAC × Planned %) | [6 empty] | 133.4453
EV – Earned Value (BAC × Actual %) | [6 empty] | 120.267
AC – Certified / paid to date | [6 empty] | 126
SV – Schedule Variance (EV − PV) | [6 empty] | -13.1783
CV – Cost Variance (EV − AC) | [6 empty] | -5.733
CPI ¦ EAC (BAC ÷ CPI) | [6 empty] | 0.95 ¦ ₹ 336.4 L
6. MANPOWER DEPLOYED TODAY | [6 empty] | 7. EQUIPMENT UTILIZATION TODAY | [6 empty] | 8. KEY MATERIAL AT SITE
TRADE / CATEGORY |  |  | PLAN | ACTUAL | MAN-DAYS |  | EQUIPMENT |  |  | QTY | WORKED HRS | IDLE HRS | UTIL. % | MATERIAL |  |  | UNIT | OPENING | RECD. | CONSUMED | BALANCE
Mason |  |  | 16 | 14 | 14.875 |  | Excavator – JCB 3DX |  |  | 2 | 13 | 3 | 81.25% | Cement OPC 53 |  |  | BAGS | 640 | 200 | 180 | 660
Bar Bender |  |  | 14 | 12 | 13.5 |  | Transit Mixer 6 CUM |  |  | 3 | 18 | 6 | 75% | Reinforcement Fe 500 D |  |  | KGS | 18500 | 4000 | 3250 | 19250
Carpenter – Shuttering |  |  | 12 | 10 | 10.625 |  | Concrete Boom Pump 36 m |  |  | 1 | 5 | 3 | 62.5% | RMC M30 (direct pour) |  |  | CUM | 0 | 96 | 96 | 0
Helper / Unskilled |  |  | 26 | 22 | 23.375 |  | Needle Vibrator 40 mm |  |  | 4 | 24.8 | 7.2 | 77.5% | Coarse Aggregate 20 / 10 mm |  |  | CUM | 127 | 30 | 26 | 131
Operators – Machine & Pump |  |  | 9 | 8 | 8 |  | Bar Cutting / Bending M/C |  |  | 4 | 28.4 | 3.6 | 88.75% | Shuttering Ply 12 mm |  |  | SQM | 420 | 60 | 0 | 480
Supervisor & PMC Staff |  |  | 7 | 7 | 7.875 |  | De-watering Pump & DG Set |  |  | 5 | 29.5 | 10.5 | 73.75% | Cover Blocks & Binding Wire |  |  | NOS | 4380 | 1000 | 872 | 4508
TOTAL WORKERS / MAN-DAYS |  |  | 84 | 73 | 78.25 |  | TOTAL / AVERAGE |  |  | 19 | 118.7 | 33.3 | 78.09% | Balance = Opening + Received − Consumed · carry Balance forward as tomorrow's Opening on the INPUT sheet
9. QUALITY CONTROL & TESTS TODAY | [6 empty] | 10. HSE / SAFETY STATISTICS | [6 empty] | 11. DELAY / IDLE TIME LOG TODAY
Pour cards offered / approved |  |  |  |  | 8 / 8 |  | Safe man-hours – today / cumulative |  |  |  |  | 626 / 42,776 |  | CAUSE (CATEGORY) |  |  |  | FROM | TO | HRS LOST | EOT
Concrete cube sets cast / slump tests |  |  |  |  | 4 / 8 |  | Days without LTI |  |  |  |  | 122 |  | Rain – concreting stopped (Weather) |  |  |  | 14:20 | 15:50 | 1.5 | Review
Reinforcement & shuttering checklists |  |  |  |  | 5 of 6 cleared |  | Toolbox talks conducted |  |  |  |  | 3 |  | RMC dispatch delayed – plant queue (Contractor) |  |  |  | 9:15 | 10:00 | 0.75 | No
7-day cube result (M30) |  |  |  |  | 24.8 N/mm² – OK |  | Permits to work issued |  |  |  |  | 5 |  | Anchor bolt template not released (Client / Vendor) |  |  |  | 11:00 | 13:00 | 2 | Yes
NCRs open / closed today |  |  |  |  | 2 / 1 |  | Safety observations raised / closed |  |  |  |  | 6 / 5 | [5 empty] | 0:00 | 0:00 |  | 0
Field density (compaction) tests |  |  |  |  | 3 taken, 2 pass |  | Near miss / first aid today |  |  |  |  | 1 / 0 |  | TOTAL HOURS LOST TODAY | [5 empty] | 4.25 | 1 EOT
12. DRAWINGS / RFI / MATERIAL APPROVALS PENDING | [10 empty] | 13. ISSUES & RISKS (open items)
REF. NO. |  | DESCRIPTION | [5 empty] | RAISED ON | AGEING | PENDING WITH | ISSUE / RISK DESCRIPTION | [6 empty] | SEVERITY |  | OWNER
RFI-062 |  | Pedestal top level at GL-7 – drawing conflict | [5 empty] | 2026-07-26 | 5 | Consultant | ⚠ Anchor bolt template pending from PEB vendor – critical path | [6 empty] | Critical |  | Client
DWG-118 |  | Plinth beam GFC drawing rev-2 | [5 empty] | 2026-07-22 | 9 | Consultant | ⚠ 16 mm dia reinforcement stock down to 3 days cover | [6 empty] | High |  | Contractor
MAR-044 |  | Floor hardener – brand approval | [5 empty] | 2026-07-16 | 15 | Client | ⚠ Cube test reports of 22-Jul pour not submitted | [6 empty] | High |  | Contractor
MAR-043 |  | Admixture – third party test certificate | [5 empty] | 2026-07-24 | 7 | PMC | ⚠ Monsoon water logging in GL-7 to GL-9 pits | [6 empty] | Medium |  | Contractor
14. TODAY'S HIGHLIGHTS | [10 empty] | 15. NEXT DAY PLAN
★ Footing concreting completed up to Grid Line GL-4 – 42 nos. | [10 empty] | ➜ Footing reinforcement GL-5 to GL-6 – 8 nos. to be completed
★ Pedestal shuttering of 6 nos. completed and offered for inspection | [10 empty] | ➜ Pedestal concreting – 6 nos. with anchor bolt templates
★ 7-day cube strength 24.8 N/mm² against M30 – satisfactory | [10 empty] | ➜ Backfilling in completed footing pits GL-1 to GL-3
★ U/G drainage trench excavation completed up to Chamber-6 | [10 empty] | ➜ Offer plinth beam reinforcement for PMC inspection
16. DECISIONS / INSTRUCTIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
1. Release of anchor bolt template drawing by PEB vendor – required by 01-Aug-26 to protect the critical path
2. Approval of floor hardener brand (MAR-044) – pending 15 days, blocks flooring procurement
3. Reply to RFI-062 on pedestal top level at GL-7 – concreting of 6 pedestals held pending confirmation
Prepared By |  |  |  |  | Checked By |  |  |  |  | Approved By |  |  |  |  | Client Representative
Name / Sign / Date — Site Engineer – SPDC |  |  |  |  | Name / Sign / Date — QA/QC Engineer – SPDC |  |  |  |  | Name / Sign / Date — Project Manager – SPDC |  |  |  |  | Name / Sign / Date — For and on behalf of Client
Sharnam Project Development Consultants & Co. (SPDC), Vadodara ¦ Project Management Consultancy ¦ THIS SHEET IS ALL FORMULAS — enter data on the INPUT sheet ¦ A3 Landscape – Page 1 of 1

## INPUT
DAILY INPUT SHEET — CIVIL & STRUCTURAL WORKS PACKAGE
TYPE ONLY IN THE YELLOW CELLS ON THIS SHEET. The DASHBOARD sheet is the printed DPR — it is all formulas and must not be typed over. Fill top to bottom, then print the DASHBOARD to PDF.
1. PROJECT HEADER (change once at the start, then only the dates each day)
Project name | <Client / Project Name>
Project manager | <PMC Project Manager>
Contractor / vendor | <Executing Agency / PEB Vendor>
Location | <Plot / GIDC / District>
Prepared by | Site Engineer – SPDC (PMC)
Contract / PO reference | <Work Order No. & Date>
Contract completion date | 2026-09-30
Calendar / working hours | 6 Days / Week – 8 hrs |  |  | Shift hours drive man-days & utilization
Shift hours per day | 8 |  |  | Used for man-days and equipment utilization
Weather | Partly Cloudy, 32 °C
REPORT DATE | 2026-07-31
DATA DATE (cut-off) | 2026-07-31 |  |  | Every planned % is measured to this date
Report number | DPR/CIV-027
AC – certified / paid to date (₹ Lakh) | 126 |  |  | From the RA bill / cost report
Cumulative man-days upto previous day | 1180
Cumulative safe man-hours upto prev. day | 42150
Date of last LTI | 2026-03-31 |  |  | Days without LTI counts from here
2. QUANTITY PROGRESS (one row per BOQ / scope item — type today's quantity in the last column)
GROUP | DESCRIPTION OF ITEM |  | UNIT | SCOPE / BOQ QTY | RATE ₹ | START | FINISH | CUM QTY UPTO PREV. | QTY TODAY
CIV-10 | Excavation for footings – GL-1 to GL-4 |  | CUM | 1500 | 180 | 2026-07-05 | 2026-07-15 | 1500 | 0
CIV-10 | Excavation for footings – GL-5 to GL-9 |  | CUM | 1700 | 180 | 2026-07-12 | 2026-07-23 | 1560 | 90
CIV-10 | PCC 1:4:8 below footings |  | CUM | 210 | 5200 | 2026-07-10 | 2026-07-24 | 186 | 8
CIV-10 | Reinforcement Fe 500 D – GL-1 to GL-4 |  | MT | 44 | 82000 | 2026-07-13 | 2026-07-25 | 44 | 0
CIV-10 | Reinforcement Fe 500 D – GL-5 to GL-9 |  | MT | 52 | 82000 | 2026-07-20 | 2026-08-05 | 26.4 | 2.8
CIV-10 | Footing concrete M30 – GL-1 to GL-4 |  | CUM | 380 | 7400 | 2026-07-18 | 2026-07-29 | 372 | 8
CIV-10 | Footing concrete M30 – GL-5 to GL-9 |  | CUM | 400 | 7400 | 2026-07-27 | 2026-08-10 | 62 | 14
CIV-10 | Pedestal shuttering & casting |  | NOS | 56 | 18500 | 2026-07-24 | 2026-08-12 | 19 | 2
CIV-10 | Anchor bolt template setting & grouting |  | NOS | 224 | 2600 | 2026-07-26 | 2026-08-12 | 58 | 8
CIV-20 | Backfilling & compaction in 200 mm layers |  | CUM | 2400 | 260 | 2026-07-28 | 2026-08-11 | 440 | 60
CIV-20 | Plinth beam RCC M30 with shuttering |  | CUM | 210 | 9600 | 2026-08-05 | 2026-08-17 | 0 | 0
CIV-30 | GSB / WMM sub-base under floor |  | CUM | 1600 | 1450 | 2026-08-14 | 2026-08-29 | 0 | 0
CIV-30 | Floor PCC & VDF with hardener topping |  | SQM | 6400 | 980 | 2026-09-01 | 2026-09-26 | 0 | 0
CIV-40 | Block masonry & plaster – office block |  | SQM | 2800 | 860 | 2026-08-20 | 2026-09-20 | 0 | 0
CIV-50 | U/G drainage lines & chambers |  | RM | 640 | 2400 | 2026-07-26 | 2026-08-13 | 148 | 12
3. MANPOWER DEPLOYED TODAY
TRADE / CATEGORY |  | PLANNED NOS | ACTUAL NOS | HOURS WORKED
Mason |  | 16 | 14 | 8.5
Bar Bender |  | 14 | 12 | 9
Carpenter – Shuttering |  | 12 | 10 | 8.5
Helper / Unskilled |  | 26 | 22 | 8.5
Operators – Machine & Pump |  | 9 | 8 | 8
Supervisor & PMC Staff |  | 7 | 7 | 9
4. EQUIPMENT DEPLOYED TODAY
EQUIPMENT |  | QTY | WORKED HRS | IDLE HRS
Excavator – JCB 3DX |  | 2 | 13 | 3
Transit Mixer 6 CUM |  | 3 | 18 | 6
Concrete Boom Pump 36 m |  | 1 | 5 | 3
Needle Vibrator 40 mm |  | 4 | 24.8 | 7.2
Bar Cutting / Bending M/C |  | 4 | 28.4 | 3.6
De-watering Pump & DG Set |  | 5 | 29.5 | 10.5
5. MATERIAL AT SITE
MATERIAL |  | UNIT | OPENING STOCK | RECEIVED TODAY | CONSUMED / ISSUED
Cement OPC 53 |  | BAGS | 640 | 200 | 180
Reinforcement Fe 500 D |  | KGS | 18500 | 4000 | 3250
RMC M30 (direct pour) |  | CUM | 0 | 96 | 96
Coarse Aggregate 20 / 10 mm |  | CUM | 127 | 30 | 26
Shuttering Ply 12 mm |  | SQM | 420 | 60 | 0
Cover Blocks & Binding Wire |  | NOS | 4380 | 1000 | 872
6. QUALITY CONTROL & TESTS TODAY
QUALITY / TEST PARAMETER |  | TODAY'S FIGURE
Pour cards offered / approved |  | 8 / 8
Concrete cube sets cast / slump tests |  | 4 / 8
Reinforcement & shuttering checklists |  | 5 of 6 cleared
7-day cube result (M30) |  | 24.8 N/mm² – OK
NCRs open / closed today |  | 2 / 1
Field density (compaction) tests |  | 3 taken, 2 pass
7. HSE / SAFETY STATISTICS
HSE PARAMETER |  | TODAY'S FIGURE
Safe man-hours – today / cumulative |  | 626 / 42,776
Days without LTI |  | 122
Toolbox talks conducted |  | 3
Permits to work issued |  | 5
Safety observations raised / closed |  | 6 / 5
Near miss / first aid today |  | 1 / 0
8. DELAY / IDLE TIME LOG TODAY (enter clock times — hours are calculated)
CAUSE OF DELAY / IDLE TIME |  | CATEGORY | FROM | TO | EOT
Rain – concreting stopped |  | Weather | 14:20 | 15:50 | Review
RMC dispatch delayed – plant queue |  | Contractor | 9:15 | 10:00 | No
Anchor bolt template not released |  | Client / Vendor | 11:00 | 13:00 | Yes
9. DRAWINGS / RFI / MATERIAL APPROVALS PENDING (ageing is calculated)
REF. NO. | DESCRIPTION |  | RAISED ON | PENDING WITH
RFI-062 | Pedestal top level at GL-7 – drawing conflict |  | 2026-07-26 | Consultant
DWG-118 | Plinth beam GFC drawing rev-2 |  | 2026-07-22 | Consultant
MAR-044 | Floor hardener – brand approval |  | 2026-07-16 | Client
MAR-043 | Admixture – third party test certificate |  | 2026-07-24 | PMC
10. ISSUES & RISKS (open items)
ISSUE / RISK DESCRIPTION |  |  | SEVERITY | OWNER
Anchor bolt template pending from PEB vendor – critical path |  |  | Critical | Client
16 mm dia reinforcement stock down to 3 days cover |  |  | High | Contractor
Cube test reports of 22-Jul pour not submitted |  |  | High | Contractor
Monsoon water logging in GL-7 to GL-9 pits |  |  | Medium | Contractor
11. TODAY'S HIGHLIGHTS
Footing concreting completed up to Grid Line GL-4 – 42 nos.
Pedestal shuttering of 6 nos. completed and offered for inspection
7-day cube strength 24.8 N/mm² against M30 – satisfactory
U/G drainage trench excavation completed up to Chamber-6
12. NEXT DAY PLAN
Footing reinforcement GL-5 to GL-6 – 8 nos. to be completed
Pedestal concreting – 6 nos. with anchor bolt templates
Backfilling in completed footing pits GL-1 to GL-3
Offer plinth beam reinforcement for PMC inspection
13. DECISIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
Release of anchor bolt template drawing by PEB vendor – required by 01-Aug-26 to protect the critical path
Approval of floor hardener brand (MAR-044) – pending 15 days, blocks flooring procurement
Reply to RFI-062 on pedestal top level at GL-7 – concreting of 6 pedestals held pending confirmation
14. S-CURVE ACTUAL HISTORY (enter once per reporting period — today's point is automatic)
DATE | ACTUAL CUM % ON THAT DATE | NOTE
2026-07-01 | 0.1013% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-06 | 0.9988% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-11 | 2.197% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-16 | 7% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-21 | 16.5% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-26 | 28.5% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-31 | ◄ calculated on the DASHBOARD | TODAY — taken from the quantity table, do not type
2026-08-05 |  | leave blank until that date is reported
2026-08-10 |  | leave blank until that date is reported
2026-08-15 |  | leave blank until that date is reported
2026-08-20 |  | leave blank until that date is reported
2026-08-25 |  | leave blank until that date is reported
2026-08-30 |  | leave blank until that date is reported

## S-Curve Calc
S-CURVE CALCULATION — ACTUAL % ON EACH REPORTING DATE (CIVIL)
Enter the CUMULATIVE quantity of each item as it stood on each reporting date (from that day's measurement book / issued DPR). The bottom row converts them into the weighted actual % for that date and feeds INPUT section 14 and the S-curve. Once a column is filled it never changes again.
SL | DESCRIPTION OF ITEM | UNIT | SCOPE QTY | WEIGHT-AGE % | 2026-07-01 | 2026-07-06 | 2026-07-11 | 2026-07-16 | 2026-07-21 | 2026-07-26 | 2026-07-31 | 2026-08-05 | 2026-08-10 | 2026-08-15 | 2026-08-20 | 2026-08-25 | 2026-08-30
1 | Excavation for footings – GL-1 to GL-4 | CUM | 1500 | 0.841% | 2026-07-01: 4; 2026-07-06: 40.04; 2026-07-11: 88.1; 2026-07-16: 280.31; 2026-07-21: 660.72; 2026-07-26: 1141.25
2 | Excavation for footings – GL-5 to GL-9 | CUM | 1700 | 0.9531% | 2026-07-01: 4.4; 2026-07-06: 44.05; 2026-07-11: 96.91; 2026-07-16: 308.34; 2026-07-21: 726.8; 2026-07-26: 1255.38
3 | PCC 1:4:8 below footings | CUM | 210 | 3.401% | 2026-07-01: 0.52; 2026-07-06: 5.18; 2026-07-11: 11.39; 2026-07-16: 36.25; 2026-07-21: 85.45; 2026-07-26: 147.6
4 | Reinforcement Fe 500 D – GL-1 to GL-4 | MT | 44 | 11.24% | 2026-07-01: 0.12; 2026-07-06: 1.17; 2026-07-11: 2.58; 2026-07-16: 8.22; 2026-07-21: 19.38; 2026-07-26: 33.48
5 | Reinforcement Fe 500 D – GL-5 to GL-9 | MT | 52 | 13.28% | 2026-07-01: 0.08; 2026-07-06: 0.78; 2026-07-11: 1.71; 2026-07-16: 5.46; 2026-07-21: 12.86; 2026-07-26: 22.22
6 | Footing concrete M30 – GL-1 to GL-4 | CUM | 380 | 8.758% | 2026-07-01: 1.01; 2026-07-06: 10.14; 2026-07-11: 22.32; 2026-07-16: 71.01; 2026-07-21: 167.38; 2026-07-26: 289.12
7 | Footing concrete M30 – GL-5 to GL-9 | CUM | 400 | 9.219% | 2026-07-01: 0.2; 2026-07-06: 2.03; 2026-07-11: 4.46; 2026-07-16: 14.2; 2026-07-21: 33.48; 2026-07-26: 57.82
8 | Pedestal shuttering & casting | NOS | 56 | 3.227% | 2026-07-01: 0.06; 2026-07-06: 0.56; 2026-07-11: 1.23; 2026-07-16: 3.92; 2026-07-21: 9.25; 2026-07-26: 15.98
9 | Anchor bolt template setting & grouting | NOS | 224 | 1.814% | 2026-07-01: 0.18; 2026-07-06: 1.76; 2026-07-11: 3.88; 2026-07-16: 12.33; 2026-07-21: 29.07; 2026-07-26: 50.22
10 | Backfilling & compaction in 200 mm layers | CUM | 2400 | 1.944% | 2026-07-01: 1.33; 2026-07-06: 13.35; 2026-07-11: 29.37; 2026-07-16: 93.44; 2026-07-21: 220.24; 2026-07-26: 380.42
11 | Plinth beam RCC M30 with shuttering | CUM | 210 | 6.279% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
12 | GSB / WMM sub-base under floor | CUM | 1600 | 7.226% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
13 | Floor PCC & VDF with hardener topping | SQM | 6400 | 19.54% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
14 | Block masonry & plaster – office block | SQM | 2800 | 7.5% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
15 | U/G drainage lines & chambers | RM | 640 | 4.784% | 2026-07-01: 0.43; 2026-07-06: 4.27; 2026-07-11: 9.4; 2026-07-16: 29.9; 2026-07-21: 70.48; 2026-07-26: 121.73
WEIGHTED ACTUAL % ON THAT DATE |  |  |  | 100% | 0.1013% | 0.9988% | 2.197% | 7% | 16.5% | 28.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
FORMULA: Actual % on a date = Σ [ item weightage × ( cumulative qty on that date ÷ scope qty ) ] — the same weighted calculation the DASHBOARD does for today, only using the quantities as they stood on that earlier date.
SHORTCUT: if the DPR was already issued on that date, simply type the Actual % printed on it over the green formula in INPUT section 14 — both routes give the same figure. NOTE: weightage is taken from the CURRENT rates, so if a rate is revised later, re-issued history will shift slightly; the figures on the DPRs already signed remain the record.

## Guide
HOW THIS FILE WORKS — CIVIL DPR
| Two sheets only | INPUT — you type here, top to bottom, yellow cells only. DASHBOARD — the printed DPR, 100% formulas, never typed. Guide — this page.
| Daily routine | Open INPUT → change Report Date and Data Date → enter today's quantities, manpower, equipment, material, quality, HSE, delays, pending approvals, issues, highlights, next-day plan → open DASHBOARD → print to PDF.
| Adding / removing an item | Insert or delete a row inside the quantity block on INPUT and the same row position on DASHBOARD; every formula uses ranges, so totals follow.
| Weightage % | Scope Qty × Rate ÷ Σ(Scope Qty × Rate). Value weightage — always totals 100%.
| Planned % | IF(Data Date ≥ Finish, 100%, IF(Data Date < Start, 0%, (Data Date − Start + 1) ÷ (Finish − Start + 1))) — the programme prorated to the cut-off date.
| Days +/− | Finish − Data Date. Negative and red means the item is already past its programmed finish.
| Cum Qty To Date / Balance | Cum upto previous + Qty today · Scope Qty − Cum to date.
| % Complete | MIN(Cum Qty To Date ÷ Scope Qty, 1), shown with an in-cell data bar.
| Earned ₹ today | Qty today × Rate — the value of work done in the day, totalled in the KPI strip.
| Package Planned / Actual % | Σ(Weightage × Planned %) and Σ(Weightage × % Complete). These two totals drive the KPI strip, group summary, earned value block and S-curve.
| Status | Not Started / Completed / On Track (actual ≥ planned) / In Progress / Delay — colour coded.
| Group summary | SUMIFS of the weighted columns by group code ÷ that group's weightage.
| Earned value | BAC = Σ(Qty × Rate) ÷ 1,00,000 · PV = BAC × Planned % · EV = BAC × Actual % · SV = EV − PV · CV = EV − AC · CPI = EV ÷ AC · EAC = BAC ÷ CPI. Only AC is typed.
| Section 6 / 7 / 8 | Man-days = Actual Nos × hours ÷ shift hours · Utilization = Worked ÷ (Qty × shift hours) · Balance stock = Opening + Received − Consumed.
| Hours lost | (To − From) × 24 from the clock times on INPUT. EOT count is a COUNTIF of the Yes entries.
| Approval ageing | Data Date − Raised on; red beyond 7 days, and counted in the Project Health box.
| S-curve actual history | Actual % on any past date = Σ [ item weightage × (cumulative qty on that date ÷ scope qty) ]. The S-CURVE CALC sheet does this for you — enter each item's cumulative quantity as it stood on each reporting date and the bottom row gives the %, which flows into INPUT section 14. If that day's DPR was already issued, just type the Actual % from it instead.
| S-curve | Planned line = SUMPRODUCT of every item's weightage × its time-prorated fraction at each date — built entirely from the programme. Actual history comes from INPUT section 14; today's point is taken live from the quantity table.
| Paper | DASHBOARD is set to A3 landscape, fit to one page. Prints on A4 at about 70% if needed.
| Roll over to the next day | Save a copy with the new date. On INPUT: move Cum Qty To Date into 'Cum qty upto prev.', move material Balance into Opening, clear Qty Today, update the cumulative man-days and man-hours.