## DASHBOARD
SPDC |  |  | DAILY PROGRESS REPORT | [10 empty] | Report Date |  |  | 2026-07-31
[14 empty] | Data Date |  |  | 2026-07-31
|  |  | MECHANICAL WORKS PACKAGE — EQUIPMENT ERECTION, PIPING & HVAC | [10 empty] | Report No. / Day |  |  | DPR/MEC-027 ¦ Friday | [5 empty] | S-CURVE DATA (not printed)
Project Name |  | <Client / Project Name> | [5 empty] | Contract / PO Ref. |  | <Work Order No. & Date> |  |  |  | PROJECT HEALTH | [8 empty] | DATE | PLANNED CUM % | ACTUAL CUM % | NOTE
Project Manager |  | <PMC Project Manager> | [5 empty] | Contract Completion |  | 2026-09-30 |  |  |  | Overall Status |  |  |  | BEHIND PROGRAMME |  |  |  |  | 2026-07-01 | 0% | 0% | from INPUT sheet section 14
Contractor / Vendor |  | <Executing Agency / PEB Vendor> | [5 empty] | Calendar / Weather |  | 6 Days / Week – 8 hrs ¦ Partly Cloudy, 32 °C |  |  |  | Critical / High issues open |  |  |  | 3 |  |  |  |  | 2026-07-06 | 0% | 0.9976% | from INPUT sheet section 14
Location |  | <Plot / GIDC / District> | [5 empty] | Contract Value (₹ Lakh) |  | 155.63 |  |  |  | Approvals pending > 7 days |  |  |  | 2 |  |  |  |  | 2026-07-11 | 0.08682% | 2.801% | from INPUT sheet section 14
1. KEY PERFORMANCE INDICATORS (all calculated — nothing is typed on this sheet) | [22 empty] | 2026-07-16 | 0.8813% | 4.799% | from INPUT sheet section 14
PLANNED % |  |  | ACTUAL % |  |  | VARIANCE |  |  | SPI |  |  | EARNED VALUE ₹ L |  |  | VALUE DONE TODAY ₹ |  |  | ITEMS DELAYED |  | HRS LOST TODAY |  |  | 2026-07-21 | 2.81% | 7.198% | from INPUT sheet section 14
10.49% |  |  | 10.24% |  |  | -0.2477% |  |  | 0.97638 |  |  | 15.935 |  |  | 201100 |  |  | 1 |  | 5.5 |  |  | 2026-07-26 | 6.349% | 9.197% | from INPUT sheet section 14
2. QUANTITY / PHYSICAL PROGRESS — ITEM-WISE (basis of the % complete above) | [22 empty] | 2026-07-31 | 10.49% | 10.24% | ◄ today – from the quantity table
SL | DESCRIPTION OF ITEM |  |  |  | UNIT | SCOPE QTY | RATE ₹ | WEIGHT-AGE % | START | FINISH | DAYS +/− | PLANNED % | CUM QTY PREV. | QTY TODAY | CUM QTY TO DATE | BALANCE QTY | % COMPL. | EARNED ₹ TODAY | WTD. PLANNED % | WTD. ACTUAL % | STATUS |  | 2026-08-05 | 15.41% |  | from INPUT sheet section 14
1 | Equipment foundation bolts & grouting |  |  |  | NOS | 48 | 3800 | 1.172% | 2026-07-10 | 2026-08-05 | 5 | 81.48% | 22 | 3 | 25 | 23 | 52.08% | 11400 | 0.955% | 0.6104% | Delay | MEC-10 | 2026-08-10 | 20.22% |  | from INPUT sheet section 14
2 | Erection & alignment of process equipment |  |  |  | NOS | 24 | 46000 | 7.094% | 2026-07-20 | 2026-09-10 | 41 | 22.64% | 4 | 1 | 5 | 19 | 20.83% | 46000 | 1.606% | 1.478% | In Progress | MEC-10 | 2026-08-15 | 25.63% |  | from INPUT sheet section 14
3 | Erection of EOT crane 10 T with rails |  |  |  | NOS | 2 | 285000 | 3.663% | 2026-08-20 | 2026-09-15 | 46 | 0% | 0 | 0 | 0 | 2 | 0% | 0 | 0% | 0% | Not Started | MEC-10 | 2026-08-20 | 31.78% |  | from INPUT sheet section 14
4 | Structural platforms, ladders & pipe racks |  |  |  | MT | 22 | 96000 | 13.57% | 2026-07-15 | 2026-08-30 | 30 | 36.17% | 6.5 | 0.8 | 7.3 | 14.7 | 33.18% | 76800 | 4.909% | 4.503% | In Progress | MEC-10 | 2026-08-25 | 38.74% |  | from INPUT sheet section 14
5 | MS ERW piping – 150 NB with fittings |  |  |  | RM | 620 | 2150 | 8.565% | 2026-07-25 | 2026-09-05 | 36 | 16.28% | 96 | 14 | 110 | 510 | 17.74% | 30100 | 1.394% | 1.52% | On Track | MEC-20 | 2026-08-30 | 45.69% |  | from INPUT sheet section 14
6 | MS ERW piping – 100 NB with fittings |  |  |  | RM | 840 | 1480 | 7.988% | 2026-08-01 | 2026-09-20 | 51 | 0% | 0 | 0 | 0 | 840 | 0% | 0 | 0% | 0% | Not Started | MEC-20
7 | SS 304 piping – 50 NB (process lines) |  |  |  | RM | 380 | 2650 | 6.47% | 2026-08-15 | 2026-09-30 | 61 | 0% | 0 | 0 | 0 | 380 | 0% | 0 | 0% | 0% | Not Started | MEC-20
8 | Pipe supports, hangers & spool fabrication |  |  |  | MT | 14 | 92000 | 8.276% | 2026-07-22 | 2026-09-10 | 41 | 19.61% | 3.2 | 0.4 | 3.6 | 10.4 | 25.71% | 36800 | 1.623% | 2.128% | On Track | MEC-20
9 | Compressed air line GI 50 NB |  |  |  | RM | 960 | 860 | 5.305% | 2026-08-10 | 2026-09-25 | 56 | 0% | 0 | 0 | 0 | 960 | 0% | 0 | 0% | 0% | Not Started | MEC-30
10 | Nitrogen / gas line with valves & fittings |  |  |  | RM | 320 | 1450 | 2.981% | 2026-08-20 | 2026-10-05 | 66 | 0% | 0 | 0 | 0 | 320 | 0% | 0 | 0% | 0% | Not Started | MEC-30
11 | HVAC ducting GI 24G with insulation |  |  |  | SQM | 1450 | 1180 | 10.99% | 2026-09-01 | 2026-10-20 | 81 | 0% | 0 | 0 | 0 | 1450 | 0% | 0 | 0% | 0% | Not Started | MEC-40
12 | AHUs, ventilation fans & louvers |  |  |  | NOS | 12 | 165000 | 12.72% | 2026-09-15 | 2026-10-25 | 86 | 0% | 0 | 0 | 0 | 12 | 0% | 0 | 0% | 0% | Not Started | MEC-40
13 | Hydro testing & flushing of piping |  |  |  | RM | 2400 | 180 | 2.776% | 2026-09-10 | 2026-10-30 | 91 | 0% | 0 | 0 | 0 | 2400 | 0% | 0 | 0% | 0% | Not Started | MEC-50
14 | Thermal insulation of hot lines |  |  |  | SQM | 640 | 720 | 2.961% | 2026-09-20 | 2026-11-05 | 97 | 0% | 0 | 0 | 0 | 640 | 0% | 0 | 0% | 0% | Not Started | MEC-50
15 | Pre-commissioning, no-load trial & painting |  |  |  | LS | 1 | 850000 | 5.462% | 2026-10-15 | 2026-11-20 | 112 | 0% | 0 | 0 | 0 | 1 | 0% | 0 | 0% | 0% | Not Started | MEC-50
TOTAL / OVERALL PACKAGE PROGRESS |  |  |  |  | ₹ 155.6 Lakh |  |  | 100% | PROGRAMME |  |  | 10.49% |  |  |  |  | 10.24% | 201100 | 10.49% | 10.24% | BEHIND
3. PROGRESS SUMMARY BY GROUP (value weighted) | [9 empty] | 4. PROGRESS S-CURVE (PLANNED vs ACTUAL)
GROUP |  | DESCRIPTION |  |  | WEIGHTAGE |  | PLANNED % | ACTUAL % | SPI
MEC-10 |  | Equipment Erection, Cranes & Support Structures |  |  | 25.5% |  | 29.29% | 25.85% | 0.88241
MEC-20 |  | Process & Utility Piping |  |  | 31.3% |  | 9.639% | 11.65% | 1.209
MEC-30 |  | Compressed Air & Gas Lines |  |  | 8.286% |  | 0% | 0%
MEC-40 |  | HVAC, Ducting & Ventilation |  |  | 23.72% |  | 0% | 0%
MEC-50 |  | Testing, Insulation & Pre-commissioning |  |  | 11.2% |  | 0% | 0%
TOTAL |  |  |  |  | 100% |  | 10.49% | 10.24% | 0.97638
5. EARNED VALUE / COMMERCIAL SNAPSHOT (₹ in Lakh)
BAC – Contract value of package | [6 empty] | 155.63
PV – Planned Value (BAC × Planned %) | [6 empty] | 16.3205
EV – Earned Value (BAC × Actual %) | [6 empty] | 15.935
AC – Certified / paid to date | [6 empty] | 16.8
SV – Schedule Variance (EV − PV) | [6 empty] | -0.38548
CV – Cost Variance (EV − AC) | [6 empty] | -0.865
CPI ¦ EAC (BAC ÷ CPI) | [6 empty] | 0.95 ¦ ₹ 164.1 L
6. MANPOWER DEPLOYED TODAY | [6 empty] | 7. EQUIPMENT UTILIZATION TODAY | [6 empty] | 8. KEY MATERIAL AT SITE
TRADE / CATEGORY |  |  | PLAN | ACTUAL | MAN-DAYS |  | EQUIPMENT |  |  | QTY | WORKED HRS | IDLE HRS | UTIL. % | MATERIAL |  |  | UNIT | OPENING | RECD. | CONSUMED | BALANCE
Mechanical Fitter |  |  | 12 | 10 | 10.625 |  | Mobile Crane 25 T |  |  | 1 | 5.5 | 2.5 | 68.75% | MS ERW Pipe 150 / 100 NB |  |  | RM | 480 | 120 | 96 | 504
Welder – TIG / 6G certified |  |  | 8 | 6 | 6.375 |  | Hydra 14 T |  |  | 1 | 6 | 2 | 75% | SS 304 Pipe 50 NB |  |  | RM | 0 | 0 | 0 | 0
Rigger |  |  | 6 | 5 | 5.3125 |  | Welding Machine – ARC / TIG |  |  | 6 | 38 | 10 | 79.17% | Pipe fittings, flanges & valves |  |  | NOS | 620 | 80 | 64 | 636
Helper |  |  | 14 | 11 | 11.6875 |  | Pipe Bending & Threading M/C |  |  | 2 | 11 | 5 | 68.75% | Welding consumables E7018 / TIG filler |  |  | KGS | 240 | 40 | 28 | 252
Crane / Machine Operator |  |  | 4 | 3 | 3 |  | Grinding & Cutting Machines |  |  | 8 | 46 | 18 | 71.88% | Structural steel for supports |  |  | MT | 8.5 | 2 | 1.2 | 9.3
Supervisor & PMC Staff |  |  | 5 | 5 | 5.625 |  | Air Compressor & DG Set |  |  | 2 | 13 | 3 | 81.25% | Anchor fasteners & foundation bolts |  |  | NOS | 380 | 0 | 46 | 334
TOTAL WORKERS / MAN-DAYS |  |  | 49 | 40 | 42.625 |  | TOTAL / AVERAGE |  |  | 20 | 119.5 | 40.5 | 74.69% | Balance = Opening + Received − Consumed · carry Balance forward as tomorrow's Opening on the INPUT sheet
9. QUALITY CONTROL & TESTS TODAY | [6 empty] | 10. HSE / SAFETY STATISTICS | [6 empty] | 11. DELAY / IDLE TIME LOG TODAY
Weld visual inspection – joints |  |  |  |  | 38 offered, 35 cleared |  | Safe man-hours – today / cumulative |  |  |  |  | 340 / 9,860 |  | CAUSE (CATEGORY) |  |  |  | FROM | TO | HRS LOST | EOT
Radiography (RT) joints – 10% sample |  |  |  |  | 6 shot, 5 accepted |  | Days without LTI |  |  |  |  | 122 |  | Equipment foundation not released by civil (Client / Vendor) |  |  |  | 9:00 | 12:00 | 3 | Yes
Equipment alignment records signed |  |  |  |  | 4 of 4 equipment |  | Hot work permits issued |  |  |  |  | 4 |  | Crane breakdown – hydraulic hose (Contractor) |  |  |  | 13:30 | 15:00 | 1.5 | No
Welder qualification certificates valid |  |  |  |  | 6 of 8 welders |  | Work at height permits issued |  |  |  |  | 3 |  | Rain – outdoor welding stopped (Weather) |  |  |  | 15:30 | 16:30 | 1 | Review
Grout strength (non-shrink) – 7 day |  |  |  |  | 42 N/mm² – OK |  | Confined space entries today |  |  |  |  | 1 – with gas test | [5 empty] | 0:00 | 0:00 |  | 0
NCRs open / closed today |  |  |  |  | 1 / 1 |  | Safety observations raised / closed |  |  |  |  | 5 / 4 |  | TOTAL HOURS LOST TODAY | [5 empty] | 5.5 | 1 EOT
12. DRAWINGS / RFI / MATERIAL APPROVALS PENDING | [10 empty] | 13. ISSUES & RISKS (open items)
REF. NO. |  | DESCRIPTION | [5 empty] | RAISED ON | AGEING | PENDING WITH | ISSUE / RISK DESCRIPTION | [6 empty] | SEVERITY |  | OWNER
RFI-104 |  | Pipe routing clash with cable tray at Grid B-4 | [5 empty] | 2026-07-25 | 6 | Consultant | ⚠ OEM delivery of 2 process equipment delayed to 20-Aug – blocks erection | [6 empty] | Critical |  | Client
DWG-206 |  | Equipment GA drawing rev-2 – anchor bolt pattern | [5 empty] | 2026-07-21 | 10 | OEM | ⚠ Radiography agency not yet mobilised – RT backlog building | [6 empty] | High |  | Contractor
MAR-062 |  | SS 304 pipe make & MTC approval | [5 empty] | 2026-07-18 | 13 | Client | ⚠ Only 6 of 8 welders hold valid qualification certificates | [6 empty] | High |  | Contractor
RFI-105 |  | Hydro test procedure & pressure approval | [5 empty] | 2026-07-28 | 3 | PMC | ⚠ Insulation material approval pending – affects hot line schedule | [6 empty] | Medium |  | PMC
14. TODAY'S HIGHLIGHTS | [10 empty] | 15. NEXT DAY PLAN
★ Foundation bolts & grouting completed for 25 of 48 locations | [10 empty] | ➜ Continue 150 NB header piping – Grid C to Grid E
★ Equipment No. 4 erected and alignment record signed off | [10 empty] | ➜ Erection of equipment No. 5 subject to OEM delivery
★ 150 NB header piping laid up to Grid C – 110 RM | [10 empty] | ➜ Fabrication of pipe supports for Bay-3
★ Pipe rack structure erected for Bay-1 and Bay-2 | [10 empty] | ➜ Offer 12 welded joints for radiography
16. DECISIONS / INSTRUCTIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
1. OEM to confirm firm delivery dates for the balance 20 process equipment – erection front is idle from 10-Aug
2. Approval of SS 304 pipe make and MTC (MAR-062) – pending 13 days, holds process line procurement
3. Reply to RFI-104 on the pipe routing clash at Grid B-4 – piping and electrical fronts both held
Prepared By |  |  |  |  | Checked By |  |  |  |  | Approved By |  |  |  |  | Client Representative
Name / Sign / Date — Site Engineer – SPDC |  |  |  |  | Name / Sign / Date — QA/QC Engineer – SPDC |  |  |  |  | Name / Sign / Date — Project Manager – SPDC |  |  |  |  | Name / Sign / Date — For and on behalf of Client
Sharnam Project Development Consultants & Co. (SPDC), Vadodara ¦ Project Management Consultancy ¦ THIS SHEET IS ALL FORMULAS — enter data on the INPUT sheet ¦ A3 Landscape – Page 1 of 1

## INPUT
DAILY INPUT SHEET — MECHANICAL WORKS PACKAGE — EQUIPMENT ERECTION, PIPING & HVAC
TYPE ONLY IN THE YELLOW CELLS ON THIS SHEET. The DASHBOARD sheet is the printed DPR — it is all formulas and must not be typed over. Fill top to bottom, then print the DASHBOARD to PDF.
1. PROJECT HEADER (change once at the start, then only the dates each day)
Project name | <Client / Project Name>
Project manager | <PMC Project Manager>
Contractor / vendor | <Executing Agency / PEB Vendor>
Location | <Plot / GIDC / District>
Prepared by | Site Engineer – SPDC (PMC)
Contract / PO reference | <Work Order No. & Date>
Contract completion date | 2026-09-30
Calendar / working hours | 6 Days / Week – 8 hrs |  |  | Shift hours drive man-days & utilization
Shift hours per day | 8 |  |  | Used for man-days and equipment utilization
Weather | Partly Cloudy, 32 °C
REPORT DATE | 2026-07-31
DATA DATE (cut-off) | 2026-07-31 |  |  | Every planned % is measured to this date
Report number | DPR/MEC-027
AC – certified / paid to date (₹ Lakh) | 16.8 |  |  | From the RA bill / cost report
Cumulative man-days upto previous day | 1180
Cumulative safe man-hours upto prev. day | 42150
Date of last LTI | 2026-03-31 |  |  | Days without LTI counts from here
2. QUANTITY PROGRESS (one row per BOQ / scope item — type today's quantity in the last column)
GROUP | DESCRIPTION OF ITEM |  | UNIT | SCOPE / BOQ QTY | RATE ₹ | START | FINISH | CUM QTY UPTO PREV. | QTY TODAY
MEC-10 | Equipment foundation bolts & grouting |  | NOS | 48 | 3800 | 2026-07-10 | 2026-08-05 | 22 | 3
MEC-10 | Erection & alignment of process equipment |  | NOS | 24 | 46000 | 2026-07-20 | 2026-09-10 | 4 | 1
MEC-10 | Erection of EOT crane 10 T with rails |  | NOS | 2 | 285000 | 2026-08-20 | 2026-09-15 | 0 | 0
MEC-10 | Structural platforms, ladders & pipe racks |  | MT | 22 | 96000 | 2026-07-15 | 2026-08-30 | 6.5 | 0.8
MEC-20 | MS ERW piping – 150 NB with fittings |  | RM | 620 | 2150 | 2026-07-25 | 2026-09-05 | 96 | 14
MEC-20 | MS ERW piping – 100 NB with fittings |  | RM | 840 | 1480 | 2026-08-01 | 2026-09-20 | 0 | 0
MEC-20 | SS 304 piping – 50 NB (process lines) |  | RM | 380 | 2650 | 2026-08-15 | 2026-09-30 | 0 | 0
MEC-20 | Pipe supports, hangers & spool fabrication |  | MT | 14 | 92000 | 2026-07-22 | 2026-09-10 | 3.2 | 0.4
MEC-30 | Compressed air line GI 50 NB |  | RM | 960 | 860 | 2026-08-10 | 2026-09-25 | 0 | 0
MEC-30 | Nitrogen / gas line with valves & fittings |  | RM | 320 | 1450 | 2026-08-20 | 2026-10-05 | 0 | 0
MEC-40 | HVAC ducting GI 24G with insulation |  | SQM | 1450 | 1180 | 2026-09-01 | 2026-10-20 | 0 | 0
MEC-40 | AHUs, ventilation fans & louvers |  | NOS | 12 | 165000 | 2026-09-15 | 2026-10-25 | 0 | 0
MEC-50 | Hydro testing & flushing of piping |  | RM | 2400 | 180 | 2026-09-10 | 2026-10-30 | 0 | 0
MEC-50 | Thermal insulation of hot lines |  | SQM | 640 | 720 | 2026-09-20 | 2026-11-05 | 0 | 0
MEC-50 | Pre-commissioning, no-load trial & painting |  | LS | 1 | 850000 | 2026-10-15 | 2026-11-20 | 0 | 0
3. MANPOWER DEPLOYED TODAY
TRADE / CATEGORY |  | PLANNED NOS | ACTUAL NOS | HOURS WORKED
Mechanical Fitter |  | 12 | 10 | 8.5
Welder – TIG / 6G certified |  | 8 | 6 | 8.5
Rigger |  | 6 | 5 | 8.5
Helper |  | 14 | 11 | 8.5
Crane / Machine Operator |  | 4 | 3 | 8
Supervisor & PMC Staff |  | 5 | 5 | 9
4. EQUIPMENT DEPLOYED TODAY
EQUIPMENT |  | QTY | WORKED HRS | IDLE HRS
Mobile Crane 25 T |  | 1 | 5.5 | 2.5
Hydra 14 T |  | 1 | 6 | 2
Welding Machine – ARC / TIG |  | 6 | 38 | 10
Pipe Bending & Threading M/C |  | 2 | 11 | 5
Grinding & Cutting Machines |  | 8 | 46 | 18
Air Compressor & DG Set |  | 2 | 13 | 3
5. MATERIAL AT SITE
MATERIAL |  | UNIT | OPENING STOCK | RECEIVED TODAY | CONSUMED / ISSUED
MS ERW Pipe 150 / 100 NB |  | RM | 480 | 120 | 96
SS 304 Pipe 50 NB |  | RM | 0 | 0 | 0
Pipe fittings, flanges & valves |  | NOS | 620 | 80 | 64
Welding consumables E7018 / TIG filler |  | KGS | 240 | 40 | 28
Structural steel for supports |  | MT | 8.5 | 2 | 1.2
Anchor fasteners & foundation bolts |  | NOS | 380 | 0 | 46
6. QUALITY CONTROL & TESTS TODAY
QUALITY / TEST PARAMETER |  | TODAY'S FIGURE
Weld visual inspection – joints |  | 38 offered, 35 cleared
Radiography (RT) joints – 10% sample |  | 6 shot, 5 accepted
Equipment alignment records signed |  | 4 of 4 equipment
Welder qualification certificates valid |  | 6 of 8 welders
Grout strength (non-shrink) – 7 day |  | 42 N/mm² – OK
NCRs open / closed today |  | 1 / 1
7. HSE / SAFETY STATISTICS
HSE PARAMETER |  | TODAY'S FIGURE
Safe man-hours – today / cumulative |  | 340 / 9,860
Days without LTI |  | 122
Hot work permits issued |  | 4
Work at height permits issued |  | 3
Confined space entries today |  | 1 – with gas test
Safety observations raised / closed |  | 5 / 4
8. DELAY / IDLE TIME LOG TODAY (enter clock times — hours are calculated)
CAUSE OF DELAY / IDLE TIME |  | CATEGORY | FROM | TO | EOT
Equipment foundation not released by civil |  | Client / Vendor | 9:00 | 12:00 | Yes
Crane breakdown – hydraulic hose |  | Contractor | 13:30 | 15:00 | No
Rain – outdoor welding stopped |  | Weather | 15:30 | 16:30 | Review
9. DRAWINGS / RFI / MATERIAL APPROVALS PENDING (ageing is calculated)
REF. NO. | DESCRIPTION |  | RAISED ON | PENDING WITH
RFI-104 | Pipe routing clash with cable tray at Grid B-4 |  | 2026-07-25 | Consultant
DWG-206 | Equipment GA drawing rev-2 – anchor bolt pattern |  | 2026-07-21 | OEM
MAR-062 | SS 304 pipe make & MTC approval |  | 2026-07-18 | Client
RFI-105 | Hydro test procedure & pressure approval |  | 2026-07-28 | PMC
10. ISSUES & RISKS (open items)
ISSUE / RISK DESCRIPTION |  |  | SEVERITY | OWNER
OEM delivery of 2 process equipment delayed to 20-Aug – blocks erection |  |  | Critical | Client
Radiography agency not yet mobilised – RT backlog building |  |  | High | Contractor
Only 6 of 8 welders hold valid qualification certificates |  |  | High | Contractor
Insulation material approval pending – affects hot line schedule |  |  | Medium | PMC
11. TODAY'S HIGHLIGHTS
Foundation bolts & grouting completed for 25 of 48 locations
Equipment No. 4 erected and alignment record signed off
150 NB header piping laid up to Grid C – 110 RM
Pipe rack structure erected for Bay-1 and Bay-2
12. NEXT DAY PLAN
Continue 150 NB header piping – Grid C to Grid E
Erection of equipment No. 5 subject to OEM delivery
Fabrication of pipe supports for Bay-3
Offer 12 welded joints for radiography
13. DECISIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
OEM to confirm firm delivery dates for the balance 20 process equipment – erection front is idle from 10-Aug
Approval of SS 304 pipe make and MTC (MAR-062) – pending 13 days, holds process line procurement
Reply to RFI-104 on the pipe routing clash at Grid B-4 – piping and electrical fronts both held
14. S-CURVE ACTUAL HISTORY (enter once per reporting period — today's point is automatic)
DATE | ACTUAL CUM % ON THAT DATE | NOTE
2026-07-01 | 0% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-06 | 0.9976% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-11 | 2.801% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-16 | 4.799% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-21 | 7.198% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-26 | 9.197% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-31 | ◄ calculated on the DASHBOARD | TODAY — taken from the quantity table, do not type
2026-08-05 |  | leave blank until that date is reported
2026-08-10 |  | leave blank until that date is reported
2026-08-15 |  | leave blank until that date is reported
2026-08-20 |  | leave blank until that date is reported
2026-08-25 |  | leave blank until that date is reported
2026-08-30 |  | leave blank until that date is reported

## S-Curve Calc
S-CURVE CALCULATION — ACTUAL % ON EACH REPORTING DATE (MECHANICAL)
Enter the CUMULATIVE quantity of each item as it stood on each reporting date (from that day's measurement book / issued DPR). The bottom row converts them into the weighted actual % for that date and feeds INPUT section 14 and the S-curve. Once a column is filled it never changes again.
SL | DESCRIPTION OF ITEM | UNIT | SCOPE QTY | WEIGHT-AGE % | 2026-07-01 | 2026-07-06 | 2026-07-11 | 2026-07-16 | 2026-07-21 | 2026-07-26 | 2026-07-31 | 2026-08-05 | 2026-08-10 | 2026-08-15 | 2026-08-20 | 2026-08-25 | 2026-08-30
1 | Equipment foundation bolts & grouting | NOS | 48 | 1.172% | 2026-07-01: 0; 2026-07-06: 2.44; 2026-07-11: 6.84; 2026-07-16: 11.72; 2026-07-21: 17.58; 2026-07-26: 22.46
2 | Erection & alignment of process equipment | NOS | 24 | 7.094% | 2026-07-01: 0; 2026-07-06: 0.49; 2026-07-11: 1.37; 2026-07-16: 2.34; 2026-07-21: 3.52; 2026-07-26: 4.49
3 | Erection of EOT crane 10 T with rails | NOS | 2 | 3.663% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
4 | Structural platforms, ladders & pipe racks | MT | 22 | 13.57% | 2026-07-01: 0; 2026-07-06: 0.71; 2026-07-11: 2; 2026-07-16: 3.42; 2026-07-21: 5.13; 2026-07-26: 6.56
5 | MS ERW piping – 150 NB with fittings | RM | 620 | 8.565% | 2026-07-01: 0; 2026-07-06: 10.74; 2026-07-11: 30.08; 2026-07-16: 51.57; 2026-07-21: 77.35; 2026-07-26: 98.84
6 | MS ERW piping – 100 NB with fittings | RM | 840 | 7.988% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
7 | SS 304 piping – 50 NB (process lines) | RM | 380 | 6.47% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
8 | Pipe supports, hangers & spool fabrication | MT | 14 | 8.276% | 2026-07-01: 0; 2026-07-06: 0.35; 2026-07-11: 0.98; 2026-07-16: 1.69; 2026-07-21: 2.53; 2026-07-26: 3.23
9 | Compressed air line GI 50 NB | RM | 960 | 5.305% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
10 | Nitrogen / gas line with valves & fittings | RM | 320 | 2.981% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
11 | HVAC ducting GI 24G with insulation | SQM | 1450 | 10.99% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
12 | AHUs, ventilation fans & louvers | NOS | 12 | 12.72% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
13 | Hydro testing & flushing of piping | RM | 2400 | 2.776% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
14 | Thermal insulation of hot lines | SQM | 640 | 2.961% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
15 | Pre-commissioning, no-load trial & painting | LS | 1 | 5.462% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
WEIGHTED ACTUAL % ON THAT DATE |  |  |  | 100% | 0% | 0.9976% | 2.801% | 4.799% | 7.198% | 9.197% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
FORMULA: Actual % on a date = Σ [ item weightage × ( cumulative qty on that date ÷ scope qty ) ] — the same weighted calculation the DASHBOARD does for today, only using the quantities as they stood on that earlier date.
SHORTCUT: if the DPR was already issued on that date, simply type the Actual % printed on it over the green formula in INPUT section 14 — both routes give the same figure. NOTE: weightage is taken from the CURRENT rates, so if a rate is revised later, re-issued history will shift slightly; the figures on the DPRs already signed remain the record.

## Guide
HOW THIS FILE WORKS — MECHANICAL DPR
| Two sheets only | INPUT — you type here, top to bottom, yellow cells only. DASHBOARD — the printed DPR, 100% formulas, never typed. Guide — this page.
| Daily routine | Open INPUT → change Report Date and Data Date → enter today's quantities, manpower, equipment, material, quality, HSE, delays, pending approvals, issues, highlights, next-day plan → open DASHBOARD → print to PDF.
| Adding / removing an item | Insert or delete a row inside the quantity block on INPUT and the same row position on DASHBOARD; every formula uses ranges, so totals follow.
| Weightage % | Scope Qty × Rate ÷ Σ(Scope Qty × Rate). Value weightage — always totals 100%.
| Planned % | IF(Data Date ≥ Finish, 100%, IF(Data Date < Start, 0%, (Data Date − Start + 1) ÷ (Finish − Start + 1))) — the programme prorated to the cut-off date.
| Days +/− | Finish − Data Date. Negative and red means the item is already past its programmed finish.
| Cum Qty To Date / Balance | Cum upto previous + Qty today · Scope Qty − Cum to date.
| % Complete | MIN(Cum Qty To Date ÷ Scope Qty, 1), shown with an in-cell data bar.
| Earned ₹ today | Qty today × Rate — the value of work done in the day, totalled in the KPI strip.
| Package Planned / Actual % | Σ(Weightage × Planned %) and Σ(Weightage × % Complete). These two totals drive the KPI strip, group summary, earned value block and S-curve.
| Status | Not Started / Completed / On Track (actual ≥ planned) / In Progress / Delay — colour coded.
| Group summary | SUMIFS of the weighted columns by group code ÷ that group's weightage.
| Earned value | BAC = Σ(Qty × Rate) ÷ 1,00,000 · PV = BAC × Planned % · EV = BAC × Actual % · SV = EV − PV · CV = EV − AC · CPI = EV ÷ AC · EAC = BAC ÷ CPI. Only AC is typed.
| Section 6 / 7 / 8 | Man-days = Actual Nos × hours ÷ shift hours · Utilization = Worked ÷ (Qty × shift hours) · Balance stock = Opening + Received − Consumed.
| Hours lost | (To − From) × 24 from the clock times on INPUT. EOT count is a COUNTIF of the Yes entries.
| Approval ageing | Data Date − Raised on; red beyond 7 days, and counted in the Project Health box.
| S-curve actual history | Actual % on any past date = Σ [ item weightage × (cumulative qty on that date ÷ scope qty) ]. The S-CURVE CALC sheet does this for you — enter each item's cumulative quantity as it stood on each reporting date and the bottom row gives the %, which flows into INPUT section 14. If that day's DPR was already issued, just type the Actual % from it instead.
| S-curve | Planned line = SUMPRODUCT of every item's weightage × its time-prorated fraction at each date — built entirely from the programme. Actual history comes from INPUT section 14; today's point is taken live from the quantity table.
| Paper | DASHBOARD is set to A3 landscape, fit to one page. Prints on A4 at about 70% if needed.
| Roll over to the next day | Save a copy with the new date. On INPUT: move Cum Qty To Date into 'Cum qty upto prev.', move material Balance into Opening, clear Qty Today, update the cumulative man-days and man-hours.