## DASHBOARD
SPDC |  |  | DAILY PROGRESS REPORT | [10 empty] | Report Date |  |  | 2026-07-31
[14 empty] | Data Date |  |  | 2026-07-31
|  |  | PEB – ERECTION PACKAGE (SITE SCOPE) | [10 empty] | Report No. / Day |  |  | DPR/PEB-E-027 ¦ Friday | [5 empty] | S-CURVE DATA (not printed)
Project Name |  | <Client / Project Name> | [5 empty] | Contract / PO Ref. |  | <Work Order No. & Date> |  |  |  | PROJECT HEALTH | [8 empty] | DATE | PLANNED CUM % | ACTUAL CUM % | NOTE
Project Manager |  | <PMC Project Manager> | [5 empty] | Contract Completion |  | 2026-09-30 |  |  |  | Overall Status |  |  |  | BEHIND PROGRAMME |  |  |  |  | 2026-07-01 | 0.9636% | 0.4989% | from INPUT sheet section 14
Contractor / Vendor |  | <Executing Agency / PEB Vendor> | [5 empty] | Calendar / Weather |  | 6 Days / Week – 8 hrs ¦ Partly Cloudy, 32 °C |  |  |  | Critical / High issues open |  |  |  | 3 |  |  |  |  | 2026-07-06 | 6.103% | 4.499% | from INPUT sheet section 14
Location |  | <Plot / GIDC / District> | [5 empty] | Contract Value (₹ Lakh) |  | 79.7 |  |  |  | Approvals pending > 7 days |  |  |  | 2 |  |  |  |  | 2026-07-11 | 13.92% | 10.5% | from INPUT sheet section 14
1. KEY PERFORMANCE INDICATORS (all calculated — nothing is typed on this sheet) | [22 empty] | 2026-07-16 | 21.01% | 16% | from INPUT sheet section 14
PLANNED % |  |  | ACTUAL % |  |  | VARIANCE |  |  | SPI |  |  | EARNED VALUE ₹ L |  |  | VALUE DONE TODAY ₹ |  |  | ITEMS DELAYED |  | HRS LOST TODAY |  |  | 2026-07-21 | 30.02% | 23% | from INPUT sheet section 14
51.36% |  |  | 47.55% |  |  | -3.811% |  |  | 0.9258 |  |  | 37.8954 |  |  | 221640 |  |  | 3 |  | 4.75 |  |  | 2026-07-26 | 39.75% | 30.5% | from INPUT sheet section 14
2. QUANTITY / PHYSICAL PROGRESS — ERECTION ITEM-WISE (basis of the % complete above) | [22 empty] | 2026-07-31 | 51.36% | 47.55% | ◄ today – from the quantity table
SL | DESCRIPTION OF ITEM |  |  |  | UNIT | SCOPE QTY | RATE ₹ | WEIGHT-AGE % | START | FINISH | DAYS +/− | PLANNED % | CUM QTY PREV. | QTY TODAY | CUM QTY TO DATE | BALANCE QTY | % COMPL. | EARNED ₹ TODAY | WTD. PLANNED % | WTD. ACTUAL % | STATUS |  | 2026-08-05 | 61.74% |  | from INPUT sheet section 14
1 | Anchor bolt template setting & survey |  |  |  | NOS | 224 | 900 | 2.529% | 2026-07-01 | 2026-07-09 | -22 | 100% | 208 | 8 | 216 | 8 | 96.43% | 7200 | 2.529% | 2.439% | In Progress | ERC-10 | 2026-08-10 | 68.51% |  | from INPUT sheet section 14
2 | Base plate placing, packing & grouting |  |  |  | NOS | 56 | 3200 | 2.248% | 2026-07-04 | 2026-07-24 | -7 | 100% | 44 | 3 | 47 | 9 | 83.93% | 9600 | 2.248% | 1.887% | In Progress | ERC-10 | 2026-08-15 | 73.7% |  | from INPUT sheet section 14
3 | Erection of columns – Bay 1 to 4 |  |  |  | MT | 64 | 8500 | 6.826% | 2026-07-01 | 2026-07-10 | -21 | 100% | 64 | 0 | 64 | 0 | 100% | 0 | 6.826% | 6.826% | Completed | ERC-20 | 2026-08-20 | 77.3% |  | from INPUT sheet section 14
4 | Erection of columns – Bay 5 to 8 |  |  |  | MT | 64 | 8500 | 6.826% | 2026-07-10 | 2026-07-21 | -10 | 100% | 61 | 3 | 64 | 0 | 100% | 25500 | 6.826% | 6.826% | Completed | ERC-20 | 2026-08-25 | 80.15% |  | from INPUT sheet section 14
5 | Main rafter erection – Bay 1 to 4 |  |  |  | MT | 78 | 9200 | 9.004% | 2026-07-08 | 2026-07-21 | -10 | 100% | 78 | 0 | 78 | 0 | 100% | 0 | 9.004% | 9.004% | Completed | ERC-20 | 2026-08-30 | 82.99% |  | from INPUT sheet section 14
6 | Main rafter erection – Bay 5 to 8 |  |  |  | MT | 78 | 9200 | 9.004% | 2026-07-20 | 2026-08-03 | 3 | 80% | 46 | 6 | 52 | 26 | 66.67% | 55200 | 7.203% | 6.003% | In Progress | ERC-20
7 | Crane gantry girder erection |  |  |  | MT | 48 | 9800 | 5.902% | 2026-07-26 | 2026-08-11 | 11 | 35.29% | 12 | 2 | 14 | 34 | 29.17% | 19600 | 2.083% | 1.721% | In Progress | ERC-20
8 | Secondary members – Bay 1 to 4 |  |  |  | MT | 31 | 8800 | 3.423% | 2026-07-15 | 2026-07-28 | -3 | 100% | 27 | 2 | 29 | 2 | 93.55% | 17600 | 3.423% | 3.202% | In Progress | ERC-30
9 | Secondary members – Bay 5 to 8 |  |  |  | MT | 31 | 8800 | 3.423% | 2026-07-29 | 2026-08-12 | 12 | 20% | 3 | 1 | 4 | 27 | 12.9% | 8800 | 0.6846% | 0.4417% | Delay | ERC-30
10 | Purlin & girt installation |  |  |  | MT | 84 | 9400 | 9.907% | 2026-07-22 | 2026-08-07 | 7 | 58.82% | 33 | 4 | 37 | 47 | 44.05% | 37600 | 5.828% | 4.364% | Delay | ERC-30
11 | Bracing, sag rods & tie rods |  |  |  | MT | 26 | 9600 | 3.132% | 2026-07-24 | 2026-08-07 | 7 | 53.33% | 12 | 1.5 | 13.5 | 12.5 | 51.92% | 14400 | 1.67% | 1.626% | In Progress | ERC-30
12 | HSFG bolting & torqueing |  |  |  | NOS | 8600 | 38 | 4.1% | 2026-07-25 | 2026-08-20 | 20 | 25.93% | 3100 | 380 | 3480 | 5120 | 40.47% | 14440 | 1.063% | 1.659% | On Track | ERC-40
13 | Site welding, NDT & touch-up painting |  |  |  | RM | 1450 | 260 | 4.73% | 2026-07-22 | 2026-08-14 | 14 | 41.67% | 430 | 45 | 475 | 975 | 32.76% | 11700 | 1.971% | 1.55% | Delay | ERC-40
14 | Roof sheeting 0.5 mm PPGL |  |  |  | SQM | 7200 | 195 | 17.62% | 2026-08-10 | 2026-09-09 | 40 | 0% | 0 | 0 | 0 | 7200 | 0% | 0 | 0% | 0% | Not Started | ERC-50
15 | Wall cladding, liner & accessories |  |  |  | SQM | 4300 | 210 | 11.33% | 2026-09-01 | 2026-09-24 | 55 | 0% | 0 | 0 | 0 | 4300 | 0% | 0 | 0% | 0% | Not Started | ERC-50
TOTAL / OVERALL PACKAGE PROGRESS |  |  |  |  | ₹ 79.7 Lakh |  |  | 100% | PROGRAMME |  |  | 51.36% |  |  |  |  | 47.55% | 221640 | 51.36% | 47.55% | BEHIND
3. PROGRESS SUMMARY BY GROUP (value weighted) | [9 empty] | 4. PROGRESS S-CURVE (PLANNED vs ACTUAL)
GROUP |  | DESCRIPTION |  |  | WEIGHTAGE |  | PLANNED % | ACTUAL % | SPI
ERC-10 |  | Anchorage – Templates, Base Plates, Grouting |  |  | 4.778% |  | 100% | 90.55% | 0.90546
ERC-20 |  | Primary Steel – Columns, Rafters, Gantry |  |  | 37.56% |  | 85.04% | 80.88% | 0.95109
ERC-30 |  | Secondary Steel – Purlins, Girts, Bracing |  |  | 19.88% |  | 58.36% | 48.45% | 0.8301
ERC-40 |  | Connections – Bolting, Welding, Alignment |  |  | 8.831% |  | 34.36% | 36.34% | 1.0576
ERC-50 |  | Cladding – Roof, Wall, Accessories |  |  | 28.95% |  | 0% | 0%
TOTAL |  |  |  |  | 100% |  | 51.36% | 47.55% | 0.9258
5. EARNED VALUE / COMMERCIAL SNAPSHOT (₹ in Lakh)
BAC – Contract value of package | [6 empty] | 79.7
PV – Planned Value (BAC × Planned %) | [6 empty] | 40.9326
EV – Earned Value (BAC × Actual %) | [6 empty] | 37.8954
AC – Certified / paid to date | [6 empty] | 39.8
SV – Schedule Variance (EV − PV) | [6 empty] | -3.0372
CV – Cost Variance (EV − AC) | [6 empty] | -1.9046
CPI ¦ EAC (BAC ÷ CPI) | [6 empty] | 0.95 ¦ ₹ 83.7 L
6. MANPOWER DEPLOYED TODAY | [6 empty] | 7. EQUIPMENT UTILIZATION TODAY | [6 empty] | 8. MATERIAL ISSUED / AT SITE
TRADE / CATEGORY |  |  | PLAN | ACTUAL | MAN-DAYS |  | EQUIPMENT |  |  | QTY | WORKED HRS | IDLE HRS | UTIL. % | MATERIAL |  |  | UNIT | OPENING | RECD. | CONSUMED | BALANCE
Rigger |  |  | 8 | 6 | 6.375 |  | Mobile Crane 50 T |  |  | 1 | 6.5 | 1.5 | 81.25% | Purlins & girts |  |  | MT | 44 | 7 | 7 | 44
Fitter |  |  | 12 | 10 | 10.625 |  | Mobile Crane 25 T |  |  | 1 | 6 | 2 | 75% | Bracing rods & sag rods |  |  | MT | 9.5 | 1.5 | 1.5 | 9.5
Welder – 6G certified |  |  | 8 | 6 | 6.375 |  | Telehandler 4 T |  |  | 1 | 6 | 2 | 75% | HSFG & ordinary bolts |  |  | KGS | 480 | 180 | 165 | 495
Bolter / Torque gang |  |  | 8 | 6 | 6.375 |  | Boom Lift 28 m |  |  | 2 | 12.4 | 3.6 | 77.5% | Connection plates & cleats |  |  | KGS | 395 | 20 | 35 | 380
Helper |  |  | 14 | 12 | 12.75 |  | Welding Machine 400 A |  |  | 6 | 43.2 | 4.8 | 90% | Welding electrodes E7018 |  |  | KGS | 90 | 15 | 5 | 100
Operators, Supervisor & PMC |  |  | 11 | 10 | 11.25 |  | Torque Wrench & Chain Blocks |  |  | 10 | 46 | 34 | 57.5% | Zinc rich primer & paint |  |  | LTR | 60 | 0 | 6 | 54
TOTAL WORKERS / MAN-DAYS |  |  | 61 | 50 | 53.75 |  | TOTAL / AVERAGE |  |  | 21 | 120.1 | 47.9 | 71.49% | Balance = Opening + Received − Consumed · carry Balance forward as tomorrow's Opening on the INPUT sheet
9. QUALITY CONTROL & TESTS TODAY | [6 empty] | 10. HSE / SAFETY STATISTICS | [6 empty] | 11. DELAY / IDLE TIME LOG TODAY
Erection checklists offered / approved |  |  |  |  | 7 / 6 |  | Safe man-hours – today / cumulative |  |  |  |  | 430 / 43,180 |  | CAUSE (CATEGORY) |  |  |  | FROM | TO | HRS LOST | EOT
Bolt torque tests – 10% sample |  |  |  |  | 6 / 6 pass |  | Days without LTI |  |  |  |  | 122 |  | Wind above 35 kmph – lifting stopped (Weather) |  |  |  | 15:00 | 16:15 | 1.25 | Review
Weld visual / DPT inspections |  |  |  |  | 42 / 8 |  | Work at height permits issued |  |  |  |  | 6 |  | Bay-7 connection plates not received (Client / Vendor) |  |  |  | 10:30 | 13:00 | 2.5 | Yes
Plumb & alignment survey – bays |  |  |  |  | Bay 1-4 accepted |  | Harness / lifeline checks done |  |  |  |  | All gangs |  | 4 riggers absent against deployment plan (Contractor) |  |  |  | 8:00 | 9:00 | 1 | No
NCRs open / closed today |  |  |  |  | 2 / 1 |  | Safety observations raised / closed |  |  |  |  | 6 / 5 | [5 empty] | 0:00 | 0:00 |  | 0
DFT readings on touch-up paint |  |  |  |  | 20 taken, 18 accepted |  | Crane third party cert. validity |  |  |  |  | 12-Nov-26 |  | TOTAL HOURS LOST TODAY | [5 empty] | 4.75 | 1 EOT
12. DRAWINGS / RFI / MATERIAL APPROVALS PENDING | [10 empty] | 13. ISSUES & RISKS (open items)
REF. NO. |  | DESCRIPTION | [5 empty] | RAISED ON | AGEING | PENDING WITH | ISSUE / RISK DESCRIPTION | [6 empty] | SEVERITY |  | OWNER
RFI-088 |  | Gantry girder stopper detail at Bay-8 | [5 empty] | 2026-07-27 | 4 | PEB Vendor | ⚠ Bay-7 connection plates not supplied – erection critical path held | [6 empty] | Critical |  | Vendor
DWG-142 |  | Roof sheeting layout rev-3 with skylight | [5 empty] | 2026-07-20 | 11 | PEB Vendor | ⚠ Rigger gang short by 4 nos. against deployment plan | [6 empty] | High |  | Contractor
MAR-051 |  | Insulation – 50 mm glass wool sample | [5 empty] | 2026-07-16 | 15 | Client | ⚠ Sheeting sub-contractor not yet mobilised | [6 empty] | High |  | Contractor
RFI-089 |  | Bracing connection at expansion joint | [5 empty] | 2026-07-29 | 2 | PEB Vendor | ⚠ Afternoon wind stoppages averaging 1.2 hrs/day | [6 empty] | Medium |  | PMC
14. TODAY'S HIGHLIGHTS | [10 empty] | 15. NEXT DAY PLAN
★ Column erection completed for all 8 bays – 28 nos. | [10 empty] | ➜ Main rafter erection – Bay 7 (subject to plate delivery)
★ Main rafter erection completed up to Bay-6 | [10 empty] | ➜ Secondary members & bracing in Bay-5 and Bay-6
★ Torque test on 10% sample bolts of Bay-3 – satisfactory | [10 empty] | ➜ HSFG torqueing and torque marking of Bay-4
★ Plumb & alignment survey of Bay 1 to 4 accepted | [10 empty] | ➜ Mobilisation of sheeting sub-contractor gang
16. DECISIONS / INSTRUCTIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
1. Expedite Bay-7 connection plates from the PEB vendor – required by 01-Aug-26 to protect the critical path
2. Confirmation of gantry stopper detail (RFI-088) – gantry erection held pending reply
3. Approval of insulation sample (MAR-051) – required before the sheeting gang is mobilised
Prepared By |  |  |  |  | Checked By |  |  |  |  | Approved By |  |  |  |  | Client Representative
Name / Sign / Date — Site Engineer – SPDC |  |  |  |  | Name / Sign / Date — QA/QC Engineer – SPDC |  |  |  |  | Name / Sign / Date — Project Manager – SPDC |  |  |  |  | Name / Sign / Date — For and on behalf of Client
Sharnam Project Development Consultants & Co. (SPDC), Vadodara ¦ Project Management Consultancy ¦ THIS SHEET IS ALL FORMULAS — enter data on the INPUT sheet ¦ A3 Landscape – Page 1 of 1

## INPUT
DAILY INPUT SHEET — PEB – ERECTION PACKAGE (SITE SCOPE)
TYPE ONLY IN THE YELLOW CELLS ON THIS SHEET. The DASHBOARD sheet is the printed DPR — it is all formulas and must not be typed over. Fill top to bottom, then print the DASHBOARD to PDF.
1. PROJECT HEADER (change once at the start, then only the dates each day)
Project name | <Client / Project Name>
Project manager | <PMC Project Manager>
Contractor / vendor | <Executing Agency / PEB Vendor>
Location | <Plot / GIDC / District>
Prepared by | Site Engineer – SPDC (PMC)
Contract / PO reference | <Work Order No. & Date>
Contract completion date | 2026-09-30
Calendar / working hours | 6 Days / Week – 8 hrs |  |  | Shift hours drive man-days & utilization
Shift hours per day | 8 |  |  | Used for man-days and equipment utilization
Weather | Partly Cloudy, 32 °C
REPORT DATE | 2026-07-31
DATA DATE (cut-off) | 2026-07-31 |  |  | Every planned % is measured to this date
Report number | DPR/PEB-E-027
AC – certified / paid to date (₹ Lakh) | 39.8 |  |  | From the RA bill / cost report
Cumulative man-days upto previous day | 1180
Cumulative safe man-hours upto prev. day | 42150
Date of last LTI | 2026-03-31 |  |  | Days without LTI counts from here
2. QUANTITY PROGRESS (one row per BOQ / scope item — type today's quantity in the last column)
GROUP | DESCRIPTION OF ITEM |  | UNIT | SCOPE / BOQ QTY | RATE ₹ | START | FINISH | CUM QTY UPTO PREV. | QTY TODAY
ERC-10 | Anchor bolt template setting & survey |  | NOS | 224 | 900 | 2026-07-01 | 2026-07-09 | 208 | 8
ERC-10 | Base plate placing, packing & grouting |  | NOS | 56 | 3200 | 2026-07-04 | 2026-07-24 | 44 | 3
ERC-20 | Erection of columns – Bay 1 to 4 |  | MT | 64 | 8500 | 2026-07-01 | 2026-07-10 | 64 | 0
ERC-20 | Erection of columns – Bay 5 to 8 |  | MT | 64 | 8500 | 2026-07-10 | 2026-07-21 | 61 | 3
ERC-20 | Main rafter erection – Bay 1 to 4 |  | MT | 78 | 9200 | 2026-07-08 | 2026-07-21 | 78 | 0
ERC-20 | Main rafter erection – Bay 5 to 8 |  | MT | 78 | 9200 | 2026-07-20 | 2026-08-03 | 46 | 6
ERC-20 | Crane gantry girder erection |  | MT | 48 | 9800 | 2026-07-26 | 2026-08-11 | 12 | 2
ERC-30 | Secondary members – Bay 1 to 4 |  | MT | 31 | 8800 | 2026-07-15 | 2026-07-28 | 27 | 2
ERC-30 | Secondary members – Bay 5 to 8 |  | MT | 31 | 8800 | 2026-07-29 | 2026-08-12 | 3 | 1
ERC-30 | Purlin & girt installation |  | MT | 84 | 9400 | 2026-07-22 | 2026-08-07 | 33 | 4
ERC-30 | Bracing, sag rods & tie rods |  | MT | 26 | 9600 | 2026-07-24 | 2026-08-07 | 12 | 1.5
ERC-40 | HSFG bolting & torqueing |  | NOS | 8600 | 38 | 2026-07-25 | 2026-08-20 | 3100 | 380
ERC-40 | Site welding, NDT & touch-up painting |  | RM | 1450 | 260 | 2026-07-22 | 2026-08-14 | 430 | 45
ERC-50 | Roof sheeting 0.5 mm PPGL |  | SQM | 7200 | 195 | 2026-08-10 | 2026-09-09 | 0 | 0
ERC-50 | Wall cladding, liner & accessories |  | SQM | 4300 | 210 | 2026-09-01 | 2026-09-24 | 0 | 0
3. MANPOWER DEPLOYED TODAY
TRADE / CATEGORY |  | PLANNED NOS | ACTUAL NOS | HOURS WORKED
Rigger |  | 8 | 6 | 8.5
Fitter |  | 12 | 10 | 8.5
Welder – 6G certified |  | 8 | 6 | 8.5
Bolter / Torque gang |  | 8 | 6 | 8.5
Helper |  | 14 | 12 | 8.5
Operators, Supervisor & PMC |  | 11 | 10 | 9
4. EQUIPMENT DEPLOYED TODAY
EQUIPMENT |  | QTY | WORKED HRS | IDLE HRS
Mobile Crane 50 T |  | 1 | 6.5 | 1.5
Mobile Crane 25 T |  | 1 | 6 | 2
Telehandler 4 T |  | 1 | 6 | 2
Boom Lift 28 m |  | 2 | 12.4 | 3.6
Welding Machine 400 A |  | 6 | 43.2 | 4.8
Torque Wrench & Chain Blocks |  | 10 | 46 | 34
5. MATERIAL AT SITE
MATERIAL |  | UNIT | OPENING STOCK | RECEIVED TODAY | CONSUMED / ISSUED
Purlins & girts |  | MT | 44 | 7 | 7
Bracing rods & sag rods |  | MT | 9.5 | 1.5 | 1.5
HSFG & ordinary bolts |  | KGS | 480 | 180 | 165
Connection plates & cleats |  | KGS | 395 | 20 | 35
Welding electrodes E7018 |  | KGS | 90 | 15 | 5
Zinc rich primer & paint |  | LTR | 60 | 0 | 6
6. QUALITY CONTROL & TESTS TODAY
QUALITY / TEST PARAMETER |  | TODAY'S FIGURE
Erection checklists offered / approved |  | 7 / 6
Bolt torque tests – 10% sample |  | 6 / 6 pass
Weld visual / DPT inspections |  | 42 / 8
Plumb & alignment survey – bays |  | Bay 1-4 accepted
NCRs open / closed today |  | 2 / 1
DFT readings on touch-up paint |  | 20 taken, 18 accepted
7. HSE / SAFETY STATISTICS
HSE PARAMETER |  | TODAY'S FIGURE
Safe man-hours – today / cumulative |  | 430 / 43,180
Days without LTI |  | 122
Work at height permits issued |  | 6
Harness / lifeline checks done |  | All gangs
Safety observations raised / closed |  | 6 / 5
Crane third party cert. validity |  | 12-Nov-26
8. DELAY / IDLE TIME LOG TODAY (enter clock times — hours are calculated)
CAUSE OF DELAY / IDLE TIME |  | CATEGORY | FROM | TO | EOT
Wind above 35 kmph – lifting stopped |  | Weather | 15:00 | 16:15 | Review
Bay-7 connection plates not received |  | Client / Vendor | 10:30 | 13:00 | Yes
4 riggers absent against deployment plan |  | Contractor | 8:00 | 9:00 | No
9. DRAWINGS / RFI / MATERIAL APPROVALS PENDING (ageing is calculated)
REF. NO. | DESCRIPTION |  | RAISED ON | PENDING WITH
RFI-088 | Gantry girder stopper detail at Bay-8 |  | 2026-07-27 | PEB Vendor
DWG-142 | Roof sheeting layout rev-3 with skylight |  | 2026-07-20 | PEB Vendor
MAR-051 | Insulation – 50 mm glass wool sample |  | 2026-07-16 | Client
RFI-089 | Bracing connection at expansion joint |  | 2026-07-29 | PEB Vendor
10. ISSUES & RISKS (open items)
ISSUE / RISK DESCRIPTION |  |  | SEVERITY | OWNER
Bay-7 connection plates not supplied – erection critical path held |  |  | Critical | Vendor
Rigger gang short by 4 nos. against deployment plan |  |  | High | Contractor
Sheeting sub-contractor not yet mobilised |  |  | High | Contractor
Afternoon wind stoppages averaging 1.2 hrs/day |  |  | Medium | PMC
11. TODAY'S HIGHLIGHTS
Column erection completed for all 8 bays – 28 nos.
Main rafter erection completed up to Bay-6
Torque test on 10% sample bolts of Bay-3 – satisfactory
Plumb & alignment survey of Bay 1 to 4 accepted
12. NEXT DAY PLAN
Main rafter erection – Bay 7 (subject to plate delivery)
Secondary members & bracing in Bay-5 and Bay-6
HSFG torqueing and torque marking of Bay-4
Mobilisation of sheeting sub-contractor gang
13. DECISIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
Expedite Bay-7 connection plates from the PEB vendor – required by 01-Aug-26 to protect the critical path
Confirmation of gantry stopper detail (RFI-088) – gantry erection held pending reply
Approval of insulation sample (MAR-051) – required before the sheeting gang is mobilised
14. S-CURVE ACTUAL HISTORY (enter once per reporting period — today's point is automatic)
DATE | ACTUAL CUM % ON THAT DATE | NOTE
2026-07-01 | 0.4989% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-06 | 4.499% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-11 | 10.5% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-16 | 16% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-21 | 23% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-26 | 30.5% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-31 | ◄ calculated on the DASHBOARD | TODAY — taken from the quantity table, do not type
2026-08-05 |  | leave blank until that date is reported
2026-08-10 |  | leave blank until that date is reported
2026-08-15 |  | leave blank until that date is reported
2026-08-20 |  | leave blank until that date is reported
2026-08-25 |  | leave blank until that date is reported
2026-08-30 |  | leave blank until that date is reported

## S-Curve Calc
S-CURVE CALCULATION — ACTUAL % ON EACH REPORTING DATE (PEB ERECTION)
Enter the CUMULATIVE quantity of each item as it stood on each reporting date (from that day's measurement book / issued DPR). The bottom row converts them into the weighted actual % for that date and feeds INPUT section 14 and the S-curve. Once a column is filled it never changes again.
SL | DESCRIPTION OF ITEM | UNIT | SCOPE QTY | WEIGHT-AGE % | 2026-07-01 | 2026-07-06 | 2026-07-11 | 2026-07-16 | 2026-07-21 | 2026-07-26 | 2026-07-31 | 2026-08-05 | 2026-08-10 | 2026-08-15 | 2026-08-20 | 2026-08-25 | 2026-08-30
1 | Anchor bolt template setting & survey | NOS | 224 | 2.529% | 2026-07-01: 2.27; 2026-07-06: 20.44; 2026-07-11: 47.7; 2026-07-16: 72.69; 2026-07-21: 104.48; 2026-07-26: 138.56
2 | Base plate placing, packing & grouting | NOS | 56 | 2.248% | 2026-07-01: 0.49; 2026-07-06: 4.45; 2026-07-11: 10.38; 2026-07-16: 15.82; 2026-07-21: 22.74; 2026-07-26: 30.15
3 | Erection of columns – Bay 1 to 4 | MT | 64 | 6.826% | 2026-07-01: 0.67; 2026-07-06: 6.06; 2026-07-11: 14.13; 2026-07-16: 21.54; 2026-07-21: 30.96; 2026-07-26: 41.05
4 | Erection of columns – Bay 5 to 8 | MT | 64 | 6.826% | 2026-07-01: 0.67; 2026-07-06: 6.06; 2026-07-11: 14.13; 2026-07-16: 21.54; 2026-07-21: 30.96; 2026-07-26: 41.05
5 | Main rafter erection – Bay 1 to 4 | MT | 78 | 9.004% | 2026-07-01: 0.82; 2026-07-06: 7.38; 2026-07-11: 17.22; 2026-07-16: 26.25; 2026-07-21: 37.73; 2026-07-26: 50.03
6 | Main rafter erection – Bay 5 to 8 | MT | 78 | 9.004% | 2026-07-01: 0.55; 2026-07-06: 4.92; 2026-07-11: 11.48; 2026-07-16: 17.5; 2026-07-21: 25.15; 2026-07-26: 33.36
7 | Crane gantry girder erection | MT | 48 | 5.902% | 2026-07-01: 0.15; 2026-07-06: 1.32; 2026-07-11: 3.09; 2026-07-16: 4.71; 2026-07-21: 6.77; 2026-07-26: 8.98
8 | Secondary members – Bay 1 to 4 | MT | 31 | 3.423% | 2026-07-01: 0.3; 2026-07-06: 2.74; 2026-07-11: 6.4; 2026-07-16: 9.76; 2026-07-21: 14.03; 2026-07-26: 18.6
9 | Secondary members – Bay 5 to 8 | MT | 31 | 3.423% | 2026-07-01: 0.04; 2026-07-06: 0.38; 2026-07-11: 0.88; 2026-07-16: 1.35; 2026-07-21: 1.93; 2026-07-26: 2.57
10 | Purlin & girt installation | MT | 84 | 9.907% | 2026-07-01: 0.39; 2026-07-06: 3.5; 2026-07-11: 8.17; 2026-07-16: 12.45; 2026-07-21: 17.9; 2026-07-26: 23.73
11 | Bracing, sag rods & tie rods | MT | 26 | 3.132% | 2026-07-01: 0.14; 2026-07-06: 1.28; 2026-07-11: 2.98; 2026-07-16: 4.54; 2026-07-21: 6.53; 2026-07-26: 8.66
12 | HSFG bolting & torqueing | NOS | 8600 | 4.1% | 2026-07-01: 36.59; 2026-07-06: 329.35; 2026-07-11: 768.49; 2026-07-16: 1171.04; 2026-07-21: 1683.37; 2026-07-26: 2232.29
13 | Site welding, NDT & touch-up painting | RM | 1450 | 4.73% | 2026-07-01: 4.99; 2026-07-06: 44.95; 2026-07-11: 104.89; 2026-07-16: 159.84; 2026-07-21: 229.77; 2026-07-26: 304.69
14 | Roof sheeting 0.5 mm PPGL | SQM | 7200 | 17.62% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
15 | Wall cladding, liner & accessories | SQM | 4300 | 11.33% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
WEIGHTED ACTUAL % ON THAT DATE |  |  |  | 100% | 0.4989% | 4.499% | 10.5% | 16% | 23% | 30.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
FORMULA: Actual % on a date = Σ [ item weightage × ( cumulative qty on that date ÷ scope qty ) ] — the same weighted calculation the DASHBOARD does for today, only using the quantities as they stood on that earlier date.
SHORTCUT: if the DPR was already issued on that date, simply type the Actual % printed on it over the green formula in INPUT section 14 — both routes give the same figure. NOTE: weightage is taken from the CURRENT rates, so if a rate is revised later, re-issued history will shift slightly; the figures on the DPRs already signed remain the record.

## Guide
HOW THIS FILE WORKS — PEB ERECTION DPR
| Two sheets only | INPUT — you type here, top to bottom, yellow cells only. DASHBOARD — the printed DPR, 100% formulas, never typed. Guide — this page.
| Daily routine | Open INPUT → change Report Date and Data Date → enter today's quantities, manpower, equipment, material, quality, HSE, delays, pending approvals, issues, highlights, next-day plan → open DASHBOARD → print to PDF.
| Adding / removing an item | Insert or delete a row inside the quantity block on INPUT and the same row position on DASHBOARD; every formula uses ranges, so totals follow.
| Weightage % | Scope Qty × Rate ÷ Σ(Scope Qty × Rate). Value weightage — always totals 100%.
| Planned % | IF(Data Date ≥ Finish, 100%, IF(Data Date < Start, 0%, (Data Date − Start + 1) ÷ (Finish − Start + 1))) — the programme prorated to the cut-off date.
| Days +/− | Finish − Data Date. Negative and red means the item is already past its programmed finish.
| Cum Qty To Date / Balance | Cum upto previous + Qty today · Scope Qty − Cum to date.
| % Complete | MIN(Cum Qty To Date ÷ Scope Qty, 1), shown with an in-cell data bar.
| Earned ₹ today | Qty today × Rate — the value of work done in the day, totalled in the KPI strip.
| Package Planned / Actual % | Σ(Weightage × Planned %) and Σ(Weightage × % Complete). These two totals drive the KPI strip, group summary, earned value block and S-curve.
| Status | Not Started / Completed / On Track (actual ≥ planned) / In Progress / Delay — colour coded.
| Group summary | SUMIFS of the weighted columns by group code ÷ that group's weightage.
| Earned value | BAC = Σ(Qty × Rate) ÷ 1,00,000 · PV = BAC × Planned % · EV = BAC × Actual % · SV = EV − PV · CV = EV − AC · CPI = EV ÷ AC · EAC = BAC ÷ CPI. Only AC is typed.
| Section 6 / 7 / 8 | Man-days = Actual Nos × hours ÷ shift hours · Utilization = Worked ÷ (Qty × shift hours) · Balance stock = Opening + Received − Consumed.
| Hours lost | (To − From) × 24 from the clock times on INPUT. EOT count is a COUNTIF of the Yes entries.
| Approval ageing | Data Date − Raised on; red beyond 7 days, and counted in the Project Health box.
| S-curve actual history | Actual % on any past date = Σ [ item weightage × (cumulative qty on that date ÷ scope qty) ]. The S-CURVE CALC sheet does this for you — enter each item's cumulative quantity as it stood on each reporting date and the bottom row gives the %, which flows into INPUT section 14. If that day's DPR was already issued, just type the Actual % from it instead.
| S-curve | Planned line = SUMPRODUCT of every item's weightage × its time-prorated fraction at each date — built entirely from the programme. Actual history comes from INPUT section 14; today's point is taken live from the quantity table.
| Paper | DASHBOARD is set to A3 landscape, fit to one page. Prints on A4 at about 70% if needed.
| Roll over to the next day | Save a copy with the new date. On INPUT: move Cum Qty To Date into 'Cum qty upto prev.', move material Balance into Opening, clear Qty Today, update the cumulative man-days and man-hours.