## DASHBOARD
SPDC |  |  | DAILY PROGRESS REPORT | [10 empty] | Report Date |  |  | 2026-07-31
[14 empty] | Data Date |  |  | 2026-07-31
|  |  | PEB – SUPPLY / FABRICATION & DELIVERY PACKAGE (VENDOR SCOPE) | [10 empty] | Report No. / Day |  |  | DPR/PEB-S-027 ¦ Friday | [5 empty] | S-CURVE DATA (not printed)
Project Name |  | <Client / Project Name> | [5 empty] | Contract / PO Ref. |  | <Work Order No. & Date> |  |  |  | PROJECT HEALTH | [8 empty] | DATE | PLANNED CUM % | ACTUAL CUM % | NOTE
Project Manager |  | <PMC Project Manager> | [5 empty] | Contract Completion |  | 2026-09-30 |  |  |  | Overall Status |  |  |  | BEHIND PROGRAMME |  |  |  |  | 2026-07-01 | 16.73% | 6.001% | from INPUT sheet section 14
Contractor / Vendor |  | <Executing Agency / PEB Vendor> | [5 empty] | Calendar / Weather |  | 6 Days / Week – 8 hrs ¦ Partly Cloudy, 32 °C |  |  |  | Critical / High issues open |  |  |  | 3 |  |  |  |  | 2026-07-06 | 26.61% | 18% | from INPUT sheet section 14
Location |  | <Plot / GIDC / District> | [5 empty] | Contract Value (₹ Lakh) |  | 623.505 |  |  |  | Approvals pending > 7 days |  |  |  | 2 |  |  |  |  | 2026-07-11 | 39.2% | 32% | from INPUT sheet section 14
1. KEY PERFORMANCE INDICATORS (all calculated — nothing is typed on this sheet) | [22 empty] | 2026-07-16 | 52.34% | 48% | from INPUT sheet section 14
PLANNED % |  |  | ACTUAL % |  |  | VARIANCE |  |  | SPI |  |  | EARNED VALUE ₹ L |  |  | VALUE DONE TODAY ₹ |  |  | ITEMS DELAYED |  | HRS LOST TODAY |  |  | 2026-07-21 | 65.64% | 60% | from INPUT sheet section 14
83.88% |  |  | 69.51% |  |  | -14.37% |  |  | 0.8287 |  |  | 433.406 |  |  | 1863600 |  |  | 4 |  | 7.3333 |  |  | 2026-07-26 | 75.8% | 68% | from INPUT sheet section 14
2. SUPPLY PROGRESS — ITEM-WISE ORDERED vs RECEIVED AT SITE (basis of the % supplied above) | [22 empty] | 2026-07-31 | 83.88% | 69.51% | ◄ today – from the quantity table
SL | DESCRIPTION OF ITEM |  |  |  | UNIT | ORDERED QTY | RATE ₹ | WEIGHT-AGE % | START | FINISH | DAYS +/− | PLANNED % | CUM RECD. PREV. | QTY TODAY | CUM QTY TO DATE | BALANCE QTY | % SUPPLIED | EARNED ₹ TODAY | WTD. PLANNED % | WTD. ACTUAL % | STATUS |  | 2026-08-05 | 89.51% |  | from INPUT sheet section 14
1 | Built-up columns – fabricated & painted |  |  |  | MT | 128 | 92000 | 18.89% | 2026-06-20 | 2026-07-12 | -19 | 100% | 128 | 0 | 128 | 0 | 100% | 0 | 18.89% | 18.89% | Completed | SUP-10 | 2026-08-10 | 91.45% |  | from INPUT sheet section 14
2 | Main rafters – fabricated & painted |  |  |  | MT | 156 | 94000 | 23.52% | 2026-06-25 | 2026-07-22 | -9 | 100% | 138 | 6 | 144 | 12 | 92.31% | 564000 | 23.52% | 21.71% | In Progress | SUP-10 | 2026-08-15 | 93.93% |  | from INPUT sheet section 14
3 | Crane gantry girders & stoppers |  |  |  | MT | 48 | 96000 | 7.39% | 2026-07-15 | 2026-08-05 | 5 | 77.27% | 14 | 2 | 16 | 32 | 33.33% | 192000 | 5.711% | 2.463% | Delay | SUP-10 | 2026-08-20 | 96.43% |  | from INPUT sheet section 14
4 | Secondary members & tie beams |  |  |  | MT | 62 | 88000 | 8.751% | 2026-07-05 | 2026-07-28 | -3 | 100% | 52 | 3 | 55 | 7 | 88.71% | 264000 | 8.751% | 7.763% | In Progress | SUP-20 | 2026-08-25 | 98.04% |  | from INPUT sheet section 14
5 | Purlins Z-200 |  |  |  | MT | 84 | 86000 | 11.59% | 2026-07-10 | 2026-08-02 | 2 | 91.67% | 46 | 4 | 50 | 34 | 59.52% | 344000 | 10.62% | 6.896% | Delay | SUP-20 | 2026-08-30 | 99.21% |  | from INPUT sheet section 14
6 | Girts Z-175 |  |  |  | MT | 56 | 86000 | 7.724% | 2026-07-12 | 2026-08-05 | 5 | 80% | 28 | 3 | 31 | 25 | 55.36% | 258000 | 6.179% | 4.276% | Delay | SUP-20
7 | Bracing, sag rods & tie rods |  |  |  | MT | 26 | 90000 | 3.753% | 2026-07-08 | 2026-07-30 | -1 | 100% | 20 | 1.5 | 21.5 | 4.5 | 82.69% | 135000 | 3.753% | 3.103% | In Progress | SUP-20
8 | HSFG bolts 8.8 – M20 / M24 |  |  |  | KGS | 3200 | 320 | 1.642% | 2026-07-01 | 2026-07-25 | -6 | 100% | 2400 | 180 | 2580 | 620 | 80.62% | 57600 | 1.642% | 1.324% | In Progress | SUP-30
9 | Anchor bolt assemblies & ordinary bolts |  |  |  | KGS | 2400 | 190 | 0.7313% | 2026-06-15 | 2026-07-20 | -11 | 100% | 2400 | 0 | 2400 | 0 | 100% | 0 | 0.7313% | 0.7313% | Completed | SUP-30
10 | Base plates, connection plates & cleats |  |  |  | MT | 18 | 98000 | 2.829% | 2026-06-25 | 2026-07-28 | -3 | 100% | 14.5 | 0.5 | 15 | 3 | 83.33% | 49000 | 2.829% | 2.358% | In Progress | SUP-30
11 | Roof sheeting 0.5 mm PPGL |  |  |  | SQM | 7200 | 420 | 4.85% | 2026-07-25 | 2026-08-20 | 20 | 25.93% | 0 | 0 | 0 | 7200 | 0% | 0 | 1.257% | 0% | Delay | SUP-40
12 | Wall cladding & liner sheet |  |  |  | SQM | 4300 | 385 | 2.655% | 2026-08-05 | 2026-08-30 | 30 | 0% | 0 | 0 | 0 | 4300 | 0% | 0 | 0% | 0% | Not Started | SUP-40
13 | Insulation – 50 mm glass wool |  |  |  | SQM | 7200 | 190 | 2.194% | 2026-08-01 | 2026-08-25 | 25 | 0% | 0 | 0 | 0 | 7200 | 0% | 0 | 0% | 0% | Not Started | SUP-40
14 | Gutter, flashing, ventilators & louvers |  |  |  | LOT | 1 | 1650000 | 2.646% | 2026-08-10 | 2026-09-05 | 36 | 0% | 0 | 0 | 0 | 1 | 0% | 0 | 0% | 0% | Not Started | SUP-50
15 | Skylight & polycarbonate sheet |  |  |  | SQM | 420 | 1250 | 0.842% | 2026-08-12 | 2026-09-05 | 36 | 0% | 0 | 0 | 0 | 420 | 0% | 0 | 0% | 0% | Not Started | SUP-50
TOTAL / OVERALL PACKAGE PROGRESS |  |  |  |  | ₹ 623.5 Lakh |  |  | 100% | PROGRAMME |  |  | 83.88% |  |  |  |  | 69.51% | 1863600 | 83.88% | 69.51% | BEHIND
3. PROGRESS SUMMARY BY GROUP (value weighted) | [9 empty] | 4. PROGRESS S-CURVE (PLANNED vs ACTUAL)
GROUP |  | DESCRIPTION |  |  | WEIGHTAGE |  | PLANNED % | ACTUAL % | SPI
SUP-10 |  | Primary Members – Columns, Rafters, Gantry |  |  | 49.8% |  | 96.63% | 86.47% | 0.89491
SUP-20 |  | Secondary Members – Purlins, Girts, Bracing |  |  | 31.81% |  | 92.11% | 69.27% | 0.75207
SUP-30 |  | Connections – Bolts, Base Plates, Cleats |  |  | 5.203% |  | 100% | 84.82% | 0.84821
SUP-40 |  | Sheeting – Roof, Wall, Insulation |  |  | 9.699% |  | 12.96% | 0% | 0
SUP-50 |  | Accessories – Gutters, Ventilators, Louvers |  |  | 3.488% |  | 0% | 0%
TOTAL |  |  |  |  | 100% |  | 83.88% | 69.51% | 0.8287
5. EARNED VALUE / COMMERCIAL SNAPSHOT (₹ in Lakh)
BAC – Contract value of package | [6 empty] | 623.505
PV – Planned Value (BAC × Planned %) | [6 empty] | 522.9953
EV – Earned Value (BAC × Actual %) | [6 empty] | 433.406
AC – Certified / paid to date | [6 empty] | 455
SV – Schedule Variance (EV − PV) | [6 empty] | -89.5893
CV – Cost Variance (EV − AC) | [6 empty] | -21.594
CPI ¦ EAC (BAC ÷ CPI) | [6 empty] | 0.95 ¦ ₹ 654.6 L
6. FABRICATION STATUS AT VENDOR WORKS (MT) | [6 empty] | 7. DISPATCH & RECEIPT TODAY | [6 empty] | 8. STOCK AT SITE / SHORTAGE & DAMAGE
STAGE AT VENDOR WORKS |  |  | PLAN MT | ACTUAL MT | % COMPLETE |  | LR / INVOICE NO. |  |  | ITEM DESPATCHED |  | QTY | GRN NO. | ITEM |  |  | RECD. CUM | ISSUED | BALANCE AT SITE |  | SHORT / DAMAGE
Shop drawings approved (equiv. MT) |  |  | 494 | 468 | 94.74% |  | INV-2264 / LR-8841 |  |  | Main rafters – Bay 7 |  | 6 | GRN-118 | Columns & rafters (MT) |  |  | 272 | 268 | 4 |  | —
Raw material cut & fit-up |  |  | 470 | 442 | 94.04% |  | INV-2265 / LR-8842 |  |  | Purlins Z-200 |  | 4 | GRN-119 | Secondary members (MT) |  |  | 55 | 51 | 4 |  | —
Welding & assembly completed |  |  | 440 | 408 | 92.73% |  | INV-2266 / LR-8848 |  |  | Girts Z-175 |  | 3 | GRN-120 | Purlins & girts (MT) |  |  | 81 | 74 | 7 |  | 0.4 MT bent – Bay 5
Blasting & shop painting |  |  | 420 | 386 | 91.9% |  | INV-2267 / LR-8851 |  |  | HSFG bolts M20 |  | 0.18 | GRN-121 | Bracing & sag rods (MT) |  |  | 21.5 | 19 | 2.5 |  | —
Inspected & ready for dispatch |  |  | 400 | 362 | 90.5% |  | INV-2268 / LR-8853 |  |  | Gantry girder – 1 no. |  | 2 | GRN-122 | Bolts – HSFG & ordinary (KGS) |  |  | 4980 | 4620 | 360 |  | 12 kg short in INV-2251
Dispatched from works |  |  | 386 | 344 | 89.12% |  | INV-2269 / LR-8855 |  |  | Bracing & sag rods |  | 1.5 | GRN-123 | Base & connection plates (MT) |  |  | 15 | 13.8 | 1.2 |  | 2 cleats damaged
OVERALL FABRICATION STATUS |  |  | 2610 | 2410 | 92.34% |  | TOTAL RECEIVED TODAY (MT eq.) |  |  |  |  | 16.68 | 6 GRN | Balance at site = Received cumulative − Issued to erection · shortages to be covered by debit note / replacement
9. QUALITY CONTROL & TESTS TODAY | [6 empty] | 10. HSE / SAFETY STATISTICS | [6 empty] | 11. DELAY / IDLE TIME LOG TODAY
MTC / test certificates received |  |  |  |  | 18 of 22 lots |  | Unloading – crane / hydra third party cert. |  |  |  |  | Valid till 12-Nov-26 |  | CAUSE (CATEGORY) |  |  |  | FROM | TO | HRS LOST | EOT
DFT readings taken / accepted |  |  |  |  | 20 / 18 |  | Safe unloading permits issued today |  |  |  |  | 4 |  | Truck detained at check post – Halol (Statutory) |  |  |  | 8:30 | 11:00 | 2.5 | Yes
Dimensional check at receipt |  |  |  |  | 6 lots – 5 OK, 1 hold |  | Toolbox talk before unloading |  |  |  |  | Done – 2 gangs |  | Bay-7 connection plates not despatched (Client / Vendor) |  |  |  | 9:00 | 13:00 | 4 | Yes
Third party inspection at works |  |  |  |  | Cleared upto Bay-6 |  | Slings & tackles inspected / colour coded |  |  |  |  | Yes |  | Rain – unloading stopped (Weather) |  |  |  | 15:10 | 16:00 | 0.83333 | Review
Material rejected / on hold today |  |  |  |  | 1 lot – purlin bundle |  | Stacking on sleepers – verified |  |  |  |  | Yes – 4 stack yards | [5 empty] | 0:00 | 0:00 |  | 0
Painting shade & primer verification |  |  |  |  | As per approved scheme |  | Incidents during unloading today |  |  |  |  | Nil |  | TOTAL HOURS LOST TODAY | [5 empty] | 7.3333 | 2 EOT
12. DRAWINGS / RFI / MATERIAL APPROVALS PENDING | [10 empty] | 13. ISSUES & RISKS (open items)
REF. NO. |  | DESCRIPTION | [5 empty] | RAISED ON | AGEING | PENDING WITH | ISSUE / RISK DESCRIPTION | [6 empty] | SEVERITY |  | OWNER
SD-142 |  | Roof sheeting layout rev-3 with skylight – approval | [5 empty] | 2026-07-20 | 11 | PEB Vendor | ⚠ Bay-7 connection plates not despatched – holds erection critical path | [6 empty] | Critical |  | Vendor
MAR-051 |  | Insulation 50 mm glass wool – sample approval | [5 empty] | 2026-07-16 | 15 | Client | ⚠ Sheeting supply not started against 25-Jul planned date | [6 empty] | Critical |  | Vendor
MAR-050 |  | HSFG bolt batch test certificate | [5 empty] | 2026-07-24 | 7 | PMC | ⚠ MTCs pending for 4 lots already erected | [6 empty] | High |  | Vendor
SD-139 |  | Gantry girder shop drawing – Bay 8 | [5 empty] | 2026-07-27 | 4 | PEB Vendor | ⚠ 12 kg HSFG bolt shortage in INV-2251 – debit note to be raised | [6 empty] | Medium |  | PMC
14. TODAY'S HIGHLIGHTS | [10 empty] | 15. NEXT DAY PLAN
★ Column supply completed in full – 128 MT received & accounted | [10 empty] | ➜ Balance 12 MT of main rafters – dispatch confirmation to be obtained
★ 6 MT of Bay-7 main rafters received today under GRN-118 | [10 empty] | ➜ Follow up Bay-7 connection plates – expedite from works
★ Gantry girder – first consignment of 2 MT received | [10 empty] | ➜ Roof sheeting dispatch schedule to be submitted by vendor
★ Third party inspection at works cleared upto Bay-6 | [10 empty] | ➜ MTC compilation for lots already erected
16. DECISIONS / INSTRUCTIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
1. Vendor to confirm firm dispatch dates for roof sheeting and wall cladding – supply is 6 days behind the delivery programme
2. Approval of 50 mm glass wool insulation sample (MAR-051) – pending 15 days, holds the sheeting order
3. Debit note / replacement for 12 kg HSFG bolt shortage and damaged cleats to be confirmed by the vendor
Prepared By |  |  |  |  | Verified By |  |  |  |  | Approved By |  |  |  |  | Client Representative
Name / Sign / Date — Site Engineer – SPDC |  |  |  |  | Name / Sign / Date — Stores / QA – Receipt |  |  |  |  | Name / Sign / Date — Project Manager – SPDC |  |  |  |  | Name / Sign / Date — For and on behalf of Client
Sharnam Project Development Consultants & Co. (SPDC), Vadodara ¦ Project Management Consultancy ¦ THIS SHEET IS ALL FORMULAS — enter data on the INPUT sheet ¦ A3 Landscape – Page 1 of 1

## INPUT
DAILY INPUT SHEET — PEB – SUPPLY / FABRICATION & DELIVERY PACKAGE (VENDOR SCOPE)
TYPE ONLY IN THE YELLOW CELLS ON THIS SHEET. The DASHBOARD sheet is the printed DPR — it is all formulas and must not be typed over. Fill top to bottom, then print the DASHBOARD to PDF.
1. PROJECT HEADER (change once at the start, then only the dates each day)
Project name | <Client / Project Name>
Project manager | <PMC Project Manager>
Contractor / vendor | <Executing Agency / PEB Vendor>
Location | <Plot / GIDC / District>
Prepared by | Site Engineer – SPDC (PMC)
Contract / PO reference | <Work Order No. & Date>
Contract completion date | 2026-09-30
Calendar / working hours | 6 Days / Week – 8 hrs |  |  | Shift hours drive man-days & utilization
Shift hours per day | 8 |  |  | Used for man-days and equipment utilization
Weather | Partly Cloudy, 32 °C
REPORT DATE | 2026-07-31
DATA DATE (cut-off) | 2026-07-31 |  |  | Every planned % is measured to this date
Report number | DPR/PEB-S-027
AC – certified / paid to date (₹ Lakh) | 455 |  |  | From the RA bill / cost report
Cumulative man-days upto previous day | 1180
Cumulative safe man-hours upto prev. day | 42150
Date of last LTI | 2026-03-31 |  |  | Days without LTI counts from here
2. QUANTITY PROGRESS (one row per BOQ / scope item — type today's quantity in the last column)
GROUP | DESCRIPTION OF ITEM |  | UNIT | ORDERED QTY | RATE ₹ | START | FINISH | CUM QTY UPTO PREV. | QTY TODAY
SUP-10 | Built-up columns – fabricated & painted |  | MT | 128 | 92000 | 2026-06-20 | 2026-07-12 | 128 | 0
SUP-10 | Main rafters – fabricated & painted |  | MT | 156 | 94000 | 2026-06-25 | 2026-07-22 | 138 | 6
SUP-10 | Crane gantry girders & stoppers |  | MT | 48 | 96000 | 2026-07-15 | 2026-08-05 | 14 | 2
SUP-20 | Secondary members & tie beams |  | MT | 62 | 88000 | 2026-07-05 | 2026-07-28 | 52 | 3
SUP-20 | Purlins Z-200 |  | MT | 84 | 86000 | 2026-07-10 | 2026-08-02 | 46 | 4
SUP-20 | Girts Z-175 |  | MT | 56 | 86000 | 2026-07-12 | 2026-08-05 | 28 | 3
SUP-20 | Bracing, sag rods & tie rods |  | MT | 26 | 90000 | 2026-07-08 | 2026-07-30 | 20 | 1.5
SUP-30 | HSFG bolts 8.8 – M20 / M24 |  | KGS | 3200 | 320 | 2026-07-01 | 2026-07-25 | 2400 | 180
SUP-30 | Anchor bolt assemblies & ordinary bolts |  | KGS | 2400 | 190 | 2026-06-15 | 2026-07-20 | 2400 | 0
SUP-30 | Base plates, connection plates & cleats |  | MT | 18 | 98000 | 2026-06-25 | 2026-07-28 | 14.5 | 0.5
SUP-40 | Roof sheeting 0.5 mm PPGL |  | SQM | 7200 | 420 | 2026-07-25 | 2026-08-20 | 0 | 0
SUP-40 | Wall cladding & liner sheet |  | SQM | 4300 | 385 | 2026-08-05 | 2026-08-30 | 0 | 0
SUP-40 | Insulation – 50 mm glass wool |  | SQM | 7200 | 190 | 2026-08-01 | 2026-08-25 | 0 | 0
SUP-50 | Gutter, flashing, ventilators & louvers |  | LOT | 1 | 1650000 | 2026-08-10 | 2026-09-05 | 0 | 0
SUP-50 | Skylight & polycarbonate sheet |  | SQM | 420 | 1250 | 2026-08-12 | 2026-09-05 | 0 | 0
3. FABRICATION STATUS AT VENDOR WORKS
STAGE AT VENDOR WORKS |  | PLAN MT | ACTUAL MT
Shop drawings approved (equiv. MT) |  | 494 | 468
Raw material cut & fit-up |  | 470 | 442
Welding & assembly completed |  | 440 | 408
Blasting & shop painting |  | 420 | 386
Inspected & ready for dispatch |  | 400 | 362
Dispatched from works |  | 386 | 344
4. DISPATCH & RECEIPT TODAY
LR / INVOICE NO. |  | ITEM DESPATCHED |  | QTY (MT eq.) | GRN NO.
INV-2264 / LR-8841 |  | Main rafters – Bay 7 |  | 6 | GRN-118
INV-2265 / LR-8842 |  | Purlins Z-200 |  | 4 | GRN-119
INV-2266 / LR-8848 |  | Girts Z-175 |  | 3 | GRN-120
INV-2267 / LR-8851 |  | HSFG bolts M20 |  | 0.18 | GRN-121
INV-2268 / LR-8853 |  | Gantry girder – 1 no. |  | 2 | GRN-122
INV-2269 / LR-8855 |  | Bracing & sag rods |  | 1.5 | GRN-123
5. STOCK AT SITE / SHORTAGE & DAMAGE
ITEM |  | RECD. CUM | ISSUED TO ERECTION | SHORTAGE / DAMAGE
Columns & rafters (MT) |  | 272 | 268 | —
Secondary members (MT) |  | 55 | 51 | —
Purlins & girts (MT) |  | 81 | 74 | 0.4 MT bent – Bay 5
Bracing & sag rods (MT) |  | 21.5 | 19 | —
Bolts – HSFG & ordinary (KGS) |  | 4980 | 4620 | 12 kg short in INV-2251
Base & connection plates (MT) |  | 15 | 13.8 | 2 cleats damaged
6. QUALITY CONTROL & TESTS TODAY
QUALITY / TEST PARAMETER |  | TODAY'S FIGURE
MTC / test certificates received |  | 18 of 22 lots
DFT readings taken / accepted |  | 20 / 18
Dimensional check at receipt |  | 6 lots – 5 OK, 1 hold
Third party inspection at works |  | Cleared upto Bay-6
Material rejected / on hold today |  | 1 lot – purlin bundle
Painting shade & primer verification |  | As per approved scheme
7. HSE / SAFETY STATISTICS
HSE PARAMETER |  | TODAY'S FIGURE
Unloading – crane / hydra third party cert. |  | Valid till 12-Nov-26
Safe unloading permits issued today |  | 4
Toolbox talk before unloading |  | Done – 2 gangs
Slings & tackles inspected / colour coded |  | Yes
Stacking on sleepers – verified |  | Yes – 4 stack yards
Incidents during unloading today |  | Nil
8. DELAY / IDLE TIME LOG TODAY (enter clock times — hours are calculated)
CAUSE OF DELAY / IDLE TIME |  | CATEGORY | FROM | TO | EOT
Truck detained at check post – Halol |  | Statutory | 8:30 | 11:00 | Yes
Bay-7 connection plates not despatched |  | Client / Vendor | 9:00 | 13:00 | Yes
Rain – unloading stopped |  | Weather | 15:10 | 16:00 | Review
9. DRAWINGS / RFI / MATERIAL APPROVALS PENDING (ageing is calculated)
REF. NO. | DESCRIPTION |  | RAISED ON | PENDING WITH
SD-142 | Roof sheeting layout rev-3 with skylight – approval |  | 2026-07-20 | PEB Vendor
MAR-051 | Insulation 50 mm glass wool – sample approval |  | 2026-07-16 | Client
MAR-050 | HSFG bolt batch test certificate |  | 2026-07-24 | PMC
SD-139 | Gantry girder shop drawing – Bay 8 |  | 2026-07-27 | PEB Vendor
10. ISSUES & RISKS (open items)
ISSUE / RISK DESCRIPTION |  |  | SEVERITY | OWNER
Bay-7 connection plates not despatched – holds erection critical path |  |  | Critical | Vendor
Sheeting supply not started against 25-Jul planned date |  |  | Critical | Vendor
MTCs pending for 4 lots already erected |  |  | High | Vendor
12 kg HSFG bolt shortage in INV-2251 – debit note to be raised |  |  | Medium | PMC
11. TODAY'S HIGHLIGHTS
Column supply completed in full – 128 MT received & accounted
6 MT of Bay-7 main rafters received today under GRN-118
Gantry girder – first consignment of 2 MT received
Third party inspection at works cleared upto Bay-6
12. NEXT DAY PLAN
Balance 12 MT of main rafters – dispatch confirmation to be obtained
Follow up Bay-7 connection plates – expedite from works
Roof sheeting dispatch schedule to be submitted by vendor
MTC compilation for lots already erected
13. DECISIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
Vendor to confirm firm dispatch dates for roof sheeting and wall cladding – supply is 6 days behind the delivery programme
Approval of 50 mm glass wool insulation sample (MAR-051) – pending 15 days, holds the sheeting order
Debit note / replacement for 12 kg HSFG bolt shortage and damaged cleats to be confirmed by the vendor
14. S-CURVE ACTUAL HISTORY (enter once per reporting period — today's point is automatic)
DATE | ACTUAL CUM % ON THAT DATE | NOTE
2026-07-01 | 6.001% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-06 | 18% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-11 | 32% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-16 | 48% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-21 | 60% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-26 | 68% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-31 | ◄ calculated on the DASHBOARD | TODAY — taken from the quantity table, do not type
2026-08-05 |  | leave blank until that date is reported
2026-08-10 |  | leave blank until that date is reported
2026-08-15 |  | leave blank until that date is reported
2026-08-20 |  | leave blank until that date is reported
2026-08-25 |  | leave blank until that date is reported
2026-08-30 |  | leave blank until that date is reported

## S-Curve Calc
S-CURVE CALCULATION — ACTUAL % ON EACH REPORTING DATE (PEB SUPPLY)
Enter the CUMULATIVE quantity of each item as it stood on each reporting date (from that day's measurement book / issued DPR). The bottom row converts them into the weighted actual % for that date and feeds INPUT section 14 and the S-curve. Once a column is filled it never changes again.
SL | DESCRIPTION OF ITEM | UNIT | SCOPE QTY | WEIGHT-AGE % | 2026-07-01 | 2026-07-06 | 2026-07-11 | 2026-07-16 | 2026-07-21 | 2026-07-26 | 2026-07-31 | 2026-08-05 | 2026-08-10 | 2026-08-15 | 2026-08-20 | 2026-08-25 | 2026-08-30
1 | Built-up columns – fabricated & painted | MT | 128 | 18.89% | 2026-07-01: 11.05; 2026-07-06: 33.15; 2026-07-11: 58.93; 2026-07-16: 88.39; 2026-07-21: 110.49; 2026-07-26: 125.22
2 | Main rafters – fabricated & painted | MT | 156 | 23.52% | 2026-07-01: 12.43; 2026-07-06: 37.29; 2026-07-11: 66.29; 2026-07-16: 99.44; 2026-07-21: 124.3; 2026-07-26: 140.87
3 | Crane gantry girders & stoppers | MT | 48 | 7.39% | 2026-07-01: 1.38; 2026-07-06: 4.14; 2026-07-11: 7.37; 2026-07-16: 11.05; 2026-07-21: 13.81; 2026-07-26: 15.65
4 | Secondary members & tie beams | MT | 62 | 8.751% | 2026-07-01: 4.75; 2026-07-06: 14.24; 2026-07-11: 25.32; 2026-07-16: 37.98; 2026-07-21: 47.47; 2026-07-26: 53.8
5 | Purlins Z-200 | MT | 84 | 11.59% | 2026-07-01: 4.32; 2026-07-06: 12.95; 2026-07-11: 23.02; 2026-07-16: 34.53; 2026-07-21: 43.16; 2026-07-26: 48.91
6 | Girts Z-175 | MT | 56 | 7.724% | 2026-07-01: 2.68; 2026-07-06: 8.03; 2026-07-11: 14.27; 2026-07-16: 21.41; 2026-07-21: 26.76; 2026-07-26: 30.33
7 | Bracing, sag rods & tie rods | MT | 26 | 3.753% | 2026-07-01: 1.86; 2026-07-06: 5.57; 2026-07-11: 9.9; 2026-07-16: 14.85; 2026-07-21: 18.56; 2026-07-26: 21.03
8 | HSFG bolts 8.8 – M20 / M24 | KGS | 3200 | 1.642% | 2026-07-01: 222.7; 2026-07-06: 668.09; 2026-07-11: 1187.72; 2026-07-16: 1781.58; 2026-07-21: 2226.98; 2026-07-26: 2523.91
9 | Anchor bolt assemblies & ordinary bolts | KGS | 2400 | 0.7313% | 2026-07-01: 207.16; 2026-07-06: 621.48; 2026-07-11: 1104.86; 2026-07-16: 1657.29; 2026-07-21: 2071.61; 2026-07-26: 2347.82
10 | Base plates, connection plates & cleats | MT | 18 | 2.829% | 2026-07-01: 1.29; 2026-07-06: 3.88; 2026-07-11: 6.91; 2026-07-16: 10.36; 2026-07-21: 12.95; 2026-07-26: 14.67
11 | Roof sheeting 0.5 mm PPGL | SQM | 7200 | 4.85% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
12 | Wall cladding & liner sheet | SQM | 4300 | 2.655% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
13 | Insulation – 50 mm glass wool | SQM | 7200 | 2.194% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
14 | Gutter, flashing, ventilators & louvers | LOT | 1 | 2.646% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
15 | Skylight & polycarbonate sheet | SQM | 420 | 0.842% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
WEIGHTED ACTUAL % ON THAT DATE |  |  |  | 100% | 6.001% | 18% | 32% | 48% | 60% | 68% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
FORMULA: Actual % on a date = Σ [ item weightage × ( cumulative qty on that date ÷ scope qty ) ] — the same weighted calculation the DASHBOARD does for today, only using the quantities as they stood on that earlier date.
SHORTCUT: if the DPR was already issued on that date, simply type the Actual % printed on it over the green formula in INPUT section 14 — both routes give the same figure. NOTE: weightage is taken from the CURRENT rates, so if a rate is revised later, re-issued history will shift slightly; the figures on the DPRs already signed remain the record.

## Guide
HOW THIS FILE WORKS — PEB SUPPLY DPR
| Two sheets only | INPUT — you type here, top to bottom, yellow cells only. DASHBOARD — the printed DPR, 100% formulas, never typed. Guide — this page.
| Daily routine | Open INPUT → change Report Date and Data Date → enter today's quantities, manpower, equipment, material, quality, HSE, delays, pending approvals, issues, highlights, next-day plan → open DASHBOARD → print to PDF.
| Adding / removing an item | Insert or delete a row inside the quantity block on INPUT and the same row position on DASHBOARD; every formula uses ranges, so totals follow.
| Weightage % | Ordered Qty × Rate ÷ Σ(Ordered Qty × Rate). Value weightage — always totals 100%.
| Planned % | IF(Data Date ≥ Finish, 100%, IF(Data Date < Start, 0%, (Data Date − Start + 1) ÷ (Finish − Start + 1))) — the programme prorated to the cut-off date.
| Days +/− | Finish − Data Date. Negative and red means the item is already past its programmed finish.
| Cum Qty To Date / Balance | Cum upto previous + Qty today · Ordered Qty − Cum to date.
| % Complete | MIN(Cum Qty To Date ÷ Ordered Qty, 1), shown with an in-cell data bar.
| Earned ₹ today | Qty today × Rate — the value of work done in the day, totalled in the KPI strip.
| Package Planned / Actual % | Σ(Weightage × Planned %) and Σ(Weightage × % Complete). These two totals drive the KPI strip, group summary, earned value block and S-curve.
| Status | Not Started / Completed / On Track (actual ≥ planned) / In Progress / Delay — colour coded.
| Group summary | SUMIFS of the weighted columns by group code ÷ that group's weightage.
| Earned value | BAC = Σ(Qty × Rate) ÷ 1,00,000 · PV = BAC × Planned % · EV = BAC × Actual % · SV = EV − PV · CV = EV − AC · CPI = EV ÷ AC · EAC = BAC ÷ CPI. Only AC is typed.
| Section 6 / 7 / 8 | Fabrication % = Actual MT ÷ Plan MT · dispatch quantities and GRN count · balance at site = received cumulative − issued.
| Hours lost | (To − From) × 24 from the clock times on INPUT. EOT count is a COUNTIF of the Yes entries.
| Approval ageing | Data Date − Raised on; red beyond 7 days, and counted in the Project Health box.
| S-curve actual history | Actual % on any past date = Σ [ item weightage × (cumulative qty on that date ÷ scope qty) ]. The S-CURVE CALC sheet does this for you — enter each item's cumulative quantity as it stood on each reporting date and the bottom row gives the %, which flows into INPUT section 14. If that day's DPR was already issued, just type the Actual % from it instead.
| S-curve | Planned line = SUMPRODUCT of every item's weightage × its time-prorated fraction at each date — built entirely from the programme. Actual history comes from INPUT section 14; today's point is taken live from the quantity table.
| Paper | DASHBOARD is set to A3 landscape, fit to one page. Prints on A4 at about 70% if needed.
| Roll over to the next day | Save a copy with the new date. On INPUT: move Cum Qty To Date into 'Cum qty upto prev.', move material Balance into Opening, clear Qty Today, update the cumulative man-days and man-hours.