## DASHBOARD
SPDC |  |  | DAILY PROGRESS REPORT | [10 empty] | Report Date |  |  | 2026-07-31
[14 empty] | Data Date |  |  | 2026-07-31
|  |  | PLUMBING, WATER SUPPLY & DRAINAGE PACKAGE | [10 empty] | Report No. / Day |  |  | DPR/PLB-027 ¦ Friday | [5 empty] | S-CURVE DATA (not printed)
Project Name |  | <Client / Project Name> | [5 empty] | Contract / PO Ref. |  | <Work Order No. & Date> |  |  |  | PROJECT HEALTH | [8 empty] | DATE | PLANNED CUM % | ACTUAL CUM % | NOTE
Project Manager |  | <PMC Project Manager> | [5 empty] | Contract Completion |  | 2026-09-30 |  |  |  | Overall Status |  |  |  | BEHIND PROGRAMME |  |  |  |  | 2026-07-01 | 0% | 0% | from INPUT sheet section 14
Contractor / Vendor |  | <Executing Agency / PEB Vendor> | [5 empty] | Calendar / Weather |  | 6 Days / Week – 8 hrs ¦ Partly Cloudy, 32 °C |  |  |  | Critical / High issues open |  |  |  | 3 |  |  |  |  | 2026-07-06 | 0% | 1.2% | from INPUT sheet section 14
Location |  | <Plot / GIDC / District> | [5 empty] | Contract Value (₹ Lakh) |  | 76.688 |  |  |  | Approvals pending > 7 days |  |  |  | 3 |  |  |  |  | 2026-07-11 | 0.2415% | 3.001% | from INPUT sheet section 14
1. KEY PERFORMANCE INDICATORS (all calculated — nothing is typed on this sheet) | [22 empty] | 2026-07-16 | 1.379% | 5.202% | from INPUT sheet section 14
PLANNED % |  |  | ACTUAL % |  |  | VARIANCE |  |  | SPI |  |  | EARNED VALUE ₹ L |  |  | VALUE DONE TODAY ₹ |  |  | ITEMS DELAYED |  | HRS LOST TODAY |  |  | 2026-07-21 | 3.427% | 6.675% | from INPUT sheet section 14
8.524% |  |  | 6.675% |  |  | -1.849% |  |  | 0.78303 |  |  | 5.1186 |  |  | 74760 |  |  | 2 |  | 5 |  |  | 2026-07-26 | 5.831% | 6.675% | from INPUT sheet section 14
2. QUANTITY / PHYSICAL PROGRESS — ITEM-WISE (basis of the % complete above) | [22 empty] | 2026-07-31 | 8.524% | 6.675% | ◄ today – from the quantity table
SL | DESCRIPTION OF ITEM |  |  |  | UNIT | SCOPE QTY | RATE ₹ | WEIGHT-AGE % | START | FINISH | DAYS +/− | PLANNED % | CUM QTY PREV. | QTY TODAY | CUM QTY TO DATE | BALANCE QTY | % COMPL. | EARNED ₹ TODAY | WTD. PLANNED % | WTD. ACTUAL % | STATUS |  | 2026-08-05 | 11.22% |  | from INPUT sheet section 14
1 | UG HDPE water line 90 mm with fittings |  |  |  | RM | 640 | 680 | 5.675% | 2026-07-10 | 2026-08-25 | 25 | 46.81% | 180 | 22 | 202 | 438 | 31.56% | 14960 | 2.656% | 1.791% | Delay | PLB-10 | 2026-08-10 | 13.91% |  | from INPUT sheet section 14
2 | UG sump, pump room piping & valves |  |  |  | LS | 1 | 480000 | 6.259% | 2026-08-15 | 2026-09-30 | 61 | 0% | 0 | 0 | 0 | 1 | 0% | 0 | 0% | 0% | Not Started | PLB-10 | 2026-08-15 | 16.74% |  | from INPUT sheet section 14
3 | Water meter, valves & masonry chambers |  |  |  | NOS | 16 | 12500 | 2.608% | 2026-07-20 | 2026-09-05 | 36 | 25% | 3 | 1 | 4 | 12 | 25% | 12500 | 0.652% | 0.652% | On Track | PLB-10 | 2026-08-20 | 20.35% |  | from INPUT sheet section 14
4 | CPVC piping 25 to 50 mm concealed |  |  |  | RM | 1450 | 420 | 7.941% | 2026-08-20 | 2026-10-15 | 76 | 0% | 0 | 0 | 0 | 1450 | 0% | 0 | 0% | 0% | Not Started | PLB-20 | 2026-08-25 | 25.15% |  | from INPUT sheet section 14
5 | GI piping 40 to 80 mm exposed |  |  |  | RM | 620 | 860 | 6.953% | 2026-08-25 | 2026-10-10 | 71 | 0% | 0 | 0 | 0 | 620 | 0% | 0 | 0% | 0% | Not Started | PLB-20 | 2026-08-30 | 29.93% |  | from INPUT sheet section 14
6 | Overhead tank connections, valves & float |  |  |  | NOS | 12 | 9800 | 1.533% | 2026-09-20 | 2026-10-25 | 86 | 0% | 0 | 0 | 0 | 12 | 0% | 0 | 0% | 0% | Not Started | PLB-20
7 | SWR / PVC soil & waste pipe 110 mm |  |  |  | RM | 980 | 480 | 6.134% | 2026-08-20 | 2026-10-10 | 71 | 0% | 0 | 0 | 0 | 980 | 0% | 0 | 0% | 0% | Not Started | PLB-30
8 | Rainwater downtake pipe 160 mm |  |  |  | RM | 720 | 620 | 5.821% | 2026-09-01 | 2026-10-20 | 81 | 0% | 0 | 0 | 0 | 720 | 0% | 0 | 0% | 0% | Not Started | PLB-30
9 | UG drainage line with inspection chambers |  |  |  | RM | 540 | 2200 | 15.49% | 2026-07-15 | 2026-09-10 | 41 | 29.31% | 96 | 14 | 110 | 430 | 20.37% | 30800 | 4.541% | 3.156% | Delay | PLB-30
10 | Manholes, gully traps & covers |  |  |  | NOS | 26 | 16500 | 5.594% | 2026-07-25 | 2026-09-20 | 51 | 12.07% | 4 | 1 | 5 | 21 | 19.23% | 16500 | 0.6751% | 1.076% | On Track | PLB-30
11 | WC, wash basin & urinal with fittings |  |  |  | NOS | 68 | 14500 | 12.86% | 2026-10-01 | 2026-11-15 | 107 | 0% | 0 | 0 | 0 | 68 | 0% | 0 | 0% | 0% | Not Started | PLB-40
12 | CP fittings, taps & health faucets |  |  |  | NOS | 120 | 3200 | 5.007% | 2026-10-10 | 2026-11-20 | 112 | 0% | 0 | 0 | 0 | 120 | 0% | 0 | 0% | 0% | Not Started | PLB-40
13 | Water cooler & drinking water stations |  |  |  | NOS | 8 | 42000 | 4.381% | 2026-11-01 | 2026-11-25 | 117 | 0% | 0 | 0 | 0 | 8 | 0% | 0 | 0% | 0% | Not Started | PLB-40
14 | Pressure testing & flushing of lines |  |  |  | RM | 3200 | 95 | 3.964% | 2026-10-15 | 2026-11-30 | 122 | 0% | 0 | 0 | 0 | 3200 | 0% | 0 | 0% | 0% | Not Started | PLB-50
15 | STP tie-in, trial run & commissioning |  |  |  | LS | 1 | 750000 | 9.78% | 2026-11-15 | 2026-12-10 | 132 | 0% | 0 | 0 | 0 | 1 | 0% | 0 | 0% | 0% | Not Started | PLB-50
TOTAL / OVERALL PACKAGE PROGRESS |  |  |  |  | ₹ 76.7 Lakh |  |  | 100% | PROGRAMME |  |  | 8.524% |  |  |  |  | 6.675% | 74760 | 8.524% | 6.675% | BEHIND
3. PROGRESS SUMMARY BY GROUP (value weighted) | [9 empty] | 4. PROGRESS S-CURVE (PLANNED vs ACTUAL)
GROUP |  | DESCRIPTION |  |  | WEIGHTAGE |  | PLANNED % | ACTUAL % | SPI
PLB-10 |  | Underground Water Supply & Sump |  |  | 14.54% |  | 22.75% | 16.8% | 0.73848
PLB-20 |  | Internal Water Supply Piping |  |  | 16.43% |  | 0% | 0%
PLB-30 |  | Soil, Waste, Rainwater & UG Drainage |  |  | 33.04% |  | 15.79% | 12.81% | 0.81128
PLB-40 |  | Sanitary Fixtures & CP Fittings |  |  | 22.25% |  | 0% | 0%
PLB-50 |  | Testing, STP Tie-in & Commissioning |  |  | 13.74% |  | 0% | 0%
TOTAL |  |  |  |  | 100% |  | 8.524% | 6.675% | 0.78303
5. EARNED VALUE / COMMERCIAL SNAPSHOT (₹ in Lakh)
BAC – Contract value of package | [6 empty] | 76.688
PV – Planned Value (BAC × Planned %) | [6 empty] | 6.5369
EV – Earned Value (BAC × Actual %) | [6 empty] | 5.1186
AC – Certified / paid to date | [6 empty] | 5.4
SV – Schedule Variance (EV − PV) | [6 empty] | -1.4183
CV – Cost Variance (EV − AC) | [6 empty] | -0.2814
CPI ¦ EAC (BAC ÷ CPI) | [6 empty] | 0.95 ¦ ₹ 80.9 L
6. MANPOWER DEPLOYED TODAY | [6 empty] | 7. EQUIPMENT UTILIZATION TODAY | [6 empty] | 8. KEY MATERIAL AT SITE
TRADE / CATEGORY |  |  | PLAN | ACTUAL | MAN-DAYS |  | EQUIPMENT |  |  | QTY | WORKED HRS | IDLE HRS | UTIL. % | MATERIAL |  |  | UNIT | OPENING | RECD. | CONSUMED | BALANCE
Plumber |  |  | 10 | 8 | 8.5 |  | Excavator – JCB 3DX |  |  | 1 | 5.5 | 2.5 | 68.75% | HDPE Pipe 90 mm |  |  | RM | 320 | 60 | 22 | 358
Pipe Fitter |  |  | 6 | 5 | 5.3125 |  | Hydro Test Pump |  |  | 1 | 2.5 | 5.5 | 31.25% | CPVC Pipe & fittings |  |  | RM | 0 | 0 | 0 | 0
Mason – chambers & manholes |  |  | 6 | 6 | 6 |  | Threading & Grooving Machine |  |  | 2 | 9 | 7 | 56.25% | SWR / PVC Pipe 110 & 160 mm |  |  | RM | 240 | 0 | 0 | 240
Helper |  |  | 12 | 10 | 10.625 |  | Core Cutting Machine |  |  | 2 | 6 | 10 | 37.5% | RCC / SW pipe for UG drainage |  |  | RM | 180 | 40 | 14 | 206
Machine Operator |  |  | 2 | 2 | 2 |  | Drilling & Chasing Machines |  |  | 6 | 28 | 20 | 58.33% | Chamber covers, gully traps & frames |  |  | NOS | 18 | 4 | 1 | 21
Supervisor & PMC Staff |  |  | 3 | 3 | 3.375 |  | De-watering Pump & DG Set |  |  | 3 | 16 | 8 | 66.67% | Solvent cement, sealant & fasteners |  |  | LTR | 60 | 15 | 8 | 67
TOTAL WORKERS / MAN-DAYS |  |  | 39 | 34 | 35.8125 |  | TOTAL / AVERAGE |  |  | 15 | 67 | 53 | 55.83% | Balance = Opening + Received − Consumed · carry Balance forward as tomorrow's Opening on the INPUT sheet
9. QUALITY CONTROL & TESTS TODAY | [6 empty] | 10. HSE / SAFETY STATISTICS | [6 empty] | 11. DELAY / IDLE TIME LOG TODAY
Pressure test – UG water line 6 kg/cm² |  |  |  |  | Section-1 passed |  | Safe man-hours – today / cumulative |  |  |  |  | 290 / 5,180 |  | CAUSE (CATEGORY) |  |  |  | FROM | TO | HRS LOST | EOT
Slope / invert level check – drainage |  |  |  |  | 4 chambers verified |  | Days without LTI |  |  |  |  | 122 |  | Sleeves / cutouts not left in slab by civil (Client / Vendor) |  |  |  | 9:30 | 12:00 | 2.5 | Yes
Water tightness test of chambers |  |  |  |  | 3 taken, all OK |  | Excavation permits issued |  |  |  |  | 2 |  | Rain – trench work stopped (Weather) |  |  |  | 14:30 | 16:00 | 1.5 | Review
Bedding & backfill compaction test |  |  |  |  | 2 tests, 1 re-do |  | Confined space entry – chambers |  |  |  |  | 1 with gas test |  | Chamber cover consignment not received (Contractor) |  |  |  | 11:00 | 12:00 | 1 | No
Chlorination of tested water lines |  |  |  |  | Not yet due |  | Trench barricading & signage verified |  |  |  |  | Yes | [5 empty] | 0:00 | 0:00 |  | 0
NCRs open / closed today |  |  |  |  | 1 / 1 |  | Safety observations raised / closed |  |  |  |  | 4 / 3 |  | TOTAL HOURS LOST TODAY | [5 empty] | 5 | 1 EOT
12. DRAWINGS / RFI / MATERIAL APPROVALS PENDING | [10 empty] | 13. ISSUES & RISKS (open items)
REF. NO. |  | DESCRIPTION | [5 empty] | RAISED ON | AGEING | PENDING WITH | ISSUE / RISK DESCRIPTION | [6 empty] | SEVERITY |  | OWNER
RFI-055 |  | Toilet layout & fixture positions – approval | [5 empty] | 2026-07-22 | 9 | Consultant | ⚠ Sanitaryware & CP fitting make not approved – 10 week procurement risk | [6 empty] | Critical |  | Client
DWG-131 |  | UG drainage invert levels rev-1 | [5 empty] | 2026-07-19 | 12 | Consultant | ⚠ Sleeves and cutouts not provided by civil in cast slabs | [6 empty] | High |  | Contractor
MAR-049 |  | CPVC pipe & sanitaryware make approval | [5 empty] | 2026-07-17 | 14 | Client | ⚠ UG drainage invert level clash with the road profile at Chamber-9 | [6 empty] | High |  | Consultant
RFI-056 |  | STP tie-in point & discharge level | [5 empty] | 2026-07-28 | 3 | PMC | ⚠ Chamber cover consignment short by 8 nos. | [6 empty] | Medium |  | Contractor
14. TODAY'S HIGHLIGHTS | [10 empty] | 15. NEXT DAY PLAN
★ UG HDPE water line laid & jointed – 202 RM of 640 RM | [10 empty] | ➜ Continue UG water line – Chainage 210 to 270
★ UG drainage line completed up to Chamber-7 – 110 RM | [10 empty] | ➜ Drainage line Chamber-7 to Chamber-9 with invert check
★ Pressure test of water line Section-1 passed at 6 kg/cm² | [10 empty] | ➜ Backfilling of tested water line section
★ 4 nos. inspection chambers completed with covers | [10 empty] | ➜ Follow up sanitaryware make approval with client
16. DECISIONS / INSTRUCTIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
1. Approval of the sanitaryware and CP fitting make (MAR-049) – 10 week procurement lead time is at risk
2. Civil agency to provide the balance sleeves and cutouts in cast slabs – concealed piping cannot start
3. Confirmation of UG drainage invert levels at Chamber-9 (DWG-131) – excavation held at that stretch
Prepared By |  |  |  |  | Checked By |  |  |  |  | Approved By |  |  |  |  | Client Representative
Name / Sign / Date — Site Engineer – SPDC |  |  |  |  | Name / Sign / Date — QA/QC Engineer – SPDC |  |  |  |  | Name / Sign / Date — Project Manager – SPDC |  |  |  |  | Name / Sign / Date — For and on behalf of Client
Sharnam Project Development Consultants & Co. (SPDC), Vadodara ¦ Project Management Consultancy ¦ THIS SHEET IS ALL FORMULAS — enter data on the INPUT sheet ¦ A3 Landscape – Page 1 of 1

## INPUT
DAILY INPUT SHEET — PLUMBING, WATER SUPPLY & DRAINAGE PACKAGE
TYPE ONLY IN THE YELLOW CELLS ON THIS SHEET. The DASHBOARD sheet is the printed DPR — it is all formulas and must not be typed over. Fill top to bottom, then print the DASHBOARD to PDF.
1. PROJECT HEADER (change once at the start, then only the dates each day)
Project name | <Client / Project Name>
Project manager | <PMC Project Manager>
Contractor / vendor | <Executing Agency / PEB Vendor>
Location | <Plot / GIDC / District>
Prepared by | Site Engineer – SPDC (PMC)
Contract / PO reference | <Work Order No. & Date>
Contract completion date | 2026-09-30
Calendar / working hours | 6 Days / Week – 8 hrs |  |  | Shift hours drive man-days & utilization
Shift hours per day | 8 |  |  | Used for man-days and equipment utilization
Weather | Partly Cloudy, 32 °C
REPORT DATE | 2026-07-31
DATA DATE (cut-off) | 2026-07-31 |  |  | Every planned % is measured to this date
Report number | DPR/PLB-027
AC – certified / paid to date (₹ Lakh) | 5.4 |  |  | From the RA bill / cost report
Cumulative man-days upto previous day | 1180
Cumulative safe man-hours upto prev. day | 42150
Date of last LTI | 2026-03-31 |  |  | Days without LTI counts from here
2. QUANTITY PROGRESS (one row per BOQ / scope item — type today's quantity in the last column)
GROUP | DESCRIPTION OF ITEM |  | UNIT | SCOPE / BOQ QTY | RATE ₹ | START | FINISH | CUM QTY UPTO PREV. | QTY TODAY
PLB-10 | UG HDPE water line 90 mm with fittings |  | RM | 640 | 680 | 2026-07-10 | 2026-08-25 | 180 | 22
PLB-10 | UG sump, pump room piping & valves |  | LS | 1 | 480000 | 2026-08-15 | 2026-09-30 | 0 | 0
PLB-10 | Water meter, valves & masonry chambers |  | NOS | 16 | 12500 | 2026-07-20 | 2026-09-05 | 3 | 1
PLB-20 | CPVC piping 25 to 50 mm concealed |  | RM | 1450 | 420 | 2026-08-20 | 2026-10-15 | 0 | 0
PLB-20 | GI piping 40 to 80 mm exposed |  | RM | 620 | 860 | 2026-08-25 | 2026-10-10 | 0 | 0
PLB-20 | Overhead tank connections, valves & float |  | NOS | 12 | 9800 | 2026-09-20 | 2026-10-25 | 0 | 0
PLB-30 | SWR / PVC soil & waste pipe 110 mm |  | RM | 980 | 480 | 2026-08-20 | 2026-10-10 | 0 | 0
PLB-30 | Rainwater downtake pipe 160 mm |  | RM | 720 | 620 | 2026-09-01 | 2026-10-20 | 0 | 0
PLB-30 | UG drainage line with inspection chambers |  | RM | 540 | 2200 | 2026-07-15 | 2026-09-10 | 96 | 14
PLB-30 | Manholes, gully traps & covers |  | NOS | 26 | 16500 | 2026-07-25 | 2026-09-20 | 4 | 1
PLB-40 | WC, wash basin & urinal with fittings |  | NOS | 68 | 14500 | 2026-10-01 | 2026-11-15 | 0 | 0
PLB-40 | CP fittings, taps & health faucets |  | NOS | 120 | 3200 | 2026-10-10 | 2026-11-20 | 0 | 0
PLB-40 | Water cooler & drinking water stations |  | NOS | 8 | 42000 | 2026-11-01 | 2026-11-25 | 0 | 0
PLB-50 | Pressure testing & flushing of lines |  | RM | 3200 | 95 | 2026-10-15 | 2026-11-30 | 0 | 0
PLB-50 | STP tie-in, trial run & commissioning |  | LS | 1 | 750000 | 2026-11-15 | 2026-12-10 | 0 | 0
3. MANPOWER DEPLOYED TODAY
TRADE / CATEGORY |  | PLANNED NOS | ACTUAL NOS | HOURS WORKED
Plumber |  | 10 | 8 | 8.5
Pipe Fitter |  | 6 | 5 | 8.5
Mason – chambers & manholes |  | 6 | 6 | 8
Helper |  | 12 | 10 | 8.5
Machine Operator |  | 2 | 2 | 8
Supervisor & PMC Staff |  | 3 | 3 | 9
4. EQUIPMENT DEPLOYED TODAY
EQUIPMENT |  | QTY | WORKED HRS | IDLE HRS
Excavator – JCB 3DX |  | 1 | 5.5 | 2.5
Hydro Test Pump |  | 1 | 2.5 | 5.5
Threading & Grooving Machine |  | 2 | 9 | 7
Core Cutting Machine |  | 2 | 6 | 10
Drilling & Chasing Machines |  | 6 | 28 | 20
De-watering Pump & DG Set |  | 3 | 16 | 8
5. MATERIAL AT SITE
MATERIAL |  | UNIT | OPENING STOCK | RECEIVED TODAY | CONSUMED / ISSUED
HDPE Pipe 90 mm |  | RM | 320 | 60 | 22
CPVC Pipe & fittings |  | RM | 0 | 0 | 0
SWR / PVC Pipe 110 & 160 mm |  | RM | 240 | 0 | 0
RCC / SW pipe for UG drainage |  | RM | 180 | 40 | 14
Chamber covers, gully traps & frames |  | NOS | 18 | 4 | 1
Solvent cement, sealant & fasteners |  | LTR | 60 | 15 | 8
6. QUALITY CONTROL & TESTS TODAY
QUALITY / TEST PARAMETER |  | TODAY'S FIGURE
Pressure test – UG water line 6 kg/cm² |  | Section-1 passed
Slope / invert level check – drainage |  | 4 chambers verified
Water tightness test of chambers |  | 3 taken, all OK
Bedding & backfill compaction test |  | 2 tests, 1 re-do
Chlorination of tested water lines |  | Not yet due
NCRs open / closed today |  | 1 / 1
7. HSE / SAFETY STATISTICS
HSE PARAMETER |  | TODAY'S FIGURE
Safe man-hours – today / cumulative |  | 290 / 5,180
Days without LTI |  | 122
Excavation permits issued |  | 2
Confined space entry – chambers |  | 1 with gas test
Trench barricading & signage verified |  | Yes
Safety observations raised / closed |  | 4 / 3
8. DELAY / IDLE TIME LOG TODAY (enter clock times — hours are calculated)
CAUSE OF DELAY / IDLE TIME |  | CATEGORY | FROM | TO | EOT
Sleeves / cutouts not left in slab by civil |  | Client / Vendor | 9:30 | 12:00 | Yes
Rain – trench work stopped |  | Weather | 14:30 | 16:00 | Review
Chamber cover consignment not received |  | Contractor | 11:00 | 12:00 | No
9. DRAWINGS / RFI / MATERIAL APPROVALS PENDING (ageing is calculated)
REF. NO. | DESCRIPTION |  | RAISED ON | PENDING WITH
RFI-055 | Toilet layout & fixture positions – approval |  | 2026-07-22 | Consultant
DWG-131 | UG drainage invert levels rev-1 |  | 2026-07-19 | Consultant
MAR-049 | CPVC pipe & sanitaryware make approval |  | 2026-07-17 | Client
RFI-056 | STP tie-in point & discharge level |  | 2026-07-28 | PMC
10. ISSUES & RISKS (open items)
ISSUE / RISK DESCRIPTION |  |  | SEVERITY | OWNER
Sanitaryware & CP fitting make not approved – 10 week procurement risk |  |  | Critical | Client
Sleeves and cutouts not provided by civil in cast slabs |  |  | High | Contractor
UG drainage invert level clash with the road profile at Chamber-9 |  |  | High | Consultant
Chamber cover consignment short by 8 nos. |  |  | Medium | Contractor
11. TODAY'S HIGHLIGHTS
UG HDPE water line laid & jointed – 202 RM of 640 RM
UG drainage line completed up to Chamber-7 – 110 RM
Pressure test of water line Section-1 passed at 6 kg/cm²
4 nos. inspection chambers completed with covers
12. NEXT DAY PLAN
Continue UG water line – Chainage 210 to 270
Drainage line Chamber-7 to Chamber-9 with invert check
Backfilling of tested water line section
Follow up sanitaryware make approval with client
13. DECISIONS REQUIRED FROM CLIENT / CONSULTANT / VENDOR
Approval of the sanitaryware and CP fitting make (MAR-049) – 10 week procurement lead time is at risk
Civil agency to provide the balance sleeves and cutouts in cast slabs – concealed piping cannot start
Confirmation of UG drainage invert levels at Chamber-9 (DWG-131) – excavation held at that stretch
14. S-CURVE ACTUAL HISTORY (enter once per reporting period — today's point is automatic)
DATE | ACTUAL CUM % ON THAT DATE | NOTE
2026-07-01 | 0% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-06 | 1.2% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-11 | 3.001% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-16 | 5.202% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-21 | 6.675% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-26 | 6.675% | calculated on the S-CURVE CALC sheet — or type the % printed on that day's issued DPR
2026-07-31 | ◄ calculated on the DASHBOARD | TODAY — taken from the quantity table, do not type
2026-08-05 |  | leave blank until that date is reported
2026-08-10 |  | leave blank until that date is reported
2026-08-15 |  | leave blank until that date is reported
2026-08-20 |  | leave blank until that date is reported
2026-08-25 |  | leave blank until that date is reported
2026-08-30 |  | leave blank until that date is reported

## S-Curve Calc
S-CURVE CALCULATION — ACTUAL % ON EACH REPORTING DATE (PLUMBING)
Enter the CUMULATIVE quantity of each item as it stood on each reporting date (from that day's measurement book / issued DPR). The bottom row converts them into the weighted actual % for that date and feeds INPUT section 14 and the S-curve. Once a column is filled it never changes again.
SL | DESCRIPTION OF ITEM | UNIT | SCOPE QTY | WEIGHT-AGE % | 2026-07-01 | 2026-07-06 | 2026-07-11 | 2026-07-16 | 2026-07-21 | 2026-07-26 | 2026-07-31 | 2026-08-05 | 2026-08-10 | 2026-08-15 | 2026-08-20 | 2026-08-25 | 2026-08-30
1 | UG HDPE water line 90 mm with fittings | RM | 640 | 5.675% | 2026-07-01: 0; 2026-07-06: 36.32; 2026-07-11: 90.79; 2026-07-16: 157.37; 2026-07-21: 202; 2026-07-26: 202
2 | UG sump, pump room piping & valves | LS | 1 | 6.259% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
3 | Water meter, valves & masonry chambers | NOS | 16 | 2.608% | 2026-07-01: 0; 2026-07-06: 0.72; 2026-07-11: 1.8; 2026-07-16: 3.12; 2026-07-21: 4; 2026-07-26: 4
4 | CPVC piping 25 to 50 mm concealed | RM | 1450 | 7.941% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
5 | GI piping 40 to 80 mm exposed | RM | 620 | 6.953% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
6 | Overhead tank connections, valves & float | NOS | 12 | 1.533% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
7 | SWR / PVC soil & waste pipe 110 mm | RM | 980 | 6.134% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
8 | Rainwater downtake pipe 160 mm | RM | 720 | 5.821% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
9 | UG drainage line with inspection chambers | RM | 540 | 15.49% | 2026-07-01: 0; 2026-07-06: 19.78; 2026-07-11: 49.44; 2026-07-16: 85.7; 2026-07-21: 110; 2026-07-26: 110
10 | Manholes, gully traps & covers | NOS | 26 | 5.594% | 2026-07-01: 0; 2026-07-06: 0.9; 2026-07-11: 2.25; 2026-07-16: 3.9; 2026-07-21: 5; 2026-07-26: 5
11 | WC, wash basin & urinal with fittings | NOS | 68 | 12.86% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
12 | CP fittings, taps & health faucets | NOS | 120 | 5.007% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
13 | Water cooler & drinking water stations | NOS | 8 | 4.381% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
14 | Pressure testing & flushing of lines | RM | 3200 | 3.964% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
15 | STP tie-in, trial run & commissioning | LS | 1 | 9.78% | 2026-07-01: 0; 2026-07-06: 0; 2026-07-11: 0; 2026-07-16: 0; 2026-07-21: 0; 2026-07-26: 0
WEIGHTED ACTUAL % ON THAT DATE |  |  |  | 100% | 0% | 1.2% | 3.001% | 5.202% | 6.675% | 6.675% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
FORMULA: Actual % on a date = Σ [ item weightage × ( cumulative qty on that date ÷ scope qty ) ] — the same weighted calculation the DASHBOARD does for today, only using the quantities as they stood on that earlier date.
SHORTCUT: if the DPR was already issued on that date, simply type the Actual % printed on it over the green formula in INPUT section 14 — both routes give the same figure. NOTE: weightage is taken from the CURRENT rates, so if a rate is revised later, re-issued history will shift slightly; the figures on the DPRs already signed remain the record.

## Guide
HOW THIS FILE WORKS — PLUMBING DPR
| Two sheets only | INPUT — you type here, top to bottom, yellow cells only. DASHBOARD — the printed DPR, 100% formulas, never typed. Guide — this page.
| Daily routine | Open INPUT → change Report Date and Data Date → enter today's quantities, manpower, equipment, material, quality, HSE, delays, pending approvals, issues, highlights, next-day plan → open DASHBOARD → print to PDF.
| Adding / removing an item | Insert or delete a row inside the quantity block on INPUT and the same row position on DASHBOARD; every formula uses ranges, so totals follow.
| Weightage % | Scope Qty × Rate ÷ Σ(Scope Qty × Rate). Value weightage — always totals 100%.
| Planned % | IF(Data Date ≥ Finish, 100%, IF(Data Date < Start, 0%, (Data Date − Start + 1) ÷ (Finish − Start + 1))) — the programme prorated to the cut-off date.
| Days +/− | Finish − Data Date. Negative and red means the item is already past its programmed finish.
| Cum Qty To Date / Balance | Cum upto previous + Qty today · Scope Qty − Cum to date.
| % Complete | MIN(Cum Qty To Date ÷ Scope Qty, 1), shown with an in-cell data bar.
| Earned ₹ today | Qty today × Rate — the value of work done in the day, totalled in the KPI strip.
| Package Planned / Actual % | Σ(Weightage × Planned %) and Σ(Weightage × % Complete). These two totals drive the KPI strip, group summary, earned value block and S-curve.
| Status | Not Started / Completed / On Track (actual ≥ planned) / In Progress / Delay — colour coded.
| Group summary | SUMIFS of the weighted columns by group code ÷ that group's weightage.
| Earned value | BAC = Σ(Qty × Rate) ÷ 1,00,000 · PV = BAC × Planned % · EV = BAC × Actual % · SV = EV − PV · CV = EV − AC · CPI = EV ÷ AC · EAC = BAC ÷ CPI. Only AC is typed.
| Section 6 / 7 / 8 | Man-days = Actual Nos × hours ÷ shift hours · Utilization = Worked ÷ (Qty × shift hours) · Balance stock = Opening + Received − Consumed.
| Hours lost | (To − From) × 24 from the clock times on INPUT. EOT count is a COUNTIF of the Yes entries.
| Approval ageing | Data Date − Raised on; red beyond 7 days, and counted in the Project Health box.
| S-curve actual history | Actual % on any past date = Σ [ item weightage × (cumulative qty on that date ÷ scope qty) ]. The S-CURVE CALC sheet does this for you — enter each item's cumulative quantity as it stood on each reporting date and the bottom row gives the %, which flows into INPUT section 14. If that day's DPR was already issued, just type the Actual % from it instead.
| S-curve | Planned line = SUMPRODUCT of every item's weightage × its time-prorated fraction at each date — built entirely from the programme. Actual history comes from INPUT section 14; today's point is taken live from the quantity table.
| Paper | DASHBOARD is set to A3 landscape, fit to one page. Prints on A4 at about 70% if needed.
| Roll over to the next day | Save a copy with the new date. On INPUT: move Cum Qty To Date into 'Cum qty upto prev.', move material Balance into Opening, clear Qty Today, update the cumulative man-days and man-hours.