## Summary
|  | Daily Progress Report | [116 empty] | 2026-07-14
Name of Project |  | Development Work of Dormitory Building at Santej | [116 empty] | Project Start | 2025-07-03
Name of Client |  | Arvind Limited | [116 empty] | Project Finish | 2026-02-28
Principle Consultant |  | A.K. Bhavsar | [116 empty] | No. of Days Completed | 240
PMC |  | Sharnam Project Development Consultants & Co. | [116 empty] | No of Days Remaining | -136
Sr.No. | Location | Descriptions | Quantity | [115 empty] | Project Status Overview
[6 empty] | Planned Qty | [44 empty] | Achieved Qty | [31 empty] | Planned Qty
|  |  | Total | Unit | Previous | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | Achieved Qty % | Cumalative Quantity (Till date) | Progress % | Remarks
1 | Up to Plinth | Excavation | 1826.1 | CUM | 1731 | 0 | 80 | 80 | 500 | 350 | 0 | 0 | 0 | 110 | 65 | 0 | 300 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | 0 | 0 | 482 | 346 | 0 | 0 | 0 | 103 | 60 | 0 | 293 | 447 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [6 empty] | 0 | 1731 | 94.79%
|  | Yellow Soil Filling | 1356.08 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Rubble Soling | 150.88 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Footing PCC | 91.31 | CUM | 1 | 0 | [7 empty] | 0 | 15 | 16 | 20 | 18 | 0 |  | 0 | 25 | 18 | 0 | 6 | 5 | 10 | 7 | 3.5 | 0 | 0 | 0 | 5 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.92 | 6.5 | 0 | 11.5 | 0 | 0 | 0 | 6 | 0 | 0 | 5.5 | 0 | 9.2 | 6.65 | 3 | 0 | 0 | 0 | 6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 25 | 18 | 0 | 6 | 5 | 10 | 7 | 3.5 | 0 | 0 | 0 | 5 | 0 | [6 empty] | 120 | 7 | 7.666%
|  | Footing Shuttering | 441.908 | SQM | 203.94 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 20 | 20 | 35 | 20 | 0 | 20 | 30 | 20 | 20 | 13 | 25 | 35 | 40 | 35 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5 | 27.5 | 23.65 | 6.84 | 0 | 18.88 | 29.05 | 7.58 | 5.75 | 12.42 | 12 | 34.42 | 12.35 | 15.1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 20 | 35 | 20 | 0 | 20 | 30 | 20 | 20 | 13 | 25 | 35 | 40 | 35 | 40 | [6 empty] | 43.1429 | 219.04 | 49.57% | Steel Work not completed
|  | Footing RCC | 292.764 | CUM | 147.91 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 13 | 15 | 25 | 20 | 0 | 12 | 18 | 6 | 10 | 14 | 20 | 25 | 30 | 25 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 16 | 0 | 18.1 | 0 | 11.75 | 13.2 | 6.5 | 0 | 12.82 | 22.54 | 20.5 | 16 | 8.35 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 15 | 25 | 20 | 0 | 12 | 18 | 6 | 10 | 14 | 20 | 25 | 30 | 25 | 30 | [6 empty] | 33.4 | 156.26 | 53.37% | Steel Work not completed
|  | Padestal Upto GB Shuttering | 243.24 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0% |  | 23.62
|  | Padestal Upto GB RCC | 23.96 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Floor PCC | 69.18 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Ground beam PCC | 14.25 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Plinth beam PCC | 20.25 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Pesestal up to plinth Shuttering | 457.66 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Pesestal up to plinth concrete | 1375.74 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Floor trimix | 77.55 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Floor trimix Shuttering | 15.3 | SQM | 0 | [23 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Ground beam Shuttering | 178 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Ground beam concrete | 30.13 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0% |  |  | 525
|  | Plinth beam Shuttering | 326.02 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Plinth beam concrete | 37.492 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
|  | Plaster up to plinth | 134.58 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | [8 empty] | 0%
2 | Ground Floor | Plinth to GF slab column shuttering | 222.32 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Plinth to GF slab column concrete | 18.7162 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF beam shuttering | 406.332 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF beam concrete | 46.7282 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF slab shuttering | 850.3968 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF slab concrete | 123.1774 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF staircase shuttering | 57.0508 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF staircase concrete | 6.9402 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF Lintel shuttering | 135.444 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF Lintel concrete | 7.788 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Brick masonary uo to plinth | 125.7438 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Brick masonary GF | 74.1138 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF partition wall | 1158.68 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF plaster | 4320.5816 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF-vitrified flooring | 841.1628 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | GF-vitrified skirting | 1859.2 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
3 | First Floor | First floor column shuttering | 222.32 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor column concrete | 18.7162 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor beam shuttering | 406.332 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor beam concrete | 46.7282 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor slab shuttering | 850.3968 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floorslab concrete | 123.1774 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor staircase shuttering | 57.0508 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor staircase concrete | 6.9402 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor Lintel shuttering | 135.444 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor Lintel concrete | 7.788 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor Brick masonary | 125.7438 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor Brick masonary | 74.1138 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor partition wall | 1158.68 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor Plaster | 134.58 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor plaster | 4320.5816 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor-vitrified flooring | 841.1628 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | First floor-vitrified skirting | 1859.2 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
4 | Second Floor | Second floor column shuttering | 222.32 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor column concrete | 18.7162 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor beam shuttering | 406.332 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor beam concrete | 46.7282 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor slab shuttering | 850.3968 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floorslab concrete | 123.1774 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor staircase shuttering | 57.0508 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor staircase concrete | 6.9402 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor Lintel shuttering | 135.444 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor Lintel concrete | 7.788 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor Brick masonary | 125.7438 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor Brick masonary | 74.1138 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor partition wall | 1158.68 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor Plaster | 134.58 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor plaster | 4320.5816 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor-vitrified flooring | 841.1628 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Second floor-vitrified skirting | 1859.2 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
5 | Third Floor | Third floor column shuttering | 222.32 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor column concrete | 18.7162 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor beam shuttering | 406.332 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor beam concrete | 46.7282 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor slab shuttering | 850.3968 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floorslab concrete | 123.1774 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor staircase shuttering | 57.0508 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor staircase concrete | 6.9402 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor Lintel shuttering | 135.444 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor Lintel concrete | 7.788 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor Brick masonary | 125.7438 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor Brick masonary | 74.1138 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor partition wall | 1158.68 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor Plaster | 134.58 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor plaster | 4320.5816 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor-vitrified flooring | 841.1628 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Third floor-vitrified skirting | 1859.2 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
6 | Fourth Floor | Fourth floor column shuttering | 222.32 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor column concrete | 18.7162 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor beam shuttering | 406.332 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor beam concrete | 46.7282 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor slab shuttering | 850.3968 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floorslab concrete | 123.1774 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor staircase shuttering | 57.0508 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor staircase concrete | 6.9402 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor Lintel shuttering | 135.444 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor Lintel concrete | 7.788 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor Brick masonary | 125.7438 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor Brick masonary | 74.1138 | CUM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor partition wall | 1158.68 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor Plaster | 134.58 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor plaster | 4320.5816 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor-vitrified flooring | 841.1628 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Fourth floor-vitrified skirting | 1859.2 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
7 | Terrace | Parapet wall | 209.412 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
|  | Waterproofing | 841.1628 | SQM | 0 | 0 | [7 empty] | 0 | 0 | 0 | [34 empty] | 0 | 0 | [7 empty] | 0 | 0 | [30 empty] | 0 | 0 | [24 empty] | #REF! | #REF!
Tomorrow Work Plan
| Sr. No. | Desciption
| 1 | Shuttering Work of Footing
| 2 | Steel work of footing, columns & beam
| 3 | Steel Bending and binding Work For Columns
| 4 | Footing Casting
| 5 | Padestal Starter Work
Sr. No. | Project Summary Report (Buildingwise)
1 | Up to Plinth | 10.27%
2 | Ground Floor | #REF!
3 | First Floor | #REF!
4 | Second Floor | #REF!
5 | Third Floor | #REF!
6 | Fourth Floor | #REF!
7 | Terrace | #REF!

## Manpower, Equipments, Materials
Manpower, Equipments & Material Details | [11 empty] | Date : | 2026-07-14
MANPOWER & MACHINERIES
MANPOWER STATUS |  |  |  |  | CONSTRUCTION EQUIPMENTS STATUS |  |  |  | Daily Material Details |  |  |  |  | Daily Material Consumption
Sr. No. | Description |  |  | Nos. | Sr. No. | Equipments |  | Nos. | Sr. No. | Description |  | Unit | Nos. | Sr. No. | Description |  | Unit | Nos.
1 | Staff (PMC) |  |  | 1 | 1 | JCB Backhoe |  | 0 | 1 | Cement |  | Bag No. | 600 | 1 | Cement |  | Bag No. | 29 |  |  |  |  | 0
2 | Staff (Civil Team) |  |  | 2 | 2 | Tractor |  | 0 | 2 | Steel |  | MT | 0 | 2 | Steel |  | MT | 1.13 | Steel
3 | Staff (Electrical Team) |  |  | 0 | 3 | Hitachi Excavator |  | 0 | 3 | Aggregate |  | MT | 0 | 3 | Aggregate |  | MT | 8.088 | 8 | 0.375 |  | 0.375
4 | Workers (Civil Team) |  |  |  | 4 | Ajex |  | 1 | 4 | Sand |  | MT | 0 | 4 | Sand |  | MT | 5.01 | 10 | 0.15 |  | 0.15
| Skilled |  |  | 23 | 5 | Baby Roller/Plate Compactor |  | 0 | 5 | Blocks |  | Nos. | 0 | 5 | Blocks |  | Nos. | 0 | 12 | 0 |  | 0
| Unskilled |  |  | 19 | 6 | Heavy Roller |  | 0 | 6 | Hume Pipe (NP3) |  | RMT | 0 | 6 | Hume Pipe (NP3) |  | RMT | 0 | 16 | 0 |  | 0
| Driver, Operator, Helper |  |  | 1 | 7 | Farana |  | 0 | Cumulative Material Details |  |  |  |  | Available Material Stock |  |  |  |  | 20 | 4.15 |  | 4.15
5 | Workers (Electrical Team) |  |  |  | 8 | Hydra |  | 0 | 1 | Cement |  | Bag No. | 1200 | 1 | Cement |  | Bag No. | 622
| Skilled |  |  | 0 | 9 | Hyva |  | 0 | 2 | Steel |  | MT | 33.94 | 2 | Steel |  | MT | 4.675
[9 empty] | 3 | Aggregate |  | MT | 206.14 | 3 | Aggregate |  | MT | 47.31
[9 empty] | 4 | Sand |  | MT | 158.29 | 4 | Sand |  | MT | 53.76
Total |  |  |  | 46 |  | Total |  | 1 | 5 | Blocks |  | Nos. | 0 | 5 | Blocks |  | Nos. | 0
Work Tracker
2026-07-14
Sr | Activity | Total Qty (Nos / Rmt/Smt) |  |  | Achieved |  | Balance Qty |  | Target date |  |  | Remaining days |  |  |  | Per day Target
1 | Footing First step | 47 |  |  | 26 |  | 21 |  | 2025-08-19 |  |  | -329 |  |  |  | -0.06383
2 | Footing Second step | 47 |  |  | 24 |  | 23 |  | 2025-08-19 |  |  | -329 |  |  |  | -0.069909
3 | Pedestal | 96 |  |  | 0 |  | 96 |  | 2025-08-24 |  |  | -324 |  |  |  | -0.2963
4 | Back filling | 892 |  |  | 0 |  | 892 |  | 2025-08-26 |  |  | -322 |  |  |  | -2.7702
5 | Ground Beam | 243 |  |  | 0 |  | 243 |  | 2025-08-31 |  |  | -317 |  |  |  | -0.76656
6 | Pedestal above GB | 96 |  |  | 0 |  | 96 |  | 2025-09-01 |  |  | -316 |  |  |  | -0.3038
7 | Masonry | 224.3 |  |  | 0 |  | 224.3 |  | 2025-09-03 |  |  | -314 |  |  |  | -0.71433
8 | Plinth filling | 892 |  |  | 0 |  | 892 |  | 2025-09-05 |  |  | -312 |  |  |  | -2.859 |  |  |  |  | 2.25
9 | Plinth beam | 392 |  |  | 0 |  | 392 |  | 2025-09-08 |  |  | -309 |  |  |  | -1.2686
10 | Soiling | 892 |  |  | 0 |  | 892 |  | 2025-09-10 |  |  | -307 |  |  |  | -2.9055
11 | PCC | 846 |  |  | 0 |  | 846 |  | 2025-09-12 |  |  | -305 |  |  |  | -2.7738
9.3333
[18 empty] | 2025-07-14 | 2025-07-22
|  |  | M10 | [5 empty] | M25 | [8 empty] | 2025-09-23 | 2026-07-14
|  |  | cement | Wt. per cmt | Cmt | Total |  |  | cement | Wt. per cmt | Cmt | Total | [5 empty] | 71 | 357
|  |  | cement | 4.2 | 6 | 25.2 |  |  | cement | 7.3 | 5.5 | 40.15
|  |  | aggr | 1.348 | 6 | 8.088 |  |  | aggr | 1.2 | 5.5 | 6.6
|  |  | sand | 0.835 | 6 | 5.01 |  |  | sand | 0.743 | 5.5 | 4.0865

## Concern Register
Daily Concern Register
Sr.No. | Building | Areas of Concern | Impact | Responsibility | Target Date | Action to be taken | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | As on date update
1 | General | The mobilization activities of the appointed civil contractor are progressing at a significantly slower pace than originally planned. Critical tasks such as site establishment, manpower deployment, material procurement, machinery mobilization, safety arrangements, and initial site clearance are either delayed or not being executed efficiently, potentially impacting the timely commencement of construction works. | Medium | Bhavna Infra | 2025-07-22 | Immediately review and assess the contractor’s mobilization plan against agreed timelines. | 2025-07-22: Open; 2025-07-23: Open; 2025-07-24: Open; 2025-07-25: Open; 2025-07-26: Open; 2025-07-27: Open; 2025-07-28: Open; 2025-07-29: Open; 2025-07-30: close; 2025-07-31: close | close | High
2 | General | Ready Mix Concrete (RMC) mix design has been submitted for your review and approval. The design includes detailed proportions for each grade of concrete as per project specifications and relevant IS codes. Additionally, the Weigh Batching Calibration has been completed and relevant calibration certificates have been enclosed. The calibration ensures the accuracy of batching equipment, and was conducted in accordance with standard procedures to maintain the quality and consistency of the concrete mix. | Low | Bhavna Infra | 2025-07-22 | Review the submitted RMC mix design for compliance with project specifications and IS codes. Verify the enclosed weigh batching calibration certificates. | 2025-07-22: Open; 2025-07-23: Open; 2025-07-24: Open; 2025-07-25: Open; 2025-07-26: Close; 2025-07-27: Close; 2025-07-28: Close; 2025-07-29: Close; 2025-07-30: Close; 2025-07-31: close | Close | Medium
1 | General | 3-phase electrical power supply is required at the site to facilitate ongoing construction and execution activities. Kindly arrange for the same on priority to avoid delays in project progress. | High | Arvind Limited | 2025-07-22 | Arrange the 3-phase power supply at the project site. | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Open | Low
4 | General | Updated and approved drawings are required for site execution. Without the latest revisions, construction activities may face delays or errors. All recent changes must be reflected in the issued drawings to ensure accurate implementation as per the design intent. Please ensure timely availability of updated drawings to proceed with the work efficiently. | Low | A.K.Bhavsar | 2025-07-22 | Expedite the preparation and approval of updated drawings incorporating all recent revisions. | 2025-07-22: Open; 2025-07-23: close; 2025-07-24: close; 2025-07-25: close; 2025-07-26: Close; 2025-07-27: Close; 2025-07-28: Close; 2025-07-29: Close; 2025-07-30: Close; 2025-07-31: Close | Close
5 | General | labour colony is required at the site to accommodate the workforce involved in construction activities. This facility should include adequate housing, sanitation, drinking water, electricity, and waste disposal arrangements as per applicable labour welfare norms and statutory compliance | Low | Bhavna Infra | 2025-07-22 | Identify Suitable Location: Allocate a designated area within or near the project site for the labour colony. | 2025-07-22: Open; 2025-07-23: Open; 2025-07-24: Open; 2025-07-25: Open; 2025-07-26: Open; 2025-07-27: Open; 2025-07-28: Open; 2025-07-29: Close; 2025-07-30: Close; 2025-07-31: Close | Close
2 | General | To ensure adherence to the project’s technical specifications, quality standards, and timely verification of construction materials and workmanship, a testing laboratory is required to be established on-site. This facility will support the Quality Control (QC) process by enabling immediate sampling and testing of materials such as concrete, cement, aggregates, bricks, steel, and water. | Low | Bhavna Infra | 2025-07-22 | Set up an on-site testing lab with required equipment and staff to ensure timely QC of materials like concrete, cement, aggregates, bricks, steel, and water as per project standards | 2025-07-22: Open; 2025-07-23: Open; 2025-07-24: Open; 2025-07-25: Open; 2025-07-26: Open; 2025-07-27: Open; 2025-07-28: Open; 2025-07-29: Open; 2025-07-30: Open; 2025-07-31: Open; 2025-08-01: close | close
7 | General | It has been observed that the necessary shuttering materials required for upcoming PCC and RCC footing concreting activities have not yet been supplied in full, nor properly stacked at the designated storage area at the site.The delay in material availability and improper site organization may affect the concrete pouring schedule and the quality of shuttering alignment. Timely supply and organized stacking is essential to avoid work disruption and ensure efficient progress. | Medium | Bhavna Infra | 2025-07-23 | Set up Site store for material stacking and supply shuttering materials at site. | 2025-07-22: -; 2025-07-23: Open; 2025-07-24: Open; 2025-07-25: Open; 2025-07-26: Open; 2025-07-27: Open; 2025-07-28: Open; 2025-07-29: close; 2025-07-30: close; 2025-07-31: close | close
8 | General | As observed men power available on site is not sufficient contractor is instructed to deploy remaining manpower and submit treadwise men power planning for every activity. | High | Bhavna Infra | 2025-07-29 | Deploy neseccery menpoer and submit planning | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: close; 2025-07-31: close | close
2 | General | As Vendor has already informed about using AJAX FIORI for concreting work with site mix. Nominal mix design shall required and will be approved based on compliance with IS standards, using either the ACT result or the 7- day compressive strength test, whichever is applicable. Also Calibration report is required of the Ajax Fiori | High | Bhavna Infra | 2025-07-29 | submit nominal mix design and calibration report | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: Open; 2025-07-31: Open; 2025-08-01: Open; 2025-08-02: Open; 2025-08-03: Open; 2025-08-04: close | close
10 | General | Detailed Project Schedule has been already shared with vendor. Vendor has to review and submit signed off copy of the shared schedule with in 1 days | High | Bhavna Infra | 2025-07-29 | Review and submit Detailed project schedule | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: close; 2025-07-31: close | close
11 | General | Dressing And Compaction work should be started as early as possible and should be completed in 1 days | High | Bhavna Infra | 2025-07-29 | Complete activity in said timeline | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: close; 2025-07-31: close | close
12 | General | Use of unauthorized land whether for parking, storage, movement of machinery, or any other activity is strictly prohibited and may lead to serious legal and contractual consequences.Clearly demarcate the approved site boundaries using visible markers, barricades, or fencing. Inform and guide all workers, operators, and staff about the limits of the work area. | Medium | Arvind Limited | 2025-07-29 | Marking out client plot area | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: close; 2025-07-31: close | close
12 | General | Sanitation facilities for workers and staff at the project site are required to ensure a clean, hygienic, and safe working environment. Adequate toilets, baths, and urinals must be provided and maintained for all personnel. | Low | Arvind Limited | 2025-07-29 | Already Supplied by client at site | 2025-07-28: -; 2025-07-29: close; 2025-07-30: close; 2025-07-31: close | close
13 | General | construction of the approach road using debris for smooth workflow and material transportation is within the client’s scope. | Low | Arvind Limited | 2025-07-29 | Make temporary approach road by dumping building waste | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: close; 2025-07-31: close | close
2 | General | Ground beam and plinth beam drawings are required for making BBS and procuring steel. Consultant has informed of sharing drawing witin two days | Medium | AK Consultant | 2025-07-29 | Required drawing needs to shared in said timeline | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: Open; 2025-07-31: Open; 2025-08-01: Open; 2025-08-02: Open; 2025-08-03: Open; 2025-08-04: Open; 2025-08-05: Open; 2025-08-06: Open; 2025-08-07: Open; 2025-08-08: Close | Close
15 | General | Steel order has been placed already and will be delivered in oney day | Medium | Bhavna Infra | 2025-07-29 | Make sure oredered steel get delivered on time | 2025-07-28: -; 2025-07-29: Open; 2025-07-30: close; 2025-07-31: close | close
2 | General | As our footing work activity is already delayed contractor should makeup the lost time by increasing menpower and productivity. | High | Bhavana Infra | 2025-08-31 | Detailed delay mitigation plan shoud be developed and followed strictly to recover the loss time and makeup the scheduled time | 2025-08-04: -; 2025-08-05: Open; 2025-08-06: Open; 2025-08-07: Open; 2025-08-08: Open; 2025-08-09: Open; 2025-08-10: Open; 2025-08-11: Open; 2025-08-12: Open; 2025-08-13: Open; 2025-08-14: Open; 2025-08-15: Open; 2025-08-16: Open; 2025-08-17: Open; 2025-08-18: Open | Open
3 | General | As excavated area is deep as 3 meters proper hard barricading should be required for safety of all livelyhood | High | Bhavana Infra | 2025-08-08 | Provide Barricading of sheets or any similar material | 2025-08-04: -; 2025-08-05: Open; 2025-08-06: Open; 2025-08-07: Open; 2025-08-08: Open; 2025-08-09: Open; 2025-08-10: Open; 2025-08-11: Open; 2025-08-12: Open; 2025-08-13: Open; 2025-08-14: Open; 2025-08-15: Open; 2025-08-16: Open; 2025-08-17: Open; 2025-08-18: Open | Open
4 | General | Raw materials should be stacked at proper cleaned area. | High | Bhavana Infra | 2025-08-08 | Plum concrete should be casted for raw materials stacking | 2025-08-05: -; 2025-08-06: -; 2025-08-07: Open; 2025-08-08: Open; 2025-08-09: Open; 2025-08-10: Open; 2025-08-11: Open; 2025-08-12: Open; 2025-08-13: Open; 2025-08-14: Open; 2025-08-15: Open; 2025-08-16: Open; 2025-08-17: Open; 2025-08-18: Open | Open
5 | General | A distribution box shall be securely fixed and installed with all necessary accessories. All connections to equipment must be made using appropriate pin-top plugs to ensure safety, security, and compliance with electrical standards | High | Bhavana Infra | 2025-08-15 | DB And Pin tops should be provided | 2025-08-07: -; 2025-08-08: -; 2025-08-10: -; 2025-08-11: Open; 2025-08-12: Open; 2025-08-13: Open; 2025-08-14: Open; 2025-08-15: Open; 2025-08-16: Open; 2025-08-17: Open; 2025-08-18: Open | Open
6 | General | The scheduled target date for completion of the Ground Floor slab RCC work is set for 19th September. However, Bhavana Infra has been instructed to expedite the work and aim for completion by 10th September. | High | Bhavana Infra | 2025-09-10 | Increase manpower and productivity to meet the target | 2025-08-10: -; 2025-08-11: -; 2025-08-12: Open; 2025-08-13: Open; 2025-08-14: Open; 2025-08-15: Open; 2025-08-16: Open; 2025-08-17: Open; 2025-08-18: Open | Open

## Hinderance Register
Hinderance Register
Sr. No | Description of Hindrance | Location | Work affected | Correspondence | Type of Hindrance | Date of Occurrence | Date Resolved | No. of Days | Critical Activity affected | Baseline Start Date | Schedule Impact | Delay Type | Actual Impact | Accountable | Status | Description of Resolution | Remarks
1 | Non-availability of updated and approved drawings is causing delays in construction activities and may lead to execution errors due to outdated design references. Immediate action is required to provide the latest drawings. | Infra | Site activity | On mail | Work in Progress | 2025-07-22 | 2025-07-23 | 1 | Constrcution Activity | 2025-07-22 | 10 days | Non-overlapping Delay |  | Client | Resolved | Updated Drawings Received |  | #REF! | #REF!
1 | Non availability of permanent power connection for 3 phase power supply and borewell for construction purposes at site may affect overall activities at site. Immediate action reqquired for permanent power supply and borewell construction. | Infra | Site activity | on site | - | 2025-07-28 |  |  | Constrcution Activity | 2025-07-28 | 12 Days | Non-overlapping Delay |  | Client | Open
2 | Container office at site for office and documentation works required at urgent basis. Immediate action requred to setup office at site. | site office | documentation | on site | - | 2025-07-28 | 2025-08-04 |  | documentation | 2025-07-28 | 2 days | Non-overlapping Delay |  | Client | Resolved
2 | Ground beam and plinth beam drawings are required for making BBS and procuring steel. Drawings are demanded from last 15 days its required on urgent basis | Infra | Steel Procurement & Site activity | Consultant | - | 2025-08-05 |  |  | Constrcution Activity | 2025-08-05 | 2 days | Non-overlapping Delay |  | consultant | Resolved
2 | unavailability Of required menpower at site can lead to delay in works and impacting schedule. Immediate required menpower should be suppiled by contractor | Infra | Site activity | on site | - | 2025-08-18 |  |  | Constrcution Activity | 2025-08-17 | 5 Days | Non-overlapping Delay |  | Contractor | Open
3 | as instructed before the detailed delay mitigation plan shoud be developed and needs to submit by contractor. As it still yet receive from contractor | Infra | Site activity | on site | - | 2025-08-18 |  |  | Constrcution Activity | 2025-08-17 | 2 Days | Non-overlapping Delay |  | Contractor | Open
[12 empty] | Overlapping Delay |  |  | Open
[12 empty] | Non-overlapping Delay |  |  | Resolved
0

## Daily Progress Dashoard
Daily Progress Dashboard

## Site Photographs
Site Photographs |  | Date : | 2026-07-14
Steel Work | Shuttering Work |  |  |  | Image Size Reference
[5 empty] | Height | 5.12 cm
[5 empty] | Width | 9.55 cm
|  |  |  | steel work | 12.5
|  |  |  | shuttering | 12.5
12.5
12.5
Curing Work | Slump Test
Footing Casting | PCC Casting
PCC Marking Checking | PCC Marking