## Dashboard
Drawing Register Dashboard - Week #
Building | Discipline | Count of Sr # | Discipline | Count of Sr # | Critical Drawing | Count of Sr #
Tower 1 | Architecture | 3 | Architecture | 13 | No | 13
| MEPF | 5 | MEPF | 13 | Yes | 28
| Structural | 6 | Structural | 15
Tower 2 | Architecture | 4
| MEPF | 2
| Structural | 4
Tower 3 | Architecture | 4
| MEPF | 5
| Structural | 3
Tower 4 | Architecture | 1
| MEPF | 1
| Structural | 1
Tower 5 | Architecture | 1
| Structural | 1
Delay Responsibility | Sum of Submission Delay (Days)
Architecture Consultant | -32
Consultant | -44
MEPF Consultant | -19
Strcutural Consultant | -2
Structural Consultant | -31
Consultant Name | Count of Sr #
Design Consultants Ltd | 13
MEP Design Associates | 7
MEPF Design Associates | 6
Structural Consultants Ltd | 15
Client Logo

## Master Drawing Register
Master Drawing Register
Sr # | Project Package | Building | Discipline | Drawing Number | Drawing Title | Drawing Type | Consultant Name | Revision Number | Revision Date | Revision Description | Latest Revision | Planned Submission Date | Actual Submission Date | Submission Delay (Days) | Delay Responsibility | Issued To | Issue Date | No. of Copies | Critical Drawing | Remarks
1 | Package A | Tower 1 | Architecture | AR-101 | Typical Floor Plan | Good For Construction (GFC) | Design Consultants Ltd | R2 | 2025-01-10 | Revised layout as per client comments | Yes | 2025-01-03 | 2025-01-05 | -2 | Strcutural Consultant | Main Contractor | 2025-01-16 | 2 | Yes | Issued to site
2 | Package A | Tower 1 | Structural | ST-201 | Footing Layout Basement | Tender Drawings | Structural Consultants Ltd | R1 | 2025-01-12 | Initial submission | Yes | 2025-01-08 | 2025-01-10 | -2 | Architecture Consultant | PMC / Client |  | 0 | Yes | Critical for foundation work
3 | Package A | Tower 1 | Architecture | AR-103 | Staircase Details | Shop Drawing | Design Consultants Ltd | R0 | 2025-01-12 | Initial submission | Yes | 2025-01-10 | 2025-01-12 | -2 | Consultant | PMC / Client | 2025-01-18 | 0 | No | Under review earlier
4 | Package A | Tower 1 | Structural | ST-201 | Footing Layout Basement | Detailed Design (DD) Drawings | Structural Consultants Ltd | R1 | 2025-01-12 | Initial submission | Yes | 2025-01-08 | 2025-01-10 | -2 | Consultant | PMC / Client |  | 0 | Yes | Critical for foundation work
5 | Package A | Tower 1 | Structural | ST-202 | Column Layout Basement | Concept Drawings | Structural Consultants Ltd | R2 | 2025-01-15 | Revised grid alignment | Yes | 2025-01-10 | 2025-01-13 | -3 | Consultant | Main Contractor | 2025-01-20 | 2 | Yes | —
6 | Package A | Tower 1 | Structural | ST-203 | Beam Reinforcement Details | Detailed Design (DD) Drawings | Structural Consultants Ltd | R0 | 2025-01-18 | Initial submission | Yes | 2025-01-15 | 2025-01-18 | -3 | Consultant | PMC / Client |  | 0 | Yes | Under approval
7 | Package A | Tower 1 | MEPF | MEP-301 | HVAC Layout Typical Floor | Good For Construction (GFC) | MEP Design Associates | R1 | 2025-01-14 | Revised routing | Yes | 2025-01-10 | 2025-01-14 | -4 | Consultant | Main Contractor | 2025-01-22 | 2 | Yes | —
8 | Package A | Tower 1 | MEPF | MEP-302 | Electrical Lighting Layout | Detailed Design (DD) Drawings | MEP Design Associates | R2 | 2025-01-16 | Revised lighting levels | Yes | 2025-01-12 | 2025-01-15 | -3 | Consultant | Main Contractor | 2025-01-24 | 2 | No | —
9 | Package A | Tower 1 | MEPF | MEP-303 | Plumbing Typical Floor | Tender Drawings | MEP Design Associates | R1 | 2025-01-18 | Initial issue | Yes | 2025-01-15 | 2025-01-18 | -3 | Consultant | Main Contractor | 2025-01-25 | 2 | No | —
10 | Package A | Tower 2 | Architecture | AR-201 | Typical Floor Plan | Tender Drawings | Design Consultants Ltd | R1 | 2025-01-20 | Initial submission | Yes | 2025-01-18 | 2025-01-20 | -2 | Consultant | PMC / Client |  | 0 | Yes | Under review
11 | Package A | Tower 2 | Architecture | AR-202 | Elevation North Side | Schematic Drawings | Design Consultants Ltd | R2 | 2025-01-25 | Revised façade treatment | Yes | 2025-01-22 | 2025-01-24 | -2 | Consultant | Main Contractor | 2025-01-30 | 2 | No | —
12 | Package A | Tower 2 | Structural | ST-301 | Foundation Layout | Good For Construction (GFC) | Structural Consultants Ltd | R1 | 2025-01-22 | Initial submission | Yes | 2025-01-20 | 2025-01-22 | -2 | Consultant | PMC / Client |  | 0 | Yes | Critical activity
13 | Package A | Tower 2 | Structural | ST-302 | Slab Reinforcement | Tender Drawings | Structural Consultants Ltd | R0 | 2025-01-26 | Initial submission | Yes | 2025-01-25 | 2025-01-26 | -1 | Consultant | PMC / Client |  | 0 | Yes | —
14 | Package A | Tower 2 | MEPF | MEP-401 | Fire Fighting Layout | Shop Drawing | MEP Design Associates | R1 | 2025-01-24 | Initial issue | Yes | 2025-01-22 | 2025-01-24 | -2 | Consultant | Main Contractor | 2025-01-30 | 2 | Yes | Fire NOC related
15 | Package B | Tower 3 | Architecture | AR-301 | Typical Floor Plan | Detailed Design (DD) Drawings | Design Consultants Ltd | R3 | 2025-02-01 | Revised after site feedback | Yes | 2025-01-28 | 2025-01-30 | -2 | Consultant | Main Contractor | 2025-02-05 | 2 | Yes | —
16 | Package B | Tower 3 | Architecture | AR-302 | Staircase Details | Concept Drawings | Design Consultants Ltd | R0 | 2025-02-03 | Initial submission | Yes | 2025-02-01 | 2025-02-03 | -2 | Consultant | PMC / Client |  | 0 | No | —
17 | Package B | Tower 3 | Structural | ST-401 | Column Layout Typical | Detailed Design (DD) Drawings | Structural Consultants Ltd | R1 | 2025-02-02 | Initial issue | Yes | 2025-01-30 | 2025-02-02 | -3 | Consultant | Main Contractor | 2025-02-08 | 2 | Yes | —
18 | Package B | Tower 3 | Structural | ST-402 | Beam Layout Typical | Good For Construction (GFC) | Structural Consultants Ltd | R0 | 2025-02-05 | Initial submission | Yes | 2025-02-03 | 2025-02-05 | -2 | Consultant | PMC / Client |  | 0 | Yes | —
19 | Package B | Tower 3 | MEPF | MEP-501 | Electrical Riser Diagram | Detailed Design (DD) Drawings | MEP Design Associates | R1 | 2025-02-04 | Initial issue | Yes | 2025-02-02 | 2025-02-04 | -2 | Consultant | Main Contractor | 2025-02-10 | 2 | No | —
20 | Package B | Tower 3 | MEPF | MEP-502 | Plumbing Riser Diagram | Tender Drawings | MEP Design Associates | R1 | 2025-02-06 | Initial issue | Yes | 2025-02-04 | 2025-02-06 | -2 | Consultant | Main Contractor | 2025-02-12 | 2 | No | —
21 | Package B | Tower 3 | MEPF | MEP-503 | HVAC Shaft Layout | Tender Drawings | MEP Design Associates | R0 | 2025-02-07 | Initial submission | Yes | 2025-02-05 | 2025-02-07 | -2 | Consultant | PMC / Client |  | 0 | Yes | Coordination required
22 | Package C | Tower 1 | Architecture | AR-401 | Typical Floor Plan | Schematic Drawings | Design Consultants Ltd | R4 | 2025-02-10 | Revised after coordination | Yes | 2025-02-03 | 2025-02-06 | -3 | Architecture Consultant | Main Contractor | 2025-02-15 | 2 | Yes | Delayed due to coordination changes
23 | Package C | Tower 1 | Structural | ST-501 | Foundation Layout | Good For Construction (GFC) | Structural Consultants Ltd | R3 | 2025-02-12 | Revised footing sizes | Yes | 2025-02-05 | 2025-02-09 | -4 | Structural Consultant | PMC / Client |  | 0 | Yes | Critical foundation drawing
24 | Package C | Tower 1 | MEPF | MEP-601 | HVAC Typical Floor | Tender Drawings | MEPF Design Associates | R2 | 2025-02-14 | Revised duct routing | Yes | 2025-02-08 | 2025-02-10 | -2 | MEPF Consultant | Main Contractor | 2025-02-18 | 2 | Yes | Coordination driven delay
25 | Package C | Tower 2 | Architecture | AR-402 | Elevation East Side | Shop Drawing | Design Consultants Ltd | R5 | 2025-02-18 | Facade design updated | Yes | 2025-02-10 | 2025-02-14 | -4 | Architecture Consultant | Main Contractor | 2025-02-22 | 2 | No | Client-driven revision
26 | Package C | Tower 2 | Structural | ST-502 | Column Layout Basement | Detailed Design (DD) Drawings | Structural Consultants Ltd | R4 | 2025-02-20 | Grid updated as per arch | Yes | 2025-02-12 | 2025-02-17 | -5 | Structural Consultant | PMC / Client |  | 0 | Yes | Delay due to arch inputs
27 | Package C | Tower 2 | MEPF | MEP-602 | Electrical Layout Typical | Concept Drawings | MEPF Design Associates | R3 | 2025-02-21 | Load recalculation done | Yes | 2025-02-15 | 2025-02-18 | -3 | MEPF Consultant | Main Contractor | 2025-02-25 | 2 | No | —
28 | Package C | Tower 3 | Architecture | AR-403 | Staircase Details | Detailed Design (DD) Drawings | Design Consultants Ltd | R2 | 2025-02-22 | Minor detailing changes | Yes | 2025-02-18 | 2025-02-20 | -2 | Architecture Consultant | PMC / Client |  | 0 | No | —
29 | Package C | Tower 3 | Structural | ST-503 | Beam Reinforcement | Good For Construction (GFC) | Structural Consultants Ltd | R1 | 2025-02-23 | Initial submission | Yes | 2025-02-20 | 2025-02-23 | -3 | Structural Consultant | PMC / Client |  | 0 | Yes | Delayed reinforcement inputs
30 | Package C | Tower 3 | MEPF | MEP-603 | Plumbing Layout Typical | Detailed Design (DD) Drawings | MEPF Design Associates | R2 | 2025-02-25 | Revised pipe routing | Yes | 2025-02-20 | 2025-02-24 | -4 | MEPF Consultant | Main Contractor | 2025-02-28 | 2 | No | —
31 | Package C | Tower 4 | Architecture | AR-404 | Refuge Floor Plan | Tender Drawings | Design Consultants Ltd | R6 | 2025-02-28 | Code compliance update | Yes | 2025-02-20 | 2025-02-26 | -6 | Architecture Consultant | Main Contractor | 2025-03-02 | 2 | Yes | Statutory driven delay
32 | Package D | Tower 1 | Structural | ST-601 | Foundation Layout | Tender Drawings | Structural Consultants Ltd | R5 | 2025-03-02 | Revised soil parameters | Yes | 2025-02-22 | 2025-02-27 | -5 | Structural Consultant | PMC / Client |  | 0 | Yes | Soil report revision
33 | Package D | Tower 1 | MEPF | MEP-701 | Fire Fighting Layout | Schematic Drawings | MEPF Design Associates | R3 | 2025-03-03 | Revised fire zoning | Yes | 2025-02-25 | 2025-02-28 | -3 | MEPF Consultant | Main Contractor | 2025-03-06 | 2 | Yes | Fire NOC comments
34 | Package D | Tower 2 | Architecture | AR-501 | Typical Floor Plan | Good For Construction (GFC) | Design Consultants Ltd | R4 | 2025-03-05 | Updated flat layouts | Yes | 2025-02-26 | 2025-03-02 | -4 | Architecture Consultant | Main Contractor | 2025-03-08 | 2 | Yes | Client revision impact
35 | Package D | Tower 2 | Structural | ST-602 | Slab Reinforcement | Tender Drawings | Structural Consultants Ltd | R2 | 2025-03-06 | Initial submission | Yes | 2025-03-01 | 2025-03-05 | -4 | Structural Consultant | PMC / Client |  | 0 | Yes | Delayed due to load changes
36 | Package D | Tower 3 | MEPF | MEP-702 | HVAC Shaft Layout | Shop Drawing | MEPF Design Associates | R1 | 2025-03-08 | Initial submission | Yes | 2025-03-04 | 2025-03-07 | -3 | MEPF Consultant | PMC / Client |  | 0 | Yes | Coordination pending
37 | Package D | Tower 3 | Architecture | AR-502 | Elevation West Side | Detailed Design (DD) Drawings | Design Consultants Ltd | R6 | 2025-03-10 | Facade redesign | Yes | 2025-03-01 | 2025-03-07 | -6 | Architecture Consultant | Main Contractor | 2025-03-12 | 2 | No | Major design change
38 | Package D | Tower 4 | Structural | ST-603 | Column Layout Typical | Concept Drawings | Structural Consultants Ltd | R4 | 2025-03-12 | Grid revised | Yes | 2025-03-05 | 2025-03-10 | -5 | Structural Consultant | Main Contractor | 2025-03-15 | 2 | Yes | Coordination delay
39 | Package D | Tower 4 | MEPF | MEP-703 | Electrical Riser Diagram | Detailed Design (DD) Drawings | MEPF Design Associates | R2 | 2025-03-14 | Load balancing update | Yes | 2025-03-08 | 2025-03-12 | -4 | MEPF Consultant | Main Contractor | 2025-03-18 | 2 | No | —
40 | Package D | Tower 5 | Architecture | AR-503 | Refuge Area Details | Good For Construction (GFC) | Design Consultants Ltd | R5 | 2025-03-16 | Code update applied | Yes | 2025-03-10 | 2025-03-15 | -5 | Architecture Consultant | Main Contractor | 2025-03-20 | 2 | Yes | Fire authority driven
41 | Package D | Tower 5 | Structural | ST-604 | Beam Layout Roof | Detailed Design (DD) Drawings | Structural Consultants Ltd | R3 | 2025-03-18 | Revised reinforcement | Yes | 2025-03-12 | 2025-03-17 | -5 | Structural Consultant | PMC / Client |  | 0 | Yes | Roof load revision

## Drawing Register - Client
Site Drawing Register
SR. NO | DETAILS OF DRAWING | Descipline | DRAWING NOMBER | RECEIVE & ISSUE DETAILS | DRAWING REVISION | [6 empty] | Date | Remarks
[5 empty] | RO | R1 | R2 | R3 | R4 | R5 | R6
1 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
2 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
3 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
4 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
5 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
6 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
7 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
8 |  |  |  | Date of Receiving | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Total Copied Received | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Contractor | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Issued to Client | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  |  |  | Receiver Signature | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Client Logo

## Input
Latest Revision | Drawing Type | Discipline | Delay Responsibility
Yes | Concept Drawings | Architecture | Architecture Consultant
No | Schematic Drawings | Structural | Strcutural Consultant
| Detailed Design (DD) Drawings | MEPF | MEPF Consultant
| Tender Drawings |  | BIM Consultant
| Good For Construction (GFC) |  | Contractor
PMC
Note:
Drawing Register Client: This need to use to track the Final Drawing and it's revision only
Master Drawing Register: Backend detailed report for all the Drawings which is submitted