## Dashboard
Hinderance Dashboard - Project # - Week #
Row Labels | Count of Approval ID | Row Labels | Sum of Delay (Days)
Approved | 12 | Client | -1
Delayed | 3 | Contractor | -5
In Progress | 4 | Grand Total | -6
Not Submitted | 4
Submitted | 7
(blank)
Grand Total | 30
Row Labels | Count of Approval ID
Environment | 4
Fire | 1
Health & Safety | 1
Insurance | 2
Labour Compliance | 5
Local Authority | 3
Police Clearance | 1
Safety | 5
Statutory | 3
Tax | 1
Traffic | 1
Utility | 3
Grand Total | 30
Authority Name | Count of Approval ID
Electricity Board | 1
EPFO | 1
ESIC | 1
Explosives Department | 1
Factory Inspectorate | 1
Fire Department | 2
Government Hospital | 1
Insurance Company | 2
Labour Department | 5
Lift Inspector | 1
Local Authority | 2
Local Police Department | 1
Municipal Corporation | 3
Pollution Control Board | 2
State Tax Department | 1
Telecom Authority | 1
Third Party Agency | 2
Traffic Police Department | 1
Water Supply Department | 1
Grand Total | 30
Client Logo

## Legal Approval Tracker
Legal Approval Tracker - Week #
Approval ID | Approval Category | Authority Name | Approval Description | Applicable Building / Package | Submission Date | Required By | Approval Received Date | Status | Delay (Days) | Responsible Party | Remarks
LA-01 | Labour Compliance | Labour Department | BOCW Registration – Building & Other Construction Works | All Towers | 2025-01-05 | 2025-01-20 | 2025-01-22 | Approved | 2 | Client | Approved with minor delay
LA-02 | Insurance | Insurance Company | CAR Policy – Contractor All Risk | All Packages | 2025-01-02 | 2025-01-10 | 2025-01-09 | Approved | -1 | Contractor | Submitted on priority
LA-03 | Labour Compliance | Labour Department | CLRA Registration – Contract Labour Regulation Act | All Towers | 2025-01-06 | 2025-01-25 |  | Submitted |  | Contractor | Under review by department
LA-04 | Labour Compliance | Labour Department | Labour License | Tower 1 | 2025-01-08 | 2025-01-20 |  | Delayed |  | Contractor | Inspection pending
LA-05 | Statutory | EPFO | PF Registration Documents | All Packages | 2025-01-03 | 2025-01-15 | 2025-01-14 | Approved | -1 | Contractor | -
LA-06 | Statutory | ESIC | ESI Registration Documents | All Packages | 2025-01-03 | 2025-01-15 | 2025-01-16 | Approved | 1 | Contractor | One day delay
LA-07 | Tax | State Tax Department | Professional Tax Registration | All Packages | 2025-01-04 | 2025-01-18 | 2025-01-17 | Approved | -1 | Contractor | -
LA-08 | Labour Compliance | Labour Department | LWF – Labour Welfare Fund Registration | All Towers | 2025-01-05 | 2025-01-18 |  | Submitted |  | Contractor | Follow-up required
LA-09 | Health & Safety | Government Hospital | Worker Medical Fitness Certification | All Towers | 2025-01-07 | 2025-01-14 | 2025-01-13 | Approved | -1 | Contractor | -
LA-10 | Police Clearance | Local Police Department | Worker Police Verification | All Towers | 2025-01-07 | 2025-01-21 |  | Delayed |  | Contractor | Police clearance pending
LA-11 | Safety | Third Party Agency | Test Certificate – Lifting Tools & Tackles | All Towers | 2025-01-09 | 2025-01-19 | 2025-01-18 | Approved | -1 | Contractor | -
LA-12 | Safety | Third Party Agency | Pressure Vessel Test Certificate | All Towers | 2025-01-09 | 2025-01-19 |  | Submitted |  | Contractor | Inspection scheduled
LA-13 | Fire | Fire Department | Fire NOC – Temporary Site Office | Site Area | 2025-01-10 | 2025-01-25 |  | In Progress |  | Client | Documents submitted
LA-14 | Environment | Pollution Control Board | Consent to Establish (CTE) | Project Site | 2025-01-12 | 2025-02-05 |  | Submitted |  | Client | Under scrutiny
LA-15 | Environment | Pollution Control Board | Consent to Operate – DG Set | Project Site | 2025-01-15 | 2025-02-10 |  | Not Submitted |  | Contractor | DG set not installed
LA-16 | Local Authority | Municipal Corporation | Building Plan Approval | Tower 1 | 2024-12-15 | 2025-01-30 | 2025-01-28 | Approved | -2 | Client | -
LA-17 | Local Authority | Municipal Corporation | Commencement Certificate | Tower 2 | 2025-01-05 | 2025-01-25 |  | Delayed |  | Client | Resubmission required
LA-18 | Utility | Electricity Board | Temporary Power Connection | Site | 2025-01-06 | 2025-01-20 | 2025-01-21 | Approved | 1 | Contractor | -
LA-19 | Utility | Water Supply Department | Temporary Water Connection | Site | 2025-01-06 | 2025-01-20 |  | Submitted |  | Contractor | Pipeline work pending
LA-20 | Traffic | Traffic Police Department | Traffic Diversion Permission | Main Road | 2025-01-10 | 2025-01-18 | 2025-01-17 | Approved | -1 | Client | -
LA-21 | Safety | Factory Inspectorate | Site Safety Registration | All Towers | 2025-01-11 | 2025-01-22 |  | In Progress |  | Contractor | Inspection awaited
LA-22 | Insurance | Insurance Company | Workmen Compensation Policy | All Labour | 2025-01-05 | 2025-01-12 | 2025-01-11 | Approved | -1 | Contractor | -
LA-23 | Labour Compliance | Labour Department | Inter-State Migrant Workmen Registration | All Towers | 2025-01-08 | 2025-01-25 |  | Submitted |  | Contractor | Documents under review
LA-24 | Environment | Local Authority | Tree Cutting Permission | Site Boundary | 2025-01-15 | 2025-02-01 |  | Not Submitted |  | Client | Tree survey pending
LA-25 | Safety | Fire Department | Fire Safety Equipment Approval | Site | 2025-01-16 | 2025-01-30 |  | In Progress |  | Contractor | Partial installation completed
LA-26 | Utility | Telecom Authority | Internet / Telecom Permission | Site Office | 2025-01-14 | 2025-01-28 | 2025-01-27 | Approved | -1 | Contractor | -
LA-27 | Local Authority | Municipal Corporation | Hoarding Permission | Site Boundary | 2025-01-18 | 2025-01-28 |  | Submitted |  | Client | Approval awaited
LA-28 | Environment | Local Authority | Debris Disposal Permission | Project Site | 2025-01-20 | 2025-02-05 |  | Not Submitted |  | Contractor | Vendor finalisation pending
LA-29 | Safety | Lift Inspector | Temporary Construction Lift Approval | Tower 1 | 2025-01-22 | 2025-02-10 |  | In Progress |  | Contractor | Inspection scheduled
LA-30 | Statutory | Explosives Department | Diesel Storage License | Project Site | 2025-01-25 | 2025-02-15 |  | Not Submitted |  | Contractor | Tank installation pending
Client Logo