## Dashboard
Hinderance Dashboard - Project # - Week #
Row Labels | Count of Sr. No | Row Labels | Sum of Schedule Impact
Casting | 3 | Approval | 113
Excavation | 4 | Design & Technical | 81
Reinforcement | 4 | Execution | 118
Shutterting | 4 | Material Procurement | 86
Grand Total | 15 | Grand Total | 398
Row Labels | Count of Sr. No | Row Labels | Count of Sr. No
Approval | 4 | Non-overlapping Delay | 8
Design & Technical | 3 | Overlapping Delay | 7
Execution | 5 | Grand Total | 15
Material Procurement | 3
Grand Total | 15
|  | Row Labels | Count of Sr. No
|  | Open | 3
Row Labels | Sum of Schedule Impact | Resolved | 12
Architecture Consultant | 56 | (blank)
Client | 112 | Grand Total | 15
Contractor | 114
PMC | 43
Structure Consultant | 73
(blank)
Grand Total | 398
Row Labels | Count of Sr. No
Open | 3
Architecture Consultant | 1
Contractor | 2
Resolved | 12
Architecture Consultant | 1
Client | 3
Contractor | 2
PMC | 2
Structure Consultant | 4
Grand Total | 15
Client Logo

## Hinderance Register
Hinderance Register
Sr. No | Description of Hindrance | Location | Critical Activity affected | Correspondence | Category | Type of Hindrance | Date of Occurrence | Date Resolved | No. of Days | Baseline Start Date | Schedule Impact | Delay Type | Accountable | Status | Description of Resolution | Remarks
1 | Staircase work | Building A | Shutterting | 2026-12-26 | Design & Technical | Storage and handling constraints | 2026-11-19 | 2026-11-22 | 4 | 2026-11-13 | 10 | Overlapping Delay | Architecture Consultant | Resolved | drawing was given on 22-11-2026 |  | #REF! | #REF!
2 | Column reinforcement and formwork for part 1A | Building B | Casting | 2026-12-26 | Approval | Delay in mock-up / sample approvals | 2026-12-24 | 2026-12-28 | 5 | 2026-12-24 | 5 | Non-overlapping Delay | Contractor | Resolved | drawing was given on 28-12-2027
3 | basement 1 slab for Part 1B,1C | Building C | Reinforcement | 2027-01-12 | Execution | Variation / change order approval delays | 2027-01-05 | 2027-01-17 | 13 | 2027-01-06 | 12 | Non-overlapping Delay | Structure Consultant | Resolved | drawing was given on 17-1-23
4 | Basement 1 slab for Part 1D | Building D | Excavation | 2027-01-12 | Material Procurement | Work front not available / handed over | 2027-01-12 | 2027-01-17 | 6 | 2026-12-31 | 18 | Overlapping Delay | PMC | Resolved | drawing was given on 17-1-23
5 | Ground floor slab for Block A | Building E | Shutterting | 2026-12-26 | Material Procurement | Import / logistics clearance delays | 2027-01-20 | 2027-02-08 | 20 | 2027-01-20 | 20 | Non-overlapping Delay | Structure Consultant | Resolved | drawing was given on 8-2-23 for shuttering
6 | Basement 3 slab for Part 2 | Building A | Casting | 2026-12-26 | Approval | Delay in statutory approvals (Fire, Local Authority, Utilities) | 2027-01-20 | 2027-02-07 | 19 | 2027-01-15 | 24 | Overlapping Delay | Client | Resolved | drawing was given on 7-2-23 for shuttering
7 | Lift 4 | Building B | Reinforcement | 2027-01-28 | Execution | Vendor / supplier non-performance | 2027-01-18 | 2027-01-31 | 14 | 2027-01-07 | 25 | Non-overlapping Delay | Contractor | Open | drawing was given on 24-1-23 and hold decision was given on 31-1-23
8 | Stair 5,6,2 - Part 2 | Building C | Excavation | 2027-02-22 | Design & Technical | Insufficient skilled manpower | 2027-02-10 | 2027-03-01 | 20 | 2027-01-15 | 46 | Non-overlapping Delay | Architecture Consultant | Open | drawing was given on 8-2-23 for shuttering
9 | Block B & C - ground floor slab | Building D | Reinforcement | 2026-12-26 | Approval | Constructability issues at site | 2027-02-15 | 2027-02-19 | 5 | 2027-01-31 | 20 | Overlapping Delay | Contractor | Resolved | drawing was given on 19-2-23 for shuttering
10 | Block A - ground floor | Building E | Excavation | 2026-12-26 | Execution | Delay in issue of GFC / IFC drawings | 2027-02-20 | 2027-02-23 | 4 | 2027-02-07 | 17 | Overlapping Delay | Structure Consultant | Resolved | drawing was given on 8-2-23 for shuttering
11 | Block C - ground floor | Building A | Shutterting | 2027-02-27 | Design & Technical | Delay in issue of GFC / IFC drawings | 2027-02-26 | 2027-02-28 | 3 | 2027-02-04 | 25 | Overlapping Delay | PMC | Resolved
12 | Block A - ground floor | Building B | Casting | 2026-12-26 | Execution | Delay in design clarifications (RFIs) | 2027-02-27 | 2027-03-02 | 4 | 2027-02-07 | 24 | Non-overlapping Delay | Structure Consultant | Resolved | casting done on 2/3/23
13 | Part 2- ramp work | Building C | Excavation | 2027-02-27 | Material Procurement | Delay in approval from Client / PMC | 2027-02-17 | 2027-03-04 | 16 | 2027-01-16 | 48 | Non-overlapping Delay | Client | Resolved
14 | Part 1- Stair 1,9 | Building D | Shutterting | 2026-12-26 | Approval | Delay in statutory approvals (Fire, Local Authority, Utilities) | 2027-03-05 | 2027-04-04 | 31 | 2027-01-31 | 64 | Overlapping Delay | Contractor | Open
15 | Part 2A- basement 2 | Building E | Reinforcement | 2027-03-14 | Execution | Delay in issue of GFC / IFC drawings | 2027-03-16 | 2027-03-21 | 6 | 2027-02-10 | 40 | Non-overlapping Delay | Client | Resolved | drawing was given on 21-3-23 for shuttering
0

## Input
Accountable | Work affected | Type of Hinderance | Category of Hinderance | Delay Type | Status
Client | Shutterting | Delay in issue of GFC / IFC drawings | Design & Technical | Overlapping Delay | Open
Contractor | Casting | Incomplete or incorrect drawings | Design & Technical | Non-overlapping Delay | Resolved
Architecture Consultant | Reinforcement | Frequent design revisions | Design & Technical
Structure Consultant | Excavation | Delay in shop drawing approvals | Design & Technical
PMC |  | Design coordination issues (Arch–Struct–MEP) | Design & Technical
|  | Constructability issues at site | Design & Technical
|  | Delay in design clarifications (RFIs) | Design & Technical
|  | Delay in approval from Client / PMC | Approval
|  | Delay in statutory approvals (Fire, Local Authority, Utilities) | Approval
|  | Delay in inspection and clearance | Approval
|  | Delay in mock-up / sample approvals | Approval
|  | Variation / change order approval delays | Approval
|  | Insufficient skilled manpower | Execution
|  | Low labour productivity | Execution
|  | Work front not available / handed over | Execution
|  | Site access restrictions | Execution
|  | Poor coordination between trades | Execution
|  | Equipment / machinery non-availability | Execution
|  | Safety stoppages affecting work | Execution
|  | Delay in material delivery | Material Procurement
|  | Long-lead item procurement delays | Material Procurement
|  | Vendor / supplier non-performance | Material Procurement
|  | Delay in material approvals | Material Procurement
|  | Material rejection due to quality issues | Material Procurement
|  | Import / logistics clearance delays | Material Procurement
|  | Storage and handling constraints | Material Procurement