## NCR CAR
Non-Conformance Report / Corrective Action Request
Project: | Centenary Geotex Pvt. Ltd.
NCR / CAR No: | 1
Date: | 2025-02-25
To: | 2025-02-25
From: | 2025-02-27
Action Required as a Result of:
Environmental Issues | -
Other | General - Project Schedule & Mix Design
Description of the problem which requires rectification:
Project Schedule: The submitted project schedule of main factory building does not conform to the agreed project requirements due to the following reasons: 1. Recipt of Foundation drawing 2. Missing critical project milestones and deliverables. 3. Lack of alignment with contract specifications or baseline schedule. 4. Incorrect resource allocation or unrealistic timelines. 5. Incomplete activity sequencing and dependencies. Mix Design: The submitted mix design does not comply with the approved project specifications and Indian standard requirements due to the following reasons: 1. Incorrect cemment ratio 2. Invalid fly ash content, exceeding limits 3. Failure to comply Indian standards
Action Required to rectify the problem (and prevent recurrence): (if not obvious from description)
Submit the revised project schedule for the Main Factor Building, considering the receipt date of the foundation drawings, along with the project schedules for the labour colony, Vastu compound wall, and RMC mix design to facilitate further construction work on-site.
Date by which action must be completed: 27/02/2025 (Note:- If the rectification works are to be completed AFTER Practical Completion, additional HSE considerations required for occupied / client managed premises due to potentially reduced HSE controls and awareness)
The work should be carried out in accordance with the shuttering requirements specified for the wall. This entails ensuring that the shuttering material is appropriately selected, positioned, and secured to create the desired formwork for the wall structure.
Signed: Nirav Parekh Position: Director Date: 25/02/2025
Follow-up review/report:
Has the Action taken been effective? Yes No (If No, a new Notice may need to be issued)
Signed: Position: Date:
The company on which this NCR is served is required to take action in order to rectify the substandard conditions detailed above. Failure to act within the specified time period will result in SPDC taking further action and any costs as a result of such action shall be costs payable by the company on which this notice is served.
Should further action and/or costs be pursued against the company on which this notice is served? Yes (If YES, then send a copy of this notice to the Project Manager for further action).
Does the Project Site Set Up System require modification to prevent a recurrence? No
Action required:
By Whom: | Completed:

## NCR REGISTER
NON CONFORMANCE AND CORRECTIVE ACTION REQUEST (CAR ) REGISTER
No. | NCR Issue Date | Type | Contractor | Brief Description of Non Conformance | Location | Planned Closure Date | Actual Closure Date | Status
1 | 2025-12-05 | General | TCC | Project Schedule: The submitted project schedule of main factory building does not conform to the agreed project requirements due to the following reasons: 1. Recipt of Foundation drawing 2. Missing critical project milestones and deliverables. 3. Lack of alignment with contract specifications or baseline schedule. 4. Incorrect resource allocation or unrealistic timelines. 5. Incomplete activity sequencing and dependencies. | India | 2025-02-18 |  | Open | Open
2 | 2025-12-05 | General | TCC | The submission of project schedule for vastu compound wall & labour colony | India | 2025-02-18 |  | Open | Close
3 | 2025-12-05 | General | TCC | Mix Design: The submitted mix design does not comply with the approved project specifications and Indian standard requirements due to the following reasons: 1. Incorrect cemment ratio 2. Invalid fly ash content, exceeding limits 3. Failure to comply Indian standards | India | 2025-02-18 | 2025-02-26 | Close
Health and Safety
Environmental
| Quality |  |  |  | Australia
| General |  |  |  | China
Hong Kong
India
Indonesia
Japan
Korea
Philippines
Singapore
Taiwan
Thailand
Vietnam