## Dashboard
Planned Vs. Actual Report - Project # - Week 13
Project Timeline |  | Planned Vs. Actual Manpower Top 3 Manpower Shortage Categories this week |  |  |  | Planned Vs. Actual Cashflow
Project Start Date | 2025-06-01 | Sr. No. | Category | Reason for Shortage
Planned End Date | 2026-06-30 | 1 | Reinforcement work | Unavailibility of Manpower
Current Date | 2026-01-31 | 2 | Plumbing | Vendor not responding
Project Progress | 61.93% | 3 | Tiles Work | Unavailibility of Manpower
Planned Vs. Actual Quantity
Past Vs. Current Progress
[5 empty] | Last Week Status |  | Current Week Status
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Weekly Manpower
Type of Manpower | Required Manpower for week | Available | Shortage | % Shortage | Rank | [14 empty] | Safety NCR |  |  | Unsafe Act |  |  | Condition
Reinforcement work | 120 | 65 | 55 | 45.83% | 1 | [14 empty] | Total | Open | Close | Total | Open | Close | Total | Open | Close
Carpenter | 125 | 100 | 25 | 20% | 9 | [14 empty] | 2 | 1 | 2 | 10 | 0 | 10 | 10 | 1 | 9
Mason | 105 | 79 | 26 | 24.76% | 8
Helper | 116 | 83 | 33 | 28.45% | 7
Unskilled Worker | 315 | 203 | 112 | 35.56% | 4 | [14 empty] | NCR |  |  | Site Observation |  |  | Site Instructions
Drivers | 13 | 13 | 0 | 0% | 10 | [14 empty] | Total | Open | Close | Total | Open | Close | Total | Open | Close
Staff | 33 | 33 | 0 | 0% | 10 | [14 empty] | 1 | 0 | 1 | 38 | 2 | 36 | 41 | 2 | 39
Plumbing | 10 | 6 | 4 | 40% | 2
Tiles Work | 48 | 30 | 18 | 37.5% | 3
Painter | 21 | 15 | 6 | 28.57% | 6
Electric Work | 32 | 22 | 10 | 31.25% | 5
Total of Above | 938 | 649 | 289
Available | [11 empty] | Available
Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff | Plumbing | Tiles | Painter | Ele. | Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff
2025-12-11 | 12 | 10 | 12 | 14 | 28 | 1 | 5 | 2 | 5 | 2 | 3 | 2025-10-23 | 0 | 5 | 0 | 3 | 1 | 0 | 0
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-12 | 10 | 7 | 11 | 8 | 29 | 1 | 5 | 2 | 5 | 2 | 5 | 2025-10-24 | 0 | 5 | 0 | 3 | 1 | 0 | 1
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-13 | 3 | 14 | 12 | 8 | 29 | 1 | 5 | 2 | 5 | 2 | 2 | 2025-10-25 | 0 | 10 | 0 | 8 | 14 | 1 | 2
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-14 | 2 | 14 | 12 | 7 | 28 | 1 | 3 | 0 | 3 | 3 | 2 | 2025-10-26 | 0 | 10 | 0 | 8 | 5 | 1 | 0
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-15 | 14 | 25 | 12 | 11 | 28 | 1 | 5 | 0 | 3 | 3 | 3 | 2025-10-27 | 0 | 5 | 0 | 4 | 3 | 1 | 4
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-16 | 14 | 15 | 10 | 16 | 30 | 4 | 6 | 0 | 3 | 3 | 3 | 2025-10-28 | 3 | 5 | 1 | 8 | 3 | 1 | 6
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-17 | 10 | 15 | 10 | 19 | 31 | 4 | 4 | 0 | 6 | 0 | 4 | 2025-10-29 | 3 | 5 | 1 | 8 | 12 | 1 | 5
Night | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Night | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 65 | 100 | 79 | 83 | 203 | 13 | 33 | 6 | 30 | 15 | 22 | Total | 6 | 45 | 2 | 42 | 39 | 5 | 18
Required | [11 empty] | Required
Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff | Plumbing | Tiles | Painter | Ele | Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff
2025-12-04 | 20 | 15 | 15 | 15 | 45 | 1 | 5 | 2 | 5 | 3 | 4 | 2025-10-23 | 10 | 8 | 2 | 4 | 6 | 5 | 6
2025-12-05 | 15 | 15 | 15 | 16 | 45 | 1 | 5 | 2 | 5 | 3 | 4 | 2025-10-24 | 10 | 8 | 2 | 4 | 6 | 4 | 5
2025-12-06 | 15 | 15 | 15 | 15 | 45 | 1 | 5 | 2 | 6 | 3 | 4 | 2025-10-25 | 10 | 8 | 2 | 4 | 6 | 4 | 5
2025-12-07 | 15 | 20 | 15 | 16 | 45 | 1 | 3 | 2 | 8 | 3 | 4 | 2025-10-26 | 10 | 8 | 2 | 4 | 6 | 4 | 5
2025-12-08 | 15 | 20 | 15 | 18 | 45 | 1 | 5 | 2 | 8 | 3 | 4 | 2025-10-27 | 10 | 8 | 2 | 4 | 6 | 2 | 6
2025-12-09 | 20 | 20 | 15 | 18 | 45 | 4 | 6 | 0 | 8 | 3 | 6 | 2025-10-28 | 10 | 8 | 2 | 4 | 6 | 2 | 7
2025-12-10 | 20 | 20 | 15 | 18 | 45 | 4 | 4 | 0 | 8 | 3 | 6 | 2025-10-29 | 10 | 8 | 2 | 4 | 6 | 2 | 6
Total | 120 | 125 | 105 | 116 | 315 | 13 | 33 | 10 | 48 | 21 | 32 | Total | 70 | 56 | 14 | 28 | 42 | 5 | 40

## Project Cashflow
Month |  | Budgeted work | Planned Work | Actual Work
August | RA 01 |  | 5000000 | 1063955
September | RA 02 |  | 7200000 | 7797193
October | RA 03 |  | 5000000 | 168333
November | RA 04 |  | 7500000 | 2376171
December | RA 05 |  | 8000000 | 11104853
January | RA 06 |  | 9000000
February | RA 07 |  | 8000000
March | RA 08 |  | 8000000
57700000
Month |  |  | January
Planned
Actual

## Planned Vs Actual
Planned Vs Actual Previous Week to Current Week (Date: 11-12-2025 to 17-12-2025)
Description | [5 empty] | Qty Planed | [6 empty] | Against GFC | Agianst Weekly Planed |  | Cumlative | Cumlative
Sr.No. | Tower | Activity | Planned Start Date by Contractor | Planned End Date by Contractor | Unit | As per BOQ total Quantity | Total GFC Qty | Executed qty till 15-10-2025 | Balance Qty. | Weekly planned Qty. | Weekly actual Qty. | Cumulative Qty. | % Balance Qty ( Remaining ) Against GFC Qty | % Planned Against Balance Qty | % Achieved Against Actual Qty | % Completed (Total against the GFC ) | % Completed (Total against the GFC )
1 | Upto Plinth | Excavation | 2025-12-11 | 2025-12-17 | CUM | 3925 | 1826 | 1826.2 | -0.2 | 0 | 0 | 1826.2 | -0.01095% | 0% | 0% | Delay | 100%
2 |  | Footing PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 91.31 | 91.31 | 0 | 0 | 0 | 91.31 | 0% | 0% | 0% | On time | 100%
3 |  | Yellow Soil Filling | 2025-12-11 | 2025-12-17 | CUM | 10000 | 1123.22 | 1123.22 | 0 | 0 | 0 | 1123.22 | 0% | 0% | 0% |  | 100%
4 |  | Rubble Soling | 2025-12-11 | 2025-12-17 | CUM | 195.5 | 173.81 | 173.81 | 0 | 0 | 0 | 173.81 | 0% | 0% | 0% |  | 100%
5 |  | Footing Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 441.908 | 441.91 | -0.002 | 0 | 0 | 441.91 | -0.0004526% | 0% | 0% |  | 100% |  | 94416.726
6 |  | Footing RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 292.764 | 292.76 | 0.004 | 0 | 0 | 292.76 | 0.001366% | 0% | 0% | On time | 100%
7 |  | Padestal Upto Plinth Top Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 664 | 664 | 0 | 0 | 0 | 664 | 0% | 0% | 0% |  | 100%
8 |  | Padestal Upto Plinth Top RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 62.65 | 62.65 | 0 | 0 | 0 | 62.65 | 0% | 0% | 0% |  | 100%
9 |  | GB Excavation | 2025-12-11 | 2025-12-17 | CUM | 3925 | 11.795 | 11.795 | 0 | 0 | 0 | 11.795 | 0% | 0% | 0% |  | 100%
10 |  | GB PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 7.944 | 7.944 | 0 | 0 | 0 | 7.944 | 0% | 0% | 0% |  | 100%
11 |  | GB Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 142.938 | 142.85 | 0.088 | 0 | 0 | 142.85 | 0.06157% | 0% | 0% |  | 99.94%
12 |  | GB RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 23.994 | 23.98 | 0.014 | 0 | 0 | 23.98 | 0.05835% | 0% | 0% |  | 99.94%
13 |  | Masonry Above GB | 2025-12-11 | 2025-12-17 | CUM | 130 | 86.294 | 86.294 | 0 | 0 | 0 | 86.294 | 0% | 0% | 0% |  | 100%
14 |  | Plinth Beam PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 18.07 | 18.07 | 0 | 0 | 0 | 18.07 | 0% | 0% | 0% |  | 100%
15 |  | Plinth Beam Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 387.1 | 387.1 | 0 | 0 | 0 | 387.1 | 0% | 0% | 0% |  | 100%
16 |  | Plinth Beam RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 45.72 | 45.72 | 0 | 0 | 0 | 45.72 | 0% | 0% | 0% |  | 100%
17 |  | Plinth Plaster | 2025-12-11 | 2025-12-17 | SMT | 5235 | 92.29 | 59.5 | 32.79 | 32.79 | 15 | 74.5 | 35.53% | 100% | 45.75% |  | 80.72%
18 |  | Masonry above PB | 2025-12-11 | 2025-12-17 | CUM | 130 | 16.168 | 16.17 | -0.002 | 0 | 0 | 16.17 | -0.01237% | 0% | 0% |  | 100%
19 |  | Floor PCC | 2025-12-11 | 2025-12-17 | CUM | 265 | 86.9 | 86.9 | 0 | 0 | 0 | 86.9 | 0% | 0% | 0% |  | 100%
20 |  | Floor RCC Shuttering | 2025-12-11 | 2025-12-17 | SMT | 1075 | 15.3 | 15.3 | 0 | 0 | 0 | 15.3 | 0% | 0% | 0% |  | 100%
21 |  | Floor RCC | 2025-12-11 | 2025-12-17 | CUM | 380 | 88.03 | 88.03 | 0 | 0 | 0 | 88.03 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 4.762% | 2.178% | #DIV/0! | 99.08%
22 | Ground Floor | Plinth to GF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 427.55 | 427.554 | -0.004 | 0 | 0 | 427.554 | -0.0009356% | 0% | 0% |  | 100%
23 |  | GF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
24 |  | GF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 664.23 | 0.03 | 0 | 0 | 664.23 | 0.004516% | 0% | 0% |  | 100%
25 |  | GF staircase shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
26 |  | GF lintel shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 67.99 | 56 | 11.99 | 0 | 0 | 56 | 17.63% | 0% | 0% |  | 82.37%
27 |  | Plinth to GF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 32.82 | 0.002 | 0 | 0 | 32.82 | 0.006093% | 0% | 0% |  | 99.99%
28 |  | GF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 61.75 | 0.01 | 0 | 0 | 61.75 | 0.01619% | 0% | 0% |  | 99.98%
29 |  | GF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 101.98 | 0.01 | 0 | 0 | 101.98 | 0.009805% | 0% | 0% |  | 99.99%
30 |  | GF staircase concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 8.52 | 0.01 | 0 | 0 | 8.52 | 0.1172% | 0% | 0% |  | 99.88%
31 |  | GF lintel Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 3.91 | 2 | 1.91 | 0 | 0 | 2 | 48.85% | 0% | 0% |  | 51.15%
32 |  | Brick masonary GF (230 mm) | 2025-12-11 | 2025-12-17 | CUM | 80 | 73.48 | 36.86 | 36.62 | 20 | 7 | 43.86 | 49.84% | 54.61% | 19.12% |  | 59.69%
33 |  | Brick masonary GF (115 mm) | 2025-12-11 | 2025-12-17 | SMT | 1170 | 768 | 346.26 | 421.74 | 100 | 10 | 356.26 | 54.91% | 23.71% | 2.371% |  | 46.39%
34 |  | Internal Plaster | 2025-12-11 | 2025-12-17 | SMT | 1591.21 | 1733.79 | 362 | 1371.79 | 600 | 301 | 663 | 79.12% | 43.74% | 21.94% |  | 38.24%
35 |  | Flooring | 2025-12-11 | 2025-12-17 | SMT | 830 | 841.16 | 0 | 841.16 | 100 | 55.15 | 55.15 | 100% | 11.89% | 6.556% |  | 6.556%
36 |  | Skirting | 2025-12-11 | 2025-12-17 | RMT | 1865 | 1859.2 | 0 | 1859.2 | 100 | 45 | 45 | 100% | 5.379% | 2.42% |  | 2.42%
Avreage Achivement : - | [13 empty] | 9.289% | 3.494% | #DIV/0! | 72.44%
37 | First Floor | GF to FF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 439.913 | 315 | 124.913 | 100 | 21.32 | 336.32 | 28.39% | 80.06% | 17.07% |  | 76.45%
38 |  | FF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 701 | -0.41 | 0 | 0 | 701 | -0.05852% | 0% | 0% |  | 100.1%
39 |  | FF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 664.26 | 0 | 0 | 0 | 664.26 | 0% | 0% | 0% |  | 100%
40 |  | FF Staircase Shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
41 |  | FF lintel shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 67.99 | 0 | 67.99 | 60 | 29 | 29 | 100% | 88.25% | 42.65% |  | 42.65%
42 |  | GF to FF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 25.81 | 7.012 | 0 | 0 | 25.81 | 21.36% | 0% | 0% |  | 78.64%
43 |  | FF Staircase Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
44 |  | FF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
45 |  | FF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
46 |  | FF lintel Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 3.91 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0%
47 |  | Brick masonary FF (230 mm) | 2025-12-11 | 2025-12-17 | CUM | 80 | 73.48 | 0 | 73.48 | 20 | 28.63 | 28.63 | 100% | 27.22% | 38.96% |  | 38.96%
48 |  | Brick masonary FF (115 mm) | 2025-12-11 | 2025-12-17 | SMT | 1170 | 768 | 0 | 768 | 300 | 174.55 | 174.55 | 100% | 39.06% | 22.73% |  | 22.73%
49 |  | Internal Plaster | 2025-12-11 | 2025-12-17 | SMT | 1591.21 | 1733.79 | 0 | 1733.79 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
50 |  | Flooring | 2025-12-11 | 2025-12-17 | SMT | 830 | 841.16 | 0 | 841.16 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
51 |  | Skirting | 2025-12-11 | 2025-12-17 | RMT | 1865 | 1859.2 | 0 | 1859.2 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
Avreage Achivement : - | [13 empty] | 15.64% | 8.094% | #DIV/0! | 57.3%
52 | Second Floor | FF to SF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 439.913 | 310.94 | 128.973 | 0 | 0 | 310.94 | 29.32% | 0% | 0% |  | 70.68% | 0.06
53 |  | SF Staircase Shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
54 |  | SF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
55 |  | SF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 664.26 | 0 | 0 | 0 | 664.26 | 0% | 0% | 0% |  | 100%
56 |  | FF to SF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 25.415 | 7.407 | 0 | 0 | 25.415 | 22.57% | 0% | 0% |  | 77.43%
57 |  | SF Staircase Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
58 |  | SF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
59 |  | SF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 93.51%
60 | Third Floor | SF to TF slab column shuttering | 2025-12-11 | 2025-12-17 | SQM | 1680 | 439.913 | 98 | 341.913 | 212 | 188.42 | 286.42 | 77.72% | 62% | 55.11% |  | 65.11% | 213
61 |  | TF Staircase Shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 57.39 | 0 | 57.39 | 30 | 30 | 30 | 100% | 52.27% | 52.27% |  | 52.27%
62 |  | TF beam shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 700.59 | 0 | 700.59 | 400 | 350 | 350 | 100% | 57.09% | 49.96% |  | 49.96%
63 |  | TF Slab shuttering | 2025-12-11 | 2025-12-17 | SQM |  | 664.26 | 0 | 664.26 | 400 | 180 | 180 | 100% | 60.22% | 27.1% |  | 27.1%
64 |  | SF to TF slab column concrete | 2025-12-11 | 2025-12-17 | CUM | 210 | 32.822 | 2.58 | 30.242 | 30 | 18 | 20.58 | 92.14% | 99.2% | 59.52% |  | 62.7%
65 |  | TF Staircase Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 8.53 | 0 | 8.53 | 5 | 2.1 | 2.1 | 100% | 58.62% | 24.62% |  | 24.62%
66 |  | TF beam Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 61.76 | 0 | 61.76 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
67 |  | TF Slab Concrete | 2025-12-11 | 2025-12-17 | CUM |  | 101.99 | 0 | 101.99 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
Avreage Achivement : - | [13 empty] | 48.68% | 33.57% | #DIV/0! | 35.22%
Cumulative Avreage Achivement : - | [13 empty] | 15.67% | 9.468% | #DIV/0! | 71.51%
2

## As per drawing status
Weekly Executed Plan
Sr.No. | Tower | Activity | Unit | As per BOQ total Quantity | As per GFC total Quantity | Weekly planned Qty. | Weekly actual Qty. | Total Achieved Qty.
1 | Worker Dormitory | Footing Excavation | CUM | 3925 | 1826 | 0 | 0 | 1826.2
2 | Worker Dormitory | GB Excavation | CUM |  | 11.795 | 0 | 0 | 11.795
3 | Worker Dormitory | Yellow Soil Filling | CUM | 10000 | 1123.22 | 0 | 0 | 1123.22
4 | Worker Dormitory | Rubble Soling | CUM | 195.5 | 173.81 | 0 | 0 | 173.81
5 | Worker Dormitory | Footing PCC | CUM | 265 | 91.31 | 0 | 0 | 91.31
6 | Worker Dormitory | GB PCC | CUM |  | 7.944 | 0 | 0 | 7.944
7 | Worker Dormitory | Floor PCC | CUM |  | 86.9 | 0 | 0 | 86.9
8 | Worker Dormitory | Plinth Beam PCC | CUM |  | 18.07 | 0 | 0 | 18.07
9 | Worker Dormitory | Footing RCC | CUM | 380 | 292.764 | 0 | 0 | 292.76
10 | Worker Dormitory | Pedestal RCC | CUM |  | 62.65 | 0 | 0 | 62.65
11 | Worker Dormitory | GB RCC | CUM |  | 23.994 | 0 | 0 | 23.98
12 | Worker Dormitory | Plinth Beam RCC | CUM |  | 45.72 | 0 | 0 | 45.72
13 | Worker Dormitory | Floor RCC | CUM |  | 88.03 | 0 | 0 | 88.03
14 | Worker Dormitory | Masonry Above GB | CUM | 130 | 86.294 | 0 | 0 | 86.294
15 | Worker Dormitory | Masonry above PB | CUM |  | 16.168 | -0.002 | 0 | 16.17
16 | Worker Dormitory | Plinth Plaster | SMT | 5235 | 92.29 | 32.79 | 15 | 74.5
17 | Worker Dormitory | Footing Shuttering | SMT | 1075 | 441.908 | 0 | 0 | 0
18 | Worker Dormitory | Padestal Upto Plinth Top Shuttering | SMT |  | 664 | 0 | 0 | 664
19 | Worker Dormitory | GB Shuttering | SMT |  | 142.938 | 0 | 0 | 142.85
20 | Worker Dormitory | Plinth Beam Shuttering | SMT |  | 387.1 | 0 | 0 | 387.1
21 | Worker Dormitory | Floor RCC Shuttering | SMT |  | 15.3 | 0 | 0 | 15.3
22 | Worker Dormitory | Plinth to GF slab column shuttering | SQM | 1680 | 427.55 | 0 | 0 | 427.554
23 | Worker Dormitory | GF beam shuttering | SQM |  | 700.59 | 0 | 0 | 700.59
24 | Worker Dormitory | GF Slab shuttering | SQM |  | 664.26 | 0 | 0 | 664.23
25 | Worker Dormitory | GF staircase shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
26 | Worker Dormitory | GF lintel shuttering | SQM |  | 67.99 | 0 | 0 | 56
27 | Worker Dormitory | Plinth to GF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 32.82
28 | Worker Dormitory | GF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.75
29 | Worker Dormitory | GF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.98
30 | Worker Dormitory | GF staircase concrete | CUM |  | 8.53 | 0 | 0 | 8.52
31 | Worker Dormitory | GF lintel Concrete | CUM |  | 3.91 | 0 | 0 | 2
32 | Worker Dormitory | Brick masonary GF (230 mm) | CUM | 80 | 73.48 | 20 | 7 | 43.86
33 | Worker Dormitory | Brick masonary GF (115 mm) | SMT | 1170 | 768 | 100 | 10 | 356.26
34 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 1733.79 | 600 | 301 | 663
35 | Worker Dormitory | Flooring | SMT | 830 | 841.16 | 100 | 55.15 | 55.15
36 | Worker Dormitory | Skirting | RMT | 1865 | 1859.2 | 100 | 45 | 45
37 | Worker Dormitory | GF to FF slab column shuttering | SQM | 1680 | 439.913 | 100 | 21.32 | 336.32
38 | Worker Dormitory | FF beam shuttering | SQM |  | 700.59 | 0 | 0 | 701
39 | Worker Dormitory | FF Slab shuttering | SQM |  | 664.26 | 0 | 0 | 664.26
40 | Worker Dormitory | FF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
41 | Worker Dormitory | FF lintel shuttering | SQM |  | 67.99 | 60 | 29 | 29
42 | Worker Dormitory | GF to FF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 25.81
43 | Worker Dormitory | FF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
44 | Worker Dormitory | FF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
45 | Worker Dormitory | FF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
46 | Worker Dormitory | FF lintel Concrete | CUM |  | 3.91 | 0 | 0 | 0
47 | Worker Dormitory | Brick masonary FF (230 mm) | CUM | 80 | 73.48 | 0 | 28.63 | 20
48 | Worker Dormitory | Brick masonary FF (115 mm) | SMT | 1170 | 768 | 0 | 174.55 | 300
49 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 1733.79 | 0 | 0 | 0
50 | Worker Dormitory | Flooring | SMT | 830 | 841.16 | 0 | 0 | 0
51 | Worker Dormitory | Skirting | RMT | 1865 | 1859.2 | 0 | 0 | 0
52 | Worker Dormitory | FF to SF slab column shuttering | SQM | 1680 | 439.913 | 0 | 0 | 101.99
53 | Worker Dormitory | SF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 310.94
54 | Worker Dormitory | SF beam shuttering | SQM |  | 700.59 | 0 | 0 | 57.39
55 | Worker Dormitory | SF Slab shuttering | SQM |  | 664.26 | 0 | 0 | 57.39
56 | Worker Dormitory | FF to SF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 25.415
57 | Worker Dormitory | SF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
58 | Worker Dormitory | SF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
59 | Worker Dormitory | SF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
60 | Worker Dormitory | SF to TF slab column shuttering | SQM | 1680 | 439.913 | 212 | 188.42 | 286.42
61 | Worker Dormitory | TF Staircase Shuttering | SQM |  | 57.39 | 30 | 30 | 30
62 | Worker Dormitory | TF beam shuttering | SQM |  | 700.59 | 400 | 350 | 350
63 | Worker Dormitory | TF Slab shuttering | SQM |  | 664.26 | 400 | 180 | 180
64 | Worker Dormitory | SF to TF slab column concrete | CUM | 210 | 32.822 | 30 | 18 | 20.58
65 | Worker Dormitory | TF Staircase Concrete | CUM |  | 8.53 | 5 | 2.1 | 2.1
66 | Worker Dormitory | TF beam Concrete | CUM |  | 61.76 | 0 | 0 | 0
67 | Worker Dormitory | TF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 0
Weekly planned Qty. | (Multiple Items)
Weekly actual Qty. | (Multiple Items)
Activity | Sum of Weekly planned Qty. | Sum of Weekly actual Qty. | Sum of Total Achieved Qty. |  | Row Labels | Sum of Weekly planned Qty. | Sum of Weekly actual Qty.
Brick masonary GF (115 mm) | 100 | 10 | 356.26 |  | CUM | 54.998 | 55.73
Brick masonary GF (230 mm) | 20 | 7 | 43.86 |  | RMT | 100 | 45
FF lintel shuttering | 60 | 29 | 29 |  | SMT | 832.79 | 555.7
Flooring | 100 | 55.15 | 55.15 |  | SQM | 1202 | 798.74
GF to FF slab column shuttering | 100 | 21.32 | 336.32 |  | Grand Total | 2189.788 | 1455.17
Internal Plaster | 600 | 301 | 663
Plinth Plaster | 32.79 | 15 | 74.5
SF to TF slab column concrete | 30 | 18 | 20.58
SF to TF slab column shuttering | 212 | 188.42 | 286.42
Skirting | 100 | 45 | 45
TF beam shuttering | 400 | 350 | 350
TF Slab shuttering | 400 | 180 | 180
TF Staircase Concrete | 5 | 2.1 | 2.1
TF Staircase Shuttering | 30 | 30 | 30
Grand Total | 2189.79 | 1251.99 | 2472.19
Manually
Activity | Sum of Weekly planned Qty. | Sum of Weekly actual Qty. | % Completed
Brick masonary GF (115 mm) | 100 | 10 | 10%
Brick masonary GF (230 mm) | 20 | 7 | 35%
FF lintel shuttering | 60 | 29 | 48.33%
Flooring | 100 | 55.15 | 55.15% |  | Row Labels | Sum of As per GFC total Quantity | Sum of Total Achieved Qty.
GF to FF slab column shuttering | 100 | 21.32 | 21.32% |  | CUM | 4929.857 | 4644.248
Internal Plaster | 600 | 301 | 50.17% |  | RMT | 3718.4 | 45
Plinth Plaster | 32.79 | 15 | 45.75% |  | SMT | 8429.436 | 2658.16
SF to TF slab column concrete | 30 | 18 | 60% |  | SQM | 7572.229 | 5067.864
SF to TF slab column shuttering | 212 | 188.42 | 88.88% |  | Grand Total | 24649.922 | 12415.272
Skirting | 100 | 45 | 45%
TF beam shuttering | 400 | 350 | 87.5%
TF Slab shuttering | 400 | 180 | 45%
TF Staircase Concrete | 5 | 2.1 | 42%
TF Staircase Shuttering | 30 | 30 | 100%
Manually
Type | Sum of As per GFC total Quantity | Sum of Total Achieved Qty.
CUM | 4929.857 | 4644.248
Weekly planned Qty. | (Multiple Items)
Activity | Planned Start Date by Contractor | Sum of % Planned Against Balance Qty | Sum of % Achieved Against Actual Qty | Sum of % Completed (Total against the GFC )2
Brick masonary FF (115 mm) | 2025-12-11 | 39.06% | 22.73% | 22.73%
Brick masonary FF (230 mm) | 2025-12-11 | 27.22% | 38.96% | 38.96%
Brick masonary GF (115 mm) | 2025-12-11 | 23.71% | 2.371% | 46.39%
Brick masonary GF (230 mm) | 2025-12-11 | 54.61% | 19.12% | 59.69%
FF lintel shuttering | 2025-12-11 | 88.25% | 42.65% | 42.65%
Flooring | 2025-12-11 | 11.89% | 6.556% | 6.556%
GF to FF slab column shuttering | 2025-12-11 | 80.06% | 17.07% | 76.45%
Internal Plaster | 2025-12-11 | 43.74% | 21.94% | 38.24%
Plinth Plaster | 2025-12-11 | 100% | 45.75% | 80.72%
SF to TF slab column concrete | 2025-12-11 | 99.2% | 59.52% | 62.7%
SF to TF slab column shuttering | 2025-12-11 | 62% | 55.11% | 65.11%
Skirting | 2025-12-11 | 5.379% | 2.42% | 2.42%
TF beam shuttering | 2025-12-11 | 57.09% | 49.96% | 49.96%
TF Slab shuttering | 2025-12-11 | 60.22% | 27.1% | 27.1%
TF Staircase Concrete | 2025-12-11 | 58.62% | 24.62% | 24.62%
TF Staircase Shuttering | 2025-12-11 | 52.27% | 52.27% | 52.27%
Grand Total |  | 863.3% | 488.1% | 696.6%