## Sheet1
Quality Assurance Plan
Project |  | Cosntruction work Worker Dormitory at Santej |  |  | LEGENDS | [6 empty] | Quality Control Logs
Client |  | Arvind Limited |  |  | BBS - Bar Bending Schedule |  | MTC - Material Test Certificate |  | RCC - Reinforced Cement Concrete |  |  | Legends | yes | Please mark each entry in the log sheet with "Yes" or "No" based on the daily quality activity performed at the site.
Design Consultant |  | A.K. Consultant |  |  | CUM - Cubic Meter |  | PCC - Plain Cement Concrete |  | SQM - Square Meter |  |  |  |  | Ensure that all entries are made on the same day of the activity to maintain accurate records.
PM Consultant |  | Sharnam Project Managemnet Consultants & Co. |  |  | HSE - Health Safety & Environment |  | QA - Quality Assurance |  | TBM - Temporary Bench Mark |  |  |  | No | This log will be reviewed during weekly quality audits, so ensure its completeness and accuracy.
Contractor |  | M/s Bhavna Infra |  |  | IS - Indian Standard |  | QC - Quality Control |  | TPC - Third Party Confirmation |  |  |  |  | At the End of Each Week: 1. Hide the current week’s sheet (Right-click tab > Hide). 2. Duplicate the sheet (Right-click tab > Move or Copy > Create a copy > OK).
Week 50
Sr.No. | Activity | Description of Activity / Material | Frequency of check | Code of Conformance | Test agency | Contractor |  | PMC | CLIENT | Records and documents to be Maintained | Remarks if any | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05
[6 empty] | Performer | Checker | Checker | Checker
1 | Site Survey | Confirmation of Calibrated Equipment | Service agency due date |  | Approved external agency | QC Engr | QC Engr | Review | Random | Calibration Certificate
|  | Building lay out and setback | Every layout | Approved Drawing |  | Surveyor | Site Engr | Witness | Witness | Setting out plan
|  | Bench Mark shifting & TBM Preparation | Once established | Client reference |  | Surveyor | Site engr | Witness | Witness | Level book
2 | Excavation | Required Safety norms coordinate to HSEM Process. | Every foundation and trench |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Disposal of black cotton soil and yellow soil in suggested area | Every foundation and trench | Client reference |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation for completion of survey activities. | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of Layout, alignment and size of excavation | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of underground utilities | Every foundation and trench | Client reference |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of drawing and drawing revision | Every foundation and trench | Updated Drawing Register |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation for joint inspection reports | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
3 | Plain Cement Concrete | Confirmation of location, excavated pit bed, levels, free from slush and well compacted. | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
|  | Confirmation of Layout, alignment and size of excavation | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
|  | Confirmation of formwork | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
|  | Confirmation of drawing and drawing revision | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
|  | Confirmation for joint inspection reports | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
|  | Confirmation of Concrete grade/Nominal Mix | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
|  | Confirmation of required tools and tackles | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
|  | Confirmation of concrete top surface | Every foundation and trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  |  | Yes
4 | Reinforcement | Required Safety norms coordinate to HSEM Process. | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of rolling margin testing | Every consignment | IS-1786 | Site Laboratory | QC/QA Engr | QC/QA Engr | Witness | Random | Work Check List
|  | Chemical Analysis of reinforcement steel | Every lot | IS-432 | Manufacturer Test Certificate | QC/QA Engr | QC/QA Engr | Review | Random | MTC
|  | Physical test of reinforcement steel | Every lot | IS-1786 | Approved external lab | QC/QA Engr | QC/QA Engr | Review | Random | TPC
|  | Confirmation of BBS preparation and approval | Each structure & Element | Approved Drawing & IS 2502 |  | Site Engr | QC Engr | Review | Approve | Bar Bending Schedule
|  | Confirmation of reinforcement Numbers, Shape, Dia, cutting and bending. | Each structure & Element | Approved Drawing & BBS |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation for reinforcement placing | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of clear concrete cover to reinforcement | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of provision for Chairs and spacers( Numbers, Shape, Length and position) | Each structure & Element | Approved Drawing & BBS |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of reinforcement lapping | Each structure & Element | Approved Drawing & IS 456 |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of reinforcement welding | As per requirement | Approved Drawing/ Client reference |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of Binding wire | Once in Every Source | IS 456 | Site Laboratory | QC/QA Engr | QC/QA Engr | Witness | Random | Test Report
5 | Formwork | Required Safety norms coordinate to HSEM Process. | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of level reference. | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for all the plates / plywood, cleaned and polished properly | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of shuttering oil/polish material |  | IS 456 |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for suitability, stability, safety, rigidity of assembled forms | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for alignment, verticality, right angle, and diagonals of shuttering faces | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of shuttering supports and bracings. | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of adequate of concrete cover blocks. | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of cutouts, sleeves and other embedded items to fix with formwork | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of shuttering gapes, joints, holes and tie rods | Each structure & Element | IS 456 & DESIGNER SPECIFICATION |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of deshuttering/form dismantling time duration | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
6 | Concreting | A) Material Confirmation
a. Cement
|  | ● Type of Material |  | Client Reference/ Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Grade of Material |  | Client Reference/ Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Fineness | Once in every lot | IS-4031 part-1, IS 269 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | ● Setting time | Once in every lot | IS-4031 part-4 &5, IS 269 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | ● Soundness | Once in every lot | IS-4031-part3, IS 269 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | ● Compressive strength | Once in every lot | IS-4031-part6, IS 269 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | ● Chemical Composition | Once in every lot | IS code for relevant grade | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
b. Coarse Aggregate
|  | ● Source of Material | Once Initial Start | Client Reference |  | Site Engr | QC Engr | Review | Approve
|  | ● Incoming material test before unloading ( over size/ finer ) | Every Consignment |  |  | Site Engr | QC Engr | Witness | Random | Register/Note
|  | ● Sieve analysis | Every 200 cum | IS-2386 Part-1, IS 383 | Site Lab/Approved external lab | Site Engr | QC Engr | Witness | Random | Test Report
|  | ● Impact value | Once in every source | IS-2386 Part-IV, IS 383 | Approved external lab | Site Engr | QC Engr | Witness | Random | TPC
|  | ● Crushing value | Once in every source | IS-2386 , IS 383 | Approved external lab | Site Engr | QC Engr | Witness | Random | TPC
|  | ● Flakiness & Elongation | Every 200 cum | IS-2386 , IS 383 | Site Lab/Approved external lab | Site Engr | QC Engr | Witness | Random | Test Report
|  | ● Specific gravity | Once in every source | IS-2386 , IS 383 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Abrasion Value | Once in every source | IS-2386 , IS 383 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Water Absorption | Once in every source | IS-2386 , IS 383 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
c. Fine Aggregate
|  | ● Source of Material | Once Initial Start | Client Reference |  | Site Engr | QC Engr | Review | Approve | Test Report
|  | ● Incoming material test before unloading ( Silt content & deleterious material) | Every Consignment | IS-383 | Site Lab | QA/QC Engr | QA/QC Engr | Witness | Random | Test Report
|  | ● Sieve analysis | Every 200 cum | IS-383 | Site Lab | Site Engr | QC Engr | Witness | Random | Test Report
|  | ● Fineness | Every 200 cum | IS-383 | Site Lab | Site Engr | QC Engr | Witness | Random | Test Report
|  | ● Specific gravity | Once in every source | IS-2386 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Deleterious materials | Once in every source | IS-383 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Water Absorption | Once in every source | IS-383 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Loose Bulk Density | Once in every source | IS-383 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
d. Water
|  | ● pH Value | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Limits of Acidity | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Limits of Alkalinity | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Percentage of solid Organic & inorganic material | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Sulphate | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Chloride | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Suspended Solid | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Color Hazen Units | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
6 | Concreting | ● Odour | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Hardness | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Fluoride | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
|  | ● Turbidity | Once in every source | IS 3025, IS 456 | Approved external lab | Site Engr | QC Engr | Review | Random | TPC
e. Admixture
|  | ● Material | Every Consignment | IS 9103 | Manufacturer | Site Engr | QC Engr | Review | Random | MTC
|  | B) Mix Design/Trial Mix | Once in initial | Client Reference | Site Lab |  |  |  |  | MTC
C) Concrete confirmation
|  | ● Slump Test | Every pour start | IS-516 | Site Lab | Site Engr | QC Engr | Witness | Random | Concrete log
|  | ● Concrete Compressive Strength check by cube Test |  | IS-456 | Site Lab | Site Engr | QC Engr | Witness | Random | Register/Note
|  | ● Actual Standard Deviation | Once in month |  | Site Lab | Site Engr | QC Engr | Witness | Random | Test Report
D) Pre-Inspection
|  | ● Confirmation of PCC level | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of Reinforcement check points | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of Formwork check points | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of embedded bolts/plates/pipe sleeves, etc. | Each structure & Element | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of material used for concrete | Each structure & Element | Concrete Batch Report |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● All required equipment arrangement |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Conformation of concreting time |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
D) Post-Inspection
|  | ● Confirmation of cube casting & testing | Each structure & Element | IS-456 |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of concrete surface, levels and surface finishing | Each structure & Element |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
7 | Back Filling | Required Safety norms coordinate to HSEM Process.
|  | Confirmation of existing ground level | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of finished ground level for all areas | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for satisfactory stripping of top soil | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for cutting of earth to required level | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of layer by layer filling | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of material quality | Each layer |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of soil MDD and OMC | Once in every source | Morth Specification | Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | TPC
|  | Check for sprinkling of water and adequate rolling ; kindly avoid ware sprinkling for lime-sand filling | Each layer |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for dressing of formed surface upto desired FGL | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of compaction by core cutter testing for soil filling | 1 test / 500 sqm | Morth Specification | Site Lab | QA/QC Engr | QA/QC Engr | Review | Random | Test Report
|  | Confirmation of compaction by sand replacement testing for lime-sand filling | 1 test / 500 sqm | Morth Specification | Site Lab | QA/QC Engr | QA/QC Engr | Review | Random | Test Report
8 | Granular Sub Base for raft, flooring, and road works | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of material source | Once Initial Start | Client Reference |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of location, level and area for GSB | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for cleaning of location | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of layer thickness of GSB | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of required rolling | Each layer |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Visual Confirmation of GSB compacted surface | Each layer |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | GSB Field Density confirmation by Sand replacement test | 1 test / 500 sqm | Morth Specification | Site Lab | QA/QC Engr | QA/QC Engr | Witness | Random | Test Report
|  | Gradation & Moisture Content confirmation for Grade 01 material | 1 test / 200 cum | Morth Specification | Site Lab | QA/QC Engr | QA/QC Engr | Witness | Random | Test Report
|  | Confirmation of Plasticity Index, Standard Proctor Test, CBR, 10% fine value of GSB | Once in every source | Morth Specification | Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | TPC
9 | Wet Mix Macadam for raft, flooring, and road works | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of material source | Once Initial Start | Client Reference |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of location, level and area for WMM | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for cleaning of location | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of layer thickness of WMM | Each layer | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of required rolling | Each layer |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Visual Confirmation of WMM compacted surface | Each layer |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | WMM Field Density confirmation by Sand replacement test | 1 test / 500 sqm | Morth Specification | Site Lab | QA/QC Engr | QA/QC Engr | Witness | Random | Test Report
|  | Gradation confirmation | 1 test / 100 cum | Morth Specification | Site Lab | QA/QC Engr | QA/QC Engr | Witness | Random | Test Report
|  | Flakiness and Elongation value confirmation | Once in every source | Morth Specification | Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | TPC
|  | Confirmation of Abrasion value, Aggregate Impact Value | Once in every source | Morth Specification | Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | TPC
10 | Anti Termite Treatment | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Material physical and chemical properties | Each lot | Manufacturer confirmation | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | Check for required tools and tackles | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for chemical and water proposal | Each structure | IS 6313 |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for hole marking and rate of spray under floor | Each structure | IS 6313 |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of area/location for treatment | Each structure | IS 6313 |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of sufficient chemical and water proposal applied | Each structure | IS 6313 |  | Site Engr | QC Engr | Witness | Random | Work Check List
11 | Masonry Work - Brick/ Concrete Block | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | A) Prior to masonry | [9 empty] | - | - | -
|  | ● Check for area cleaning | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Check for material stacking on site location for use | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Check for material wet surface | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Check for door, window and other opening frame erection or installation completion | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Confirmation of line and level marking for masonry | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Confirmation of mortar proposal | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Confirmation of masonry bond | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Check for bee holes and Weep holes | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | - | - | -
|  | B) During masonry | [9 empty] | - | - | -
|  | ● Confirmation of dimensions | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Confirmation of door, window and other opening size | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Check for margins left for plastering jambs | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Check for plumb, line and levels | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | ● Check for racking of joints to receive plastering or pointing | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | C) After masonry | [9 empty] | - | - | -
|  | ● Check for curing arrangement | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | yes | yes | yes
|  | ● Check for all mortar joints are raked and cleaned | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | yes | yes | yes
|  | ● Check for thee filling of all bee holes | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | yes | yes | yes
|  | ● Check for weep holes are clean and serviceable | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | yes | yes | yes
|  | ● Check that all flatwork has been cleaned and is scraped free of mortar splatters | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | yes | yes | yes
|  | ● Check all waste material has been piled in designated trash area | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | yes | yes | yes
|  | D) Material Confirmation | [9 empty] | - | - | -
|  | Cement | As per concreting item | [8 empty] | Yes | Yes | Yes
|  | Fine Aggregate | As per concreting item | [8 empty] | Yes | Yes | Yes
|  | Water | As per concreting item | [8 empty] | Yes | Yes | Yes
|  | Confirmation of Density in oven dry condition, & Compressive Strength in Mpa for concrete block | 1 test / 5000 no's | IS 2185 | Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | TPC |  | - | - | -
|  | Confirmation of measurement, water absorption, compressive strength in Mpa, effloresces, shrinkage | 1 test / 50000 no's |  | Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | TPC |  | - | - | -
12 | Plastering | Preparatory arrangement of surface preparation like raking of joints, removal of loose mortar and fixing chicken mesh at RCC and Masonry joints ant wetting surface | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | Proportion of cement mortar, mixing and placing in location | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | Checking of alignment, thickness, verticality in line of construction drawing | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
13 | Flooring | Required Safety norms coordinate to HSEM Process.
A) Vacuum Dewatering Floor
|  | ● Check area for cleanliness before concreting | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check for stability of formwork | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check alignment, level, joint sealing | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check for reinforcement size, spacing, location, numbers, overlapping, welding, joint, hooks, bends, and cover | Each structure | Approved Drawing & Approved Bar Bending Schedule |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check process of concrete pouring and grade of concrete | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check quantity of concrete to be poured | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check for workability of concrete at site before pouring | Each structure | Approved Trial Mix |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of equipment and machinery for work | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check for concrete top level | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check for vacuum dewatering as per the specification | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of finished floor surface | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of curing arrangement | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
A) Tile Flooring- Vitrified/Ceramic
|  | ● Check for the tile material approval | Each structure | Client Reference | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | Material Data Sheet
|  | ● Check for the surface cleaning-free from loose mortar, laitance etc. | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Tiles are sound, non-sbsorbingflat and true to shape with straight edge | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check for fixing of level pads | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● All tiles which are used in work have soaked | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of mortar proposal | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Check for bedding of cement mortar properly levelled, temped, and corrected to desire level or thickness | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Bed mortar roughened before laying tile | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of tile laying pattern | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of tile joints | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of floor final level | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | ● Confirmation of epoxy grouting for tile joint filling | Each structure | Client Reference | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | Material Data Sheet
|  | ● Confirmation of curing arrangement | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
14 | Wall tile work-Dado fixing | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QA/QC Engr | Witness | Random | Work Check List
|  | Check for the tile material approval | Each structure | Client Reference | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | Material Data Sheet
|  | Check for the surface cleaning-free from loose mortar, laitance etc. | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Tiles are sound, non-sbsorbingflat and true to shape with straight edge | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for fixing of level pads | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | All tiles which are used in work have soaked | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of mortar proposal | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for bedding of cement mortar properly levelled, temped, and corrected to desire level or thickness | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Bed mortar roughened before laying tile | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of tile laying pattern | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of tile joints | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of top final level | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of epoxy grouting for tile joint filling | Each structure | Client Reference | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | Material Data Sheet
|  | Confirmation of curing arrangement | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of Dimension, surface quality, physical properties, chemical properties | Each lot | IS 15622 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
15 | RCC hume pipe laying | Required Safety norms coordinate to HSEM Process. | Each trench
|  | Confirmation of trench section | Each trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of trench gridline | Each trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of Sand/PCC top level | Each trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of Sand/PCC thickness | Each trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Conformation of pipe diameter | Each trench | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of pipe gradient | Each trench | Approved Drawing | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | Confirmation of pipe condition | Each trench |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of pipe collar thickness and dia | Each Joint | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of pipe and collar fixing mortar proposal | Each Joint | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of backfilling with proper compaction | As per backfilling item
|  | Confirmation of three edge bearing load to produce 0.25mm crack KN/Linear meter | Each lot | IS 458 | Manufacturer / Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | MTC/TPC
|  | Confirmation of unlimited load KN/Linear meter | Each lot | IS 458 | Manufacturer / Approved external lab | QA/QC Engr | QA/QC Engr | Review | Random | MTC/TPC
16 | Grouting of Insert Plate and Anchor Bolts | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for pedestal top surface cleaning | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of formwork | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of grouting material | Each structure | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of grouting material mixing ratio | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of finished grouted surface | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of compressive strength by cube testing | 1 set (6 cubes) / Day for each deferent structure for 7 days and 28 days testing | Manufacturer Technical Data Sheet | Site Lab | QA/QC Engr | QA/QC Engr | Review | Random | Test Report
17 | Painting | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | A) Application of white putty | [9 empty] | - | - | -
|  | Check for the surface cleaning from all masking tape, loos mortar, etc. | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | Confirmation of material | Each lot | Client Reference | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | Yes | Yes | Yes
|  | Confirmation of material mixing according to manufacturer specification | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | Confirmation of 1st coat application | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | Confirmation of application and covered all joints like slab and beam, column and beam | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | Yes | Yes | Yes
|  | confirmation of glass paper application before start second coat | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | - | - | -
|  | confirmation of final finishing | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | - | - | -
|  | Confirmation of tensile adhesion test @ 28 days | Each lot | EN 1348 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | - | - | -
|  | Confirmation of compression adhesion test @ 28 days | Each lot | EN 196 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | - | - | -
|  | Confirmation of initial and final setting setting time | Each lot | EN 196 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | Yes | Yes | Yes
|  | confirmation of water capillary absorption, 30min 28 days | Each lot | Karsten Tube | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | - | - | -
|  | Confirmation of water retentively | Each lot | DIN 18555-7 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | - | - | -
|  | B) Application of paint | [9 empty] | - | - | -
|  | Confirmation of material with requires shad/RAL no. | Each lot | Client Reference | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | YES | YES | YES
|  | Check for the surface cleaning from all masking tape, loos mortar, etc. | Each structure |  |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | YES | YES | YES
|  | Confirmation of marking for 1st coat, 2nd coat, & finish coat | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | YES | YES | YES
|  | Check for time between paint deferent coats | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | - | - | -
|  | Confirmation of final coat finishing and shad | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | - | - | -
|  | Check for flaking /cracking /Sagging /Blistering | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | YES | YES | YES
|  | Check for stick for foreign matter | Each structure | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List |  | - | - | -
|  | Confirmation of physical and chemical properties | Each lot | Manufacturer Specification | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC |  | - | - | -
18 | Paver Block Laying | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for sand bed thickness |  | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for paver block laying pattern |  | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check for paver block top finished level |  | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of compressive strength | Each lot | IS 15658 | Site Lab | QA/QC Engr | QA/QC Engr | Review | Random | Test Report
|  | Confirmation of dimension | Each lot | IS 15658 | Site Lab | QA/QC Engr | QA/QC Engr | Review | Random | Test Report
|  | Confirmation of water observation | Each lot | IS 15658 | Site Lab | QA/QC Engr | QA/QC Engr | Review | Random | Test Report
19 | Water Proofing | Required Safety norms coordinate to HSEM Process. |  |  |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of material | Each lot | Client Reference | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC/Technical Data Sheet
|  | Confirmation of application method |  | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of surface preparation according to manufacturer specification |  | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Check weather all the opening/cutouts are sealed off as per requirement |  | Approved Drawing |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of completion of waterproofing with required coats/application of material up to required level/depth before expedite further activity |  | Manufacturer Technical Data Sheet |  | Site Engr | QC Engr | Witness | Random | Work Check List
|  | Confirmation of material physical and chemical properties | Each lot | Manufacturer Technical Data Sheet | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC/Technical Data Sheet
20 | Structural Steel | Chemical Test : |  |  | Manufacturer
|  | 1. Carbon | Brand source change | IS Code of Testing 1608 IS 1599,IS 228 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | 2. Sulpher | Brand source change | IS Code of Testing 1608 IS 1599,IS 228 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | 3. Phosphorous | Brand source change | IS Code of Testing 1608 IS 1599,IS 228 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
Physical Test :
|  | 1. 0.2% Proof Stress | Brand source change | IS Code of Testing 1608 IS 1599,IS 229 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | 2. Ultimate Tensile Stress | Brand source change | IS Code of Testing 1608 IS 1599,IS 230 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | 3. Elongation | Brand source change | IS Code of Testing 1608 IS 1599,IS 231 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | 4. Bend Test | Brand source change | IS Code of Testing 1608 IS 1599,IS 232 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
|  | 5.Nominal Mass | Brand source change | IS Code of Testing 1608 IS 1599,IS 233 | Manufacturer | QA/QC Engr | QA/QC Engr | Review | Random | MTC
21 | Mix Design | Site Mix
|  | M-10 | Once in every source | IS456: 2000 , IS:10262 :2009 | Site lab | Site Engr | QA/QC Engr | Review | Random | TPC
|  | M-15 | Once in every source | IS456: 2000 , IS:10262 :2009 | Site lab | Site Engr | QA/QC Engr | Review | Random | TPC
|  | M-20 | Once in every source | IS456: 2000 , IS:10262 :2009 | Site lab | Site Engr | QA/QC Engr | Review | Random | TPC
|  | M-25 | Once in every source | IS456: 2000 , IS:10262 :2009 | Site lab | Site Engr | QA/QC Engr | Review | Random | TPC
|  | M-30 | Once in every source | IS456: 2000 , IS:10262 :2009 | Site lab | Site Engr | QA/QC Engr | Review | Random | TPC
Ready Mix Concrete
|  | M-7.5 | Once in every source | IS:10262 :2009 | Manufacturer |  | QA/QC Engr | Review | Random | TPC & MTC
|  | M-10 | Once in every source | IS:10262 :2009 | Manufacturer |  | QA/QC Engr | Review | Random | TPC & MTC
|  | M-15 | Once in every source | IS:10262 :2009 | Manufacturer |  | QA/QC Engr | Review | Random | TPC & MTC
|  | M-20 | Once in every source | IS:10262 :2009 | Manufacturer |  | QA/QC Engr | Review | Random | TPC & MTC
|  | M-25 | Once in every source | IS:10262 :2009 | Manufacturer |  | QA/QC Engr | Review | Random | TPC & MTC
|  | M-30 | Once in every source | IS:10262 :2009 | Manufacturer |  | QA/QC Engr | Review | Random | TPC & MTC

## Sheet2
Activity | Description of Activity / Material | Frequency of check | Code of Conformance | Test agency
Reinforcement | Confirmation of rolling margin testing | Every consignment | IS-1786 | Site Laboratory
| Chemical Analysis of reinforcement steel | Every lot | IS-432 | Manufacturer Test Certificate
| Physical test of reinforcement steel | Every lot | IS-1786 | Approved external lab
Cement | ● Type of Material |  | Client Reference/ Approved Drawing
| ● Grade of Material |  | Client Reference/ Approved Drawing
| ● Fineness | Once in every lot | IS-4031 part-1, IS 269 | Manufacturer
| ● Setting time | Once in every lot | IS-4031 part-4 &5, IS 269 | Manufacturer
| ● Soundness | Once in every lot | IS-4031-part3, IS 269 | Manufacturer
| ● Compressive strength | Once in every lot | IS-4031-part6, IS 269 | Manufacturer
| ● Chemical Composition | Once in every lot | IS code for relevant grade | Manufacturer
Coarse Aggregate | ● Source of Material | Once Initial Start | Client Reference
| ● Incoming material test before unloading ( over size/ finer ) | Every Consignment
| ● Sieve analysis | Every 200 cum | IS-2386 Part-1, IS 383 | Site Lab/Approved external lab
| ● Impact value | Once in every source | IS-2386 Part-IV, IS 383 | Approved external lab
| ● Crushing value | Once in every source | IS-2386 , IS 383 | Approved external lab
| ● Flakiness & Elongation | Every 200 cum | IS-2386 , IS 383 | Site Lab/Approved external lab
| ● Specific gravity | Once in every source | IS-2386 , IS 383 | Approved external lab
| ● Abrasion Value | Once in every source | IS-2386 , IS 383 | Approved external lab
| ● Water Absorption | Once in every source | IS-2386 , IS 383 | Approved external lab
Fine Aggregate | ● Source of Material | Once Initial Start | Client Reference
| ● Incoming material test before unloading ( Silt content & deleterious material) | Every Consignment | IS-383 | Site Lab
| ● Sieve analysis | Every 200 cum | IS-383 | Site Lab
| ● Fineness | Every 200 cum | IS-383 | Site Lab
| ● Specific gravity | Once in every source | IS-2386 | Approved external lab
| ● Deleterious materials | Once in every source | IS-383 | Approved external lab
| ● Water Absorption | Once in every source | IS-383 | Approved external lab
| ● Loose Bulk Density | Once in every source | IS-383 | Approved external lab
Water | ● pH Value | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Limits of Acidity | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Limits of Alkalinity | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Percentage of solid Organic & inorganic material | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Sulphate | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Chloride | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Suspended Solid | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Color Hazen Units | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Odour | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Hardness | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Fluoride | Once in every source | IS 3025, IS 456 | Approved external lab
| ● Turbidity | Once in every source | IS 3025, IS 456 | Approved external lab
Admixture | ● Material | Every Consignment | IS 9103 | Manufacturer
Concrete confirmation | ● Slump Test | Every pour start | IS-516 | Site Lab