## DCI
ARVIND LIMTED : DRAWING REGISTER
DISCIPLINE | BUILDING/AREA | DWG. NO. | CONSULTANT DRW. NO. | TITLE | DATES RECEIVED BY THE CONSULTANT | R0 | R1 | R2 | R3 | R4 | R5 | TOTAL | R0 | R1 | R2 | R3 | R4 | R5
Architecture Drawing
A-01 | GENERAL | A-01 |  | Area diagram | 2025-07-18 | R0: 2025-07-18; R1: 2025-08-02 | 2 | 1 | 1 | 0 | 0 | 0 | 0
A-02 | GENERAL | A-02 |  | Site Layout Option-04 | 2025-07-18 | R0: 2025-09-29; R1: 2025-11-06 | 2 | 1 | 1 | 0 | 0 | 0 | 0
A-03 | GENERAL | A-03 |  | Revised plan for dormitory | 2025-07-18 | R0: 2025-07-18; R1: 2025-09-05 | 2 | 1 | 1 | 0 | 0 | 0 | 0
A-04 | Master Layout Plan | A-04 |  | Site boundaries, access, services |  | R1: 2025-09-05 | 1 | 0 | 1 | 0 | 0 | 0 | 0
A-05 | Area Statement | A-05 |  | Floor-Wise BUA/FAR/FSI | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
A6–A11 | Floor Plans (GF to 4F + Terrace) | A6–A11 |  | Room layout, shafts, corridor widths | 2025-09-10 | 2025-09-05 | 2025-11-06 | 2025-11-18 | 2025-12-03 | 2026-01-07 |  | 5 | 1 | 1 | 1 | 1 | 1 | 0 |  | 0.79412
A12–A15 | Elevations (North, East, South, West) | A12–A15 |  | Façade, window alignment, height | 2025-09-25 | R0: 2025-09-05; R1: 2025-11-18 | 2 | 1 | 1 | 0 | 0 | 0 | 0 |  | 79.4118
A-15.1 | Elevations | A-15.1 | G.A.~ 04 | ELEVATION.~ A for DORMITORY BUILDING. |  | R0: 2025-09-09; R1: 2025-11-18 | 2 | 1 | 1 | 0 | 0 | 0 | 0
A16–A17 | Sections (AA, BB) | A16–A17 |  | Vertical height, structural cut | 2025-09-25 | R0: 2025-09-05; R1: 2025-11-18 | 2 | 1 | 1 | 0 | 0 | 0 | 0
A18 | Door/Window Schedule | A18 |  | Type, sizes, opening direction | 2025-09-25 | 2025-09-05 | 2025-11-06 | 2025-11-18 | 2025-12-03 |  |  | 4 | 1 | 1 | 1 | 1 | 0 | 0
A19 | Staircase Plan & Details | A19 |  | Riser, tread, railing detail | 2025-09-25 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
A20 | Typical Toilet Layout | A20 |  | Plumbing point, tile zone, partition | 2025-09-25 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
A21–A24 | Toilet Elevations (4 Sides) | A21–A24 |  | Tile layout, mirror, tap fittings | 2025-09-25 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
A25–A31 | Finishing Layouts (GF–4F) | A25–A31 |  | Floor finish types, borders, skirting | 2025-09-25 | R0: 2025-11-18 | 1 | 1 | 0 | 0 | 0 | 0 | 0
A32 | Finishing Schedule – Room-wise | A32 |  | Wall/ceiling/floor finish, paint codes | 2025-09-25 | R0: 2025-11-29 | 1 | 1 | 0 | 0 | 0 | 0 | 0
A33 | Fire Evacuation Plan | A33 |  | Fire exits, signage, assembly point | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
A34 | Floor Build-up Section (typical) | A34 |  | Slab + screed + tile + skirting buildup | 2025-09-25 | R0: 2025-08-08; R1: 2025-08-20 | 2 | 1 | 1 | 0 | 0 | 0 | 0
Structure Drawing
ST-01 | Dormitory | ST-01 |  | Column Location | 2025-07-18 | R0: 2025-07-18; R1: 2025-07-22; R2: 2025-07-23 | 3 | 1 | 1 | 1 | 0 | 0 | 0
ST-01 | Dormitory | ST-01 |  | Column Location | 2025-07-18 | R0: 2025-07-18; R1: 2025-07-22; R2: 2025-07-23 | 3 | 1 | 1 | 1 | 0 | 0 | 0
ST-02 | Dormitory | ST-02 |  | Schedule of column | 2025-07-18 | R0: 2025-07-18; R1: 2025-07-22; R2: 2025-07-23 | 3 | 1 | 1 | 1 | 0 | 0 | 0
ST-03 | Dormitory | ST-03 |  | Typical footing section | 2025-07-18 | R0: 2025-07-18; R1: 2025-07-22; R2: 2025-07-23 | 3 | 1 | 1 | 1 | 0 | 0 | 0
ST-04-12 | Dormitory | ST-04-12 |  | Combined foundation detail for C1,C2,C3 | 2025-07-18 | R0: 2025-07-18; R1: 2025-07-22; R2: 2025-07-23 | 3 | 1 | 1 | 1 | 0 | 0 | 0 |  | 0.96552
S-05 | Design Basis Report | S-05 |  | Load assumptions, codes, seismic zone | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96.5517
S-06 | Wall Foundation detail | ST-04 |  | Bar spacing, lap, type | 2025-08-08 | R0: 2025-08-08 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S-07 | Ground & Plinth beam Layout | ST-01 |  | Beam spans, support conditions | 2025-08-08 | R0: 2025-08-08; R1: 2025-08-20 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-08 to S-10 | Ground & Plinth beam Reinforcement | ST-02 to 04 |  | Top/bottom steel, stirrups | 2025-08-08 | R0: 2025-08-08; R1: 2025-08-20 | 2 | 1 | 1 | 0 | 0 | 0 | 0
ST-10.1 | Column Details Schudle | ST-14 |  | SCHEDULE OF COLUMN'S REDUCTION DETAIL.from PLINTH Lvl. to TOP SLAB Lvl. |  | R0: 2025-09-05 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S-10.1 | Stair Detail | GF-06 |  | R.C.C. STAIR DETAIL.Plinth Lvl. to G.F.SLAB Top Lvl |  | R0: 2025-09-11 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S-11 | Flooring Section at Plinth | S-11 |  | PCC, mortar, tile build-up | 2025-08-20 | R0: 2025-08-08; R1: 2025-08-20 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-12 to S-16 | Slab & Beam Layouts (GF to 4F) | S-12 to S-16 |  | Beam/slab grid, spans | 2025-09-02 | R0: 2025-09-15 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S-12 | Slab & Beam Layouts (GF to 4F) | S-12 | ST.~ G.F.- 01 | GROUND FLOOR SLAB TOP Lvl. Lay out. PLAN.+3150 Lvl. UN FINISH LVL. | 2025-09-02 | R0: 2025-09-15; R1: 2025-12-03 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-13 | Slab & Beam Layouts (GF to 4F) | S-13 | ST.~ G.F.- 02 | GROUND FLOOR SLAB BEAM DETAILS ,+3150 Lvl. UN FINISH LVL. | 2025-09-02 | R0: 2025-09-15; R1: 2025-12-03 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-14 | Slab & Beam Layouts (GF to 4F) | S-14 | ST.~ G.F.- 03 | GROUND FLOOR SLAB BEAM DETAILS +3150 Lvl. UN FINISH LVL. | 2025-09-02 | R0: 2025-09-15; R1: 2025-12-03 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-15 | Slab & Beam Layouts (GF to 4F) | S-15 | ST.~ G.F.- 04 | GROUND FLOOR SLAB BEAM DETAILS , +3150 Lvl. UN FINISH LVL. | 2025-09-02 | R0: 2025-09-15; R1: 2025-12-03 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-16 | Slab & Beam Layouts (GF to 4F) | S-16 | ST.~ G.F.- 05 | GROUND FLOOR SLAB BEAM DETAILS , +3150 Lvl. UN FINISH LVL. | 2025-09-02 | R0: 2025-09-15; R1: 2025-12-03 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-17 to S-21 | Slab & Beam Reinforcement | S-17 to S-21 |  | Bar dia, stirrup spacing | 2025-09-02 | R0: 2025-09-15; R1: 2025-12-03 | 2 | 1 | 1 | 0 | 0 | 0 | 0
S-22 | Staircase RCC Details | S-22 | ST.~ G.F.- 06 | Waist slab, landing, reinforcement | 2025-09-06 | R0: 2025-09-10 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S-23 | Stair Cabin and Overhead Tank RCC Detail | S-23 | ST.~ T.F.- 01 to 05 | Slab/beam for stair cabin and tank support | 2025-09-18 | R0: 2025-12-15 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S-24 | Typical RCC Floor Section | S-24 | ST.~ G.F.- 01 to 05 | Slab thickness, beam depth | 2025-09-02 | R0: 2025-09-15 | 1 | 1 | 0 | 0 | 0 | 0 | 0
S-25 | U.G.WATER TANK & PUMP ROOM Layout | S-25 | ST-01 | U.G.WATER TANK Foundation Layout |  | R0: 2025-11-01; R1: 2025-12-15; R2: 2026-04-06 | 3 | 1 | 1 | 1 | 0 | 0 | 0
S-26 | U.G Tank Section | S-26 | ST-02 | U.G.WATER TANK (SECTION A-A AND B-B) |  | 2025-11-01 | 2025-12-15 | 2026-01-13 | 2026-01-20 | 2026-01-30 |  | 5 | 1 | 1 | 1 | 1 | 1 | 0
S-27 | Compound Wall Plan & Details | S-27 |  | Compound Wall Layout & Details |  | R0: 2026-01-22; R1: 2026-02-27 |  | 1
S-28 | Typical lintel details | S-28 | Lint-01 | Typical floor lintel layout & details |  | R0: 2025-11-18; R1: 2025-12-03 |  | 1
S-29 | Sockpit and Ceptic Tank details | S-29 |  | Plan and sectional details |  | R0: 2026-02-14
S-30 | Road Layout And Cross Section | S-30 |  | Plan and sectional details |  | R0: 2026-02-14
C. Electrical Drawings
E1 | Power Layout – Floor-wise | E-01 |  | Power socket layout, DB |  | R0: 2026-01-17 | 1 | 1 | 0 | 0 | 0 | 0 | 0
E2 | Lighting Layout – Floor-wise | E-02 |  | Switchboard, lights |  | 2025-11-10 | 2025-11-25 | 2026-01-17 | 2026-01-30 |  |  | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 1
E3 | Rising Main Single Line Diagram | E-03 |  | Main cable route |  | R0: 2025-11-25; R1: 2026-01-17; R2: 2026-01-30 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 100
E4 | Panel Room Layout & Detail | E-04 |  | Panel size, breaker chart |  | R0: 2026-01-17 | 1 | 1 | 0 | 0 | 0 | 0 | 0
E5 | External Area lighting & Earthing Layout | E-05 |  | Street lights,Earth pit, GI strip routing |  | R0: 2025-11-25; R1: 2026-01-17 | 2 | 1 | 1 | 0 | 0 | 0 | 0
E6 | Transformer Layout (if any) | E-06 |  | HT Panel & Transformer |  | R0: 2026-01-17 | 1 | 1 | 0 | 0 | 0 | 0 | 0
D. Plumbing Drawings
P1 | Ground Fllor | P-01 |  | CP piping, riser line |  | R0: 2025-11-11; R1: 2026-02-03; R2: 2026-03-02 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 1
P2 | Typical Floor | P-02 |  |  |  | R0: 2025-11-14; R1: 2025-11-17; R2: 2025-12-09 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 100
P3 | Terrace Floor | P-03 |  | Soil, waste & vent line |  | R0: 2025-11-14; R1: 2025-11-22; R2: 2025-12-09 | 3 | 1 | 1 | 1 | 0 | 0 | 0
E. Fire Drawing
F1 | Ground Floor Layout | 25-101-DOR-MEC-GF-R1-10A |  | Layout |  | R0: 2025-11-11 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1
F2 | First Fllor Layout | 25-101-DOR-MEC-FF-R1-10A |  | Layout |  | R0: 2025-11-14 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 100
F3 | Second Fllor Layout | 25-101-DOR-MEC-SF-R1-10A |  | Layout |  | R0: 2025-11-14 | 1 | 1 | 0 | 0 | 0 | 0 | 0
F4 | Third Fllor Layout | 25-101-DOR-MEC-3rdF-R1-10A |  | Layout |  | R0: 2025-11-14 | 1 | 1 | 0 | 0 | 0 | 0 | 0
F5 | Fourth Floor | 25-101-DOR-MEC-FF-R1-10A |  | Layout |  | R0: 2025-11-14 | 1 | 1 | 0 | 0 | 0 | 0 | 0
[12 empty] | 100 | 50 | 32 | 14 | 4 | 2 | 0
Summary Of Drawings
Total Released Drawings R0 | 50
Total Released Drawings R1 | 32 | [18 empty] | 0.79327
Total Released Drawings R2 | 14
Total Released Drawings R3 | 0
Total Released Drawings R4 | 0
Total Released Drawings R5 | 0