## Hinderance Register
Hinderance Register
Sr. No | Description of Hindrance | Location | Work affected | Correspondence | Type of Hindrance | Date of Occurrence | Date Resolved | No. of Days | Critical Activity affected | Baseline Start Date | Schedule Impact | Delay Type | Actual Impact | Accountable | Status | Description of Resolution | Remarks
1 | Non-availability of updated and approved drawings is causing delays in construction activities and may lead to execution errors due to outdated design references. Immediate action is required to provide the latest drawings. | Infra | Site activity | On mail | Work in Progress | 2025-07-22 | 2025-07-23 | 1 | Constrcution Activity | 2025-07-22 | 10 days | Non-overlapping Delay |  | Client | Resolved | Updated Drawings Received |  | #REF! | #REF!
2 | Non availability of permanent power connection for 3 phase power supply and borewell for construction purposes at site may affect overall activities at site. Immediate action reqquired for permanent power supply and borewell construction. | Infra | Site activity | on site | - | 2025-07-28 |  |  | Constrcution Activity | 2025-07-28 | 12 Days | Non-overlapping Delay |  | Client | Resolved
3 | Container office at site for office and documentation works required at urgent basis. Immediate action requred to setup office at site. | site office | documentation | on site | - | 2025-07-28 | 2025-08-04 |  | documentation | 2025-07-28 | 2 days | Non-overlapping Delay |  | Client | Resolved
4 | Ground beam and plinth beam drawings are required for making BBS and procuring steel. Drawings are demanded from last 15 days its required on urgent basis | Infra | Steel Procurement & Site activity | Consultant | - | 2025-08-05 | 2025-08-08 |  | Constrcution Activity | 2025-08-05 | 2 days | Non-overlapping Delay |  | consultant | Resolved
1 | In spite of repeated instructions and assurances, the manpower deployment for finishing work has not been augmented by M/s Bhavana Infra Projects Pvt. Ltd., leading to delays in planned activities and affecting the overall completion timeline | Infra | Site activity | on site | - | 2025-08-18 |  |  | Constrcution Activity | 2025-08-17 | 30 Days | Non-overlapping Delay |  | Contractor | Open
6 | as instructed before the detailed delay mitigation plan shoud be developed and needs to submit by contractor. As it still yet receive from contractor | Infra | Site activity | on site | - | 2025-08-18 |  |  | Constrcution Activity | 2025-08-17 | 2 Days | Non-overlapping Delay |  | Contractor | Resolved
2 | all drawings should be delivered on time as per schedule. Delay in drawings can lead to overall construction project delays. Remaining Drawings are Stair cabin slab with Over Head Water Tank | Infra | Site activity | on site | - | 2025-08-19 |  |  | Constrcution Activity | 2025-08-19 | 15 Days | Non-overlapping Delay |  | Consultant | Close
8 | Due to heavy rains over the past three days, the approach road to the site has become muddy. To improve accessibility, debris will be laid along the road to stabilize the surface and facilitate movement. | Infra | Site activity | on site | - | 2025-08-25 |  |  | Constrcution Activity | 2025-08-25 | 2 Days | Non-overlapping Delay |  | Contractor | Resolved
2 | Firefighting work vendor is still not available at site, which may potentially delay the completion of dependent activities; therefore, timely mobilization of the vendor is essential. | Infra | Site activity | on site | Vendor Onboarding Delays | 2025-10-27 |  |  | Constrcution Activity | 2025-10-27 | - | Non-overlapping Delay |  | Client | Open
4 | Vendor POs are not alloted to all of the vendors. Which is causing delays in timely submission of bills and payment on time. | Infra | Site activity | on site |  | 2025-10-29 |  |  | Billing and Payments | 2025-10-27 | - | Non-overlapping Delay |  | Client | Close
4 | All material procurement approvals shall be shared with the vendor, ensuring that the PMC is kept informed. | Infra | Site activity | on site | - | 2025-10-29 |  |  | Site Execution / Construction Work | 2025-10-27 | - | Non-overlapping Delay |  | Client | Close
3 | The final drawings for external development works—including the septic tank with soak pit, road, and paver block layout and sections—are still pending submission from the design consultant, AK Bhavsar. | Infra | Site activity | on site | - | 2025-11-11 |  |  | Constrcution Activity | 2025-10-28 | - | Non-overlapping Delay |  | Consultant | Close
5 | The required changes for the electrical raising layout, Single Line Diagram (SLD) plan, and wire diagram are still pending submission, which is delaying the final approval and coordination of MEP works on site. | Infra | Site activity | on site | - | 2025-11-11 |  |  | Constrcution Activity | 2025-11-11 | - | Non-overlapping Delay |  | Consultant | Close
4 | The timely completion of all external development activities is being affected due to the delay in onboarding the required vendor. Vendor onboarding is essential to mobilize resources and commence the scheduled works. Any further delay in finalizing and engaging the vendor will directly impact the project timeline and may result in unavoidable delays in completing the external development works. | Infra | Site activity | - | Vendor Onboarding Delays | 2025-12-01 |  |  | Constrcution Activity | 2025-12-01 | - | Non-overlapping Delay |  | Client | Close
5 | Ground Floor Canteen Floor plan is yet to receive. Which is causing delays in completion of ground floor activities. | Infra | Site activity | - | - | 2025-12-24 |  |  | Constrcution Activity | 2025-12-24 | - | Non-overlapping Delay |  | Client | Close
If you want, I can also draft a concise version suitable for a site daily report or hindrance log.
4 | Delay in execution of compound wall work due to non-confirmation of compound wall marking by DILR survey. | Infra | Site activity | on site | - | 2026-01-28 |  |  | Constrcution Activity | 2026-01-28 | - | Non-overlapping Delay |  | Client | Close
1 | Delay in plumbing work due to non-mobilization of adequate manpower by the plumbing vendor, which is consequently affecting progress of dependent activities such as masonry, plastering, and flooring works. | Infra | Site activity | on site | - | 2026-02-10 |  |  | Constrcution Activity | 2026-02-10 | - | Non-overlapping Delay |  | Contractor | Open
4 | Delay in tiling work and dependent activities has been noted on site due to non availability of materials at site due to shortage in supply from manufacturar. Alternative arrangements should be made by Vendor. | Infra | Site activity | on site | Materials procurement delay | 2026-03-17 |  |  | Constrcution Activity | 2026-02-10 | - | Non-overlapping Delay |  | Contractor | Close
0

## Risk Register
Risk ID | Risk Category | Dated Raised | Risk Name | Risk Description | Probability of Risk occuring | Consequence of Risk | Severity | Risk Owner | Miitigation plan | Impact | Target date | Status
1 | General | 2025-07-29 | Contractor Mobilization Delay | The mobilization activities of the appointed civil contractor are progressing at a significantly slower pace than originally planned. Critical tasks such as site establishment, manpower deployment, material procurement, machinery mobilization, safety arrangements, and initial site clearance are either delayed or not being executed efficiently, potentially impacting the timely commencement of construction works. | High | High | High | Bhavna Infra | 1. Immediate Contractor Performance Review Conduct a formal review meeting with the contractor to understand the root causes of the delay. Issue a formal notice highlighting non-performance and requesting a corrective action plan within 48 hours. 2. Revised Mobilization Plan Instruct the contractor to submit a revised mobilization schedule with clear timelines for: Site establishment Manpower deployment (minimum skilled/unskilled workforce numbers) Machinery mobilization (type and number of equipment) Material procurement status (cement, steel, shuttering, etc.) | The delayed mobilization of the civil contractor is directly affecting the project’s baseline schedule. Key early-stage activities such as site establishment, resource deployment, and initial clearance are lagging, which may lead to a cascading delay in construction commencement. This can disrupt the sequencing of dependent works, increase project overheads, compress float in the schedule, and ultimately jeopardize timely project completion, client satisfaction, and cost control. | 2025-08-05 | Close
2 | General | 2025-07-29 | Testing Lab Setup Delay | To ensure adherence to project-specific technical specifications and quality standards, it is essential to establish a fully functional testing laboratory at the project site. The absence or delay in setting up this facility may hinder the timely sampling and testing of critical construction materials such as concrete, cement, aggregates, bricks, steel, and water. This can compromise the quality control (QC) process, delay approvals, and increase the risk of using substandard materials, ultimately affecting the structural integrity, safety, and overall progress of the project. | High | High | High | Bhavna Infra | Include lab setup in the contractor’s mobilization plan with fixed timelines. Pre-appoint a reliable testing agency/vendor. Arrange temporary off-site testing until the on-site lab is ready. Procure key lab equipment in advance. Deploy trained QC personnel early. Establish clear testing and approval protocols. Monitor setup progress regularly and escalate delays promptly. | The absence or delay in establishing a site-based testing laboratory adversely affects the Quality Control (QC) process by delaying timely sampling and testing of key construction materials. This can lead to the inadvertent use of substandard materials, compromise structural integrity, delay approvals, and disrupt project timelines—ultimately impacting safety, quality assurance, and the overall progress and credibility of the project. | 2025-08-05 | Close
3 | General | 2025-07-29 | Delay in Shuttering Material Supply and Site Organization | The shuttering materials required for upcoming PCC and RCC footing concreting works have not been fully supplied, nor are they properly stacked at the designated storage area on site. This delay and disorganization may hinder the concreting schedule and compromise shuttering alignment quality. | High | High | High | Bhavna Infra | Immediate Reconciliation: Check and record missing shuttering materials and inform procurement. Expedite Delivery: Follow up with vendors for urgent supply; arrange from local sources if needed. Organized Stacking: Designate proper stacking areas; assign staff to ensure safe and accessible storage. Work Rescheduling: Adjust site activities to avoid idle time; reuse shuttering from completed areas if possible. Daily Monitoring: Track material availability daily; use checklists to avoid delays.. | The incomplete supply and improper stacking of shuttering materials at the designated storage area can significantly disrupt the construction schedule. Specifically, it may delay the planned PCC and RCC footing concreting works, leading to a cascading effect on subsequent project activities. Additionally, disorganized material handling can compromise the quality and precision of shuttering alignment, potentially resulting in dimensional inaccuracies, structural defects, and rework. This not only affects quality control but may also increase labor costs, reduce overall productivity, and jeopardize project deadlines. | 2025-08-05 | Close
1 | General | 2025-07-29 | The available site manpower is currently insufficient to meet scheduled activity demands, there is insufficiency of masons for masonry and plaster work on site. | It has been observed that the manpower currently available at the site is inadequate to meet the scheduled activity requirements of the project. The contractor has been instructed to mobilize the remaining workforce at the earliest. 8 masons are available on site for masonry and plaster work , which is targeted for 30 nos. | High | High | High | Bhavna Infra | The contractor is required to immediately deploy the necessary manpower to meet current site requirements. | The shortage of manpower at the site is likely to cause significant delays in executing scheduled project activities, disrupting the overall project timeline. This may lead to resource mismanagement, reduced work efficiency, and a cascading impact on dependent tasks. If not resolved promptly, it can also increase project costs due to idle equipment, extended project duration, and potential contractual penalties. | 2025-09-26 | Pending | Medium | Pending
5 | General | 2025-07-29 | Unauthorized Land Encroachment | Use of unauthorized land—whether for parking, material storage, machinery movement, or any other construction-related activity—is strictly prohibited and may result in serious legal and contractual consequences, including penalties, work stoppages, or disputes with landowners or authorities. To mitigate this risk, the approved site boundaries must be clearly demarcated using visible markers, barricades, or fencing. All workers, operators, and site personnel must be informed and routinely guided about the designated work area limits to prevent inadvertent encroachment. | High | High | High | Arvind Limited | Demarcation: Clearly mark site boundaries with barricades, fencing, or signage. Awareness: Brief all workers and staff on approved work limits during induction. Monitoring: Assign a supervisor to regularly inspect site peripheries. Access Control: Restrict and monitor entry/exit points for vehicles and materials. Documentation: Keep updated site layout and record any violations. Enforcement: Stop unauthorized activities immediately and impose penalties if required. | Unauthorized use of land beyond approved site boundaries can lead to legal disputes, regulatory penalties, and contractual violations, potentially resulting in work stoppages, project delays, or eviction orders by local authorities. Such incidents may also damage the client’s reputation, strain relationships with nearby landowners or communities, and lead to financial losses due to fines, litigation, or rework. Additionally, unplanned occupation of external areas poses safety and security risks, and can complicate insurance claims or project audits. | 2025-08-05 | Close | Low
2 | General | 2025-07-29 | Delay in Structural Drawing Release | Ground beam and plinth beam construction drawings are currently pending, which are essential for preparing the Bar Bending Schedule (BBS) and initiating steel procurement. The design consultant has committed to providing the required drawings within two days. Any delay beyond this timeline may lead to procurement hold-ups, reinforcement cutting/fabrication delays, and a potential impact on the construction schedule. | High | High | High | AK.Consultant | Daily follow-up with consultant to ensure timely drawing submission. Start provisional BBS using typical sections if available. Procure buffer stock of standard rebar sizes. Hold coordination meeting to reinforce deadlines. Include 2–3 day buffer in schedule. Escalate if delay exceeds committed timeline. Fast-track BBS and steel cutting upon drawing receipt. | Delay in receiving the ground beam and plinth beam drawings will hinder the preparation of the Bar Bending Schedule (BBS), which in turn will stall steel procurement and reinforcement cutting/fabrication activities. This can disrupt the planned sequence of construction, lead to idle manpower and machinery, increase project costs, and ultimately cause slippage in the overall project timeline. | 2025-08-05 | Close
2 | General | 2025-08-07 | Delay in Footing Work Progress | As our footing work activity is already delayed contractor should makeup the lost time by increasing manpower and productivity. | High | High | High | Bhavna Infra | Due to delays in footing activity, the contractor must take immediate corrective actions to recover lost time: Increase Manpower: Deploy additional skilled/unskilled workers to accelerate progress. Boost Productivity: Work in multiple shifts, streamline tasks, and ensure smooth material flow. Add Resources: Mobilize extra tools, equipment, and machinery as needed. Daily Monitoring: Track progress daily against a revised micro-schedule. Ensure Quality & Safety: Maintain all work standards despite acceleration. Recovery Timeline: Contractor to submit and follow a catch-up plan to align footing activity with the overall project timeline. | This statement places formal responsibility on the contractor for recovering the schedule delay. It emphasizes urgency and suggests proactive measures. | 2025-08-08 | Close
2 | General | 2025-08-12 | Delay In plinth level activity | The mitgation plan target date for completion of the Ground Floor slab RCC work is set for 18th October. Bhavana Infra has been instructed to increase night work hours work and aim for completion by 18th October. | High | High | High | Bhavna Infra | Due to delays in foundation activity, the contractor must take immediate corrective actions to recover lost time and keep the project on track: Increase Manpower: Deploy additional skilled/unskilled workers to accelerate progress. Boost Productivity: Work in multiple shifts, streamline tasks, and ensure smooth material flow. Add Resources: Mobilize extra tools, equipment, and machinery as needed. Daily Monitoring: Day to Day planning should be initiated to mitigate loss time. Ensure Quality & Safety: Maintain all work standards despite acceleration. | This advancement in the completion timeline is expected to significantly improve overall project progress, allowing subsequent activities to begin earlier and reducing the risk of delays in the critical path." | 2025-10-10 | Close
2 | General | 2025-08-07 | Wastage of raw materials and mixing with soil | Raw materials should be stacked at proper cleaned area to decrease wastage and maintain proper quality of materials | High | High | High | Bhavna Infra | Plum concrete should be casted for raw materials stacking | This statement places formal responsibility on the contractor for maintaining quality of raw materials stacked at site. | 2025-08-15 | Close
3 | General | 2025-08-11 | Electrcal Safety | A distribution box shall be securely fixed and installed with all necessary accessories. All connections to equipment must be made using appropriate pin-top plugs to ensure safety, security, and compliance with electrical standards | High | High | High | Bhavna Infra | DB And Pin tops should be provided for safety and security at site | This will ensure a safer working environment, minimize the risk of electrical hazards, and maintain compliance with standard electrical safety regulations, thereby reducing the likelihood of equipment failure or onsite accidents. | 2025-08-10 | Close
6 | General | 2025-08-08 | Hard Barricading for excavated area | As excavated area is deep as 3 meters proper hard barricading should be required for safety of all livelyhood | High | High | High | Bhavna Infra | Provide Barricading of sheets or any similar material | Implementing proper hard barricading around the 3-meter-deep excavated area will significantly enhance site safety, preventing accidental falls and ensuring the protection of workers and nearby personnel | 2025-08-08 | Close
7 | General | 2025-07-28 | Unavailability of permanent Power Supply And Borewell | The ongoing unavailability of a permanent 3-phase power connection and borewell at the construction site is significantly impacting overall site activities. The current temporary power supply is insufficient to support multiple operations, especially during night shifts, leading to delays and inefficiencies. | High | High | High | Arvind Limited | As a mitigation measure, it is recommended to arrange for permanent power supply and borewell construction | Immediate escalation and coordination with relevant authorities and vendors is essential to ensure the swift provision of permanent 3-phase power and borewell facilities, as further delays will critically hinder project progress and timelines. | 2025-08-14 | Close
7 | General | 2025-08-19 | Padestal Conctete Activity Delay | Concrete work for the pedestal must commence at the earliest to mitigate delays in the overall project schedule. | High | High | High | Arvind Limited | Concrete work should start at easrliest | Immediate commencement of concrete work for the pedestal is critical to prevent cascading delays and ensure alignment with the overall project timeline. | 2025-08-21 | Close
5 | General | 2025-08-19 | Drawings shoudld be made available on time. | The design deliverables schedule should be signed off by the consultant, and all design submissions must be delivered on time as per the agreed schedule | High | High | High | Arvind Limited | drawings to be delivered on time | Timely sign-off of the design deliverables schedule by the consultant, along with strict adherence to submission deadlines, is essential to maintain project momentum and avoid schedule slippage | 2025-08-29 | Close
9 | General | 2025-08-26 | Delay in steel procurement | The steel delivery has been delayed due to a production issue at the supplier’s end. | High | High | High | Bhavna Infra | An alternative shoild be arranged to get the steel delivered on site without further delay. | To avoid further project delays, an alternative steel delivery method must be implemented immediately to ensure materials arrive on site without interruption. | 2025-08-29 | Close
10 | General | 2025-08-24 | Waterlogging in excavated area | Due to heavy rains flood water is looged in excavated area. Dewatering should be carried out at earliest | High | High | High | Bhavna Infra | Dewatering should be carried out at the earliest using a mud pump to prevent any impact on site activities and avoid delays. | Immediate dewatering using a mud pump is essential to prevent disruption of site activities and eliminate the risk of project delays. | 2025-08-26 | Close
5 | General | 2025-08-26 | Bricks Procurement Pending | Bhavana Infra should procure bricks that approximate the specified make and standards outlined in the BOQ. This will help ensure timely material availability on site and facilitate the completion of testing as scheduled | High | High | High | Bhavna Infra | first lot of bricks should be delivered earliest so that necessary testing should be carried out. | Timely delivery of the first lot of bricks is crucial to conduct necessary testing without delay and maintain the project schedule. | 2025-08-29
5 | General | 2025-09-01 | Shuttering and steel to be stacked at desired place. | Materials Should not be dumped directly on soil surface. Steel and shuttering materials found layed in mud and soil. | High | High | High | Bhavna Infra | Materials should be stacked at desired place to maintain its quality. | Materials should be stored or stacked at desired place so that no rusting or damage shold be done. Its important to maintain quality of materials. | 2025-09-05
5 | General | 2025-09-02 | PPE Issuance and workerd ID list | Workers safety and ID list with PPE issuance is required for safety and security purposes. | High | High | High | Bhavna Infra | A list with PPE issuance and Workers List with ID needs to be submitted. | A full list should submitted earliest for safety and security. | 2025-09-04
4 | General | 2025-09-05 | Sieve test set not available at site. | Site testing materials(sieve test set) for gradation test not available on site. | High | High | High | Bhavna Infra | Sieve set of different sizes as per requirement should be made available at site. | As sieve set is available on site it would be easier to test materials at site when required. | 2025-09-08 | Close
6 | General | 2025-09-17 | Volume box not available at site | Volume box for preparing mortar for masonry is not available on site. | High | High | High | Bhavna Infra | Volume box for measuring wight of cement and sand should be made available at site. | The provision of a standard volume box at the site has ensured accurate measurement of cement and sand, significantly improving the quality and consistency of the mix. | 2025-09-08
2 | General | 2025-11-04 | Honey Combing in columns and damages to the egdes | During the site visit, it was observed that the quality of the concrete was unsatisfactory, with honeycombing noted on the cast columns | High | High | High | Open | As described on 04.11.2025, the mock-up of column shuttering and the concrete pouring method resulted in an improvement in the quality of the column finish. This method should be strictly followed for every concrete casting. | The method demonstrated on 04.11.2025 has proven to improve column finish quality and must henceforth be followed without deviation for all concrete casting activities. | 2025-11-05 | Close
2 | General | 2025-11-10 | NDT test Confirmation pending by Design Consultant | The 7-day concrete cube test results failed to meet the required strength parameters. Following this, Non-Destructive Testing (NDT) was conducted and all relevant reports and supporting documents were submitted to the design consultant (AK Consultant). However, no comments, approval, or technical confirmation have been received from the consultant. This lack of timely feedback poses a risk to construction progress, quality assurance, and structural safety decision-making. | High | High | High | Bhavna Infra | Sent a formal written reminder requesting immediate review and confirmation of NDT results on urgent basis. | Timely consultant response will allow confirmation of concrete adequacy or the need for corrective action. Reduced risk of structural failure by ensuring decisions are based on verified engineering assessment. Construction delays can be minimized through proactive follow-ups and structured communication. Enhanced quality assurance and compliance by maintaining proper documentation and approval flow. | 2025-11-18 | Pending
3 | General | 2025-11-10 | The erection, provision of proper structural supports, and installation of stair access for the watch tower are still pending. | Since the watch tower is proposed primarily for observation and work tracking purposes, the delay may affect site monitoring efficiency and hinder effective supervision of ongoing construction activities. Limited visibility from ground level could result in reduced oversight of manpower deployment, equipment utilization, and progress tracking. This may lead to coordination challenges, delays in identifying on-site issues, and reduced accuracy in reporting daily work progress. Although the pending erection does not pose a direct structural or safety risk to ongoing works, it impacts project management effectiveness and may indirectly influence overall productivity and schedule adherence. | High | High | High | Bhavna Infra | Prioritize the fabrication and erection of the watch tower to ensure it is completed at the earliest possible stage without compromising safety or quality. Allocate sufficient manpower, equipment, and materials to avoid further delays. | Prioritizing the fabrication and erection of the watch tower, along with adequate allocation of manpower, equipment, and materials, will facilitate timely completion of the structure. This will enhance site visibility and supervision efficiency, improve progress tracking accuracy, and ensure that monitoring activities are conducted safely and effectively without further project delays. | 2025-11-17 | Close
3 | General | 2025-11-11 | Delay in MockUp room activities | Delay in execution of masonry, plaster, plumbing, and finishing works in the mock-up room due to late delivery of materials, unavailability of skilled labour, and concurrent site activities. | High | High | High | Bhavna Infra | 1.Resource Allocation: Mobilize additional skilled labour and subcontractors for masonry, plaster, plumbing, and finishing works. 2. Material Management: Ensure early procurement and onsite availability of all required materials. 3. Scheduling Adjustment: Reschedule activities with overlap where possible, e.g., start plumbing after masonry progress in part of the room. 4. Monitoring & Coordination: Daily progress monitoring and coordination meeting with all trades to fast-track work. | Reduction in overall delay; recovery of 70–80% of lost time. Improved coordination reduces rework and conflicts between trades. Early completion of mock-up allows timely review and approval for main works. | 2025-11-14 | Close
1 | General | 2025-11-11 | Legal Documents submission pending by Civil vendor due to unavailability of Form 5. | The vendor has not submitted the required legal documents, namely the CAR Policy, Labour License, Principal Employer Certificate, and Labour Law Undertaking, as issuance of the pending statutory documents requires Form-5 to be issued by the Client, which is currently pending for release to the vendor. | High | High | High | Arvind Limited | The contractor requires Form 5, which must be issued by the client so that the contractor can arrange the Labour Licence, Principal Employer Certificate, and Labour Law Compliance Undertaking documents. | Timely follow-up and enforcement will ensure the vendor complies with legal and project requirements, reducing legal and contractual risks. This will protect the project from liability, ensure smooth vendor mobilization, and maintain uninterrupted progress of works. | 2025-11-20 | Pending
4 | General | 2025-11-25 | Absence of Safety Net on Building Periphery | Safety nets have not been installed around the periphery of the building, creating a high‐risk environment for workers and nearby personnel. In the event of a fall, there is no secondary protection to prevent severe injury or fatality. This also increases the risk of falling tools or materials, which could harm people or damage property below. | High | High | High | Bhavna Infra | Immediate installation of certified safety nets around all open edges and building periphery. Conduct a safety audit to identify all areas requiring fall protection. Ensure the nets comply with safety standards (material strength, anchoring, load capacity). Brief workers and supervisors on safe installation and usage procedures. Regular inspection and maintenance of installed nets. | Significant reduction in risk of worker falls and injuries. Enhanced compliance with safety regulations and statutory requirements. Reduced downtime due to accidents. Increased worker confidence and productivity. Prevention of material fall that could lead to damage or liability. | 2025-11-25
6 | General | 2025-11-25 | Absence of Plumbing Points for Curing on Each Floor | Plumbing points for curing have not been installed on every floor, resulting in insufficient and inconsistent curing of concrete works. Without adequate water supply, the concrete may not achieve the required strength, durability, or finish. This can lead to cracks, surface defects, reduced structural integrity, and potential long-term maintenance issues. Workers may also adopt unsafe or inefficient alternatives (manual carrying of water), increasing effort, time, and potential risk of slips or mishandling. | High | High | High | Bhavna Infra | Install temporary or permanent plumbing points on every floor to ensure continuous water supply for curing. Arrange temporary water lines or hoses until the permanent plumbing is completed. Monitor curing schedules to ensure concrete receives the required water quantity and duration. Assign a dedicated team to ensure curing is carried out systematically. Conduct inspections to verify curing effectiveness and correct any deficiencies promptly. | Ensures proper concrete strength, durability, and structural performance. Prevents cracks, defects, and future repair costs. Improves quality of construction and reduces chances of rework. Enhances safety by avoiding unsafe manual handling of water. Helps maintain project timelines by preventing structural quality delays. | 2025-11-25 | Close

## Legal Approval Tracker
Sr. No. | Approvals | Authority for Approval | Action Taken | Action Required | Due date | Approval Date | Risk Associated | Status
1 | 3-Phase Electrical Power Supply at Site | Arvind limited | Construction electric power has to provided by client at site |  | 2025-08-05 |  | Construction activity | Done
2 | Labour License (Form V) | Arvind limited | Required if more than 20 workers are engaged at the site. | Form 5 must be issued by client | 2025-08-05 |  | Legal penalty,project stoppage. | Not done | Done
3 | Form V – Principal Employer Certificate | Arvind limited | Must be signed and stamped by the client (principal employer). | Form 5 must be issued by client | 2025-08-05 |  | Delay in license; unclear liability. | Not done | Not done
4 | Contractor’s All Risk (CAR) Insurance Policy | Bhavna Infra | Must cover civil works, machinery, equipment, and third-party liabilities. |  | 2025-08-05 |  | Financial loss from damages; contract issues. | Not done
5 | Workmen Compensation Insurance Policy | Bhavna Infra | Mandatory to safeguard against workplace accidents and injuries. |  | 2025-08-05 |  | Heavy liability in case of injury; legal action. | Done
6 | PPE Issuance Proof | Bhavna Infra | Record of issued helmets, shoes, jackets, gloves, etc., with signature. |  | 2025-08-05 |  | Injury risk; safety non-compliance. | Done
7 | Labour Law Compliance Undertaking | Arvind limited | Signed declaration by contractor to comply with labour laws and safety standards. | Form 5 must be issued by client | 2025-08-05 |  | Legal gaps; accountability issues. | Not done
8 | ESIC Registration | Bhavna Infra | Declaration submitted. Not applicable if <10 workers. |  | 2025-08-05 |  | Penalty for non-compliance; worker dissatisfaction. | Done
9 | EPF Registration & Challan Copy | Bhavna Infra | Registration completed. Latest challan submitted. |  | 2025-08-05 |  | Audit issues; client may withhold payment. | Done
10 | First Aid Facility Details | Bhavna Infra | First aid kit arranged and available on site. |  | 2025-08-05 |  | Poor emergency response; safety violation. | Done
11 | Worker List with ID Proof | Bhavna Infra | Updated list with ID proofs submitted weekly. |  | 2025-08-05 |  | Security risk; claims complications. | Done

## Procurement tracker (hidden)
Sr.No. | Workpackage | Items descriptions | Responsible stakeholder | Contractor Name | Target date of inquiry float | Date of Vendor appointment | Lead time | Priority Level | Vendor Appointed | Remark
1 | Weight Bridge | Weight bridge | Client | Eagle Scale Manufacturing Works | 2025-01-20 | 2025-02-11 | 22 days | 1 | Yes
2 | Dock Leveller | Dock Leveller | Client |  | 2025-01-20 |  |  | 1 | No
3 | Mechanical Packages | HVAC (Heating, Ventilation & Air Conditioning), Fire Fighting & Suppression System, Plumbing & Drainage and Compressed Air System | Client |  | 2025-05-10 |  |  | 1 | No |  | High | 1
4 | Electrical Packages | Power Distribution System, Lighting & Small Power, Low Current Systems (CCTV, Access Control) & Earthing & Lightning Protection | Client |  | 2025-06-10 |  |  | 1 | No |  | Medium | 2
5 | Process Equipment & Utilities | Heavy Machinery & Equipment | Client |  | 2025-05-12 |  |  | 2 | No |  | Low | 3

## Procurement Status
Project: Arvind limited , Santej
Client: | Arvind Limited |  |  |  |  | Legends |  | No
Consultants: | AK.Consultant | [6 empty] | Pending
PMC: | Sharnam Project Develoment & Consultants & Co. | [6 empty] | Yes
Nomenclature
A | A. Design Consultancy 1. Architectural 2.Structural 3.Plumbing 4.Fire 5.Electrical 6.Interior |  |  |  | DC
B | Civil Packages |  |  |  | CP
C | Façade ( Door & Window ) Packages |  |  |  | FP
D | Electrial Packages |  |  |  | EP
E | Plumbing Packages |  |  |  | PP
F | Fire Protection Packages |  |  |  | FP
G | Interior Packages |  |  |  | IP
H | External Development Package |  |  |  | EDP
I | Gas Line Package |  |  |  | GL
J | External Electric Package |  |  |  | EEP
K | Canteen Furniture Package |  |  |  | CFP
Package No. | Package Name | Location/ Area | Design Status | Inquiry Scope | Target Date of Inquiry Start | Target Date of Inquiry Close | Vednor On Bord | Decision Status | Remarks
DC | A. Design Consultancy 1. Architectural 2.Structural 3.Plumbing 4.Fire 5.Electrical 6.Interior | Worker Dormitory | 90% | Arvind Limited | 2025-04-30 | 2025-05-15 | 2025-05-20 | Yes
CP | Civil Packages | Worker Dormitory | 65% | Arvind Limited | 2025-06-01 | 2025-06-10 | 2025-06-18 | Yes
FP | Façade ( Door & Window ) Packages | Worker Dormitory | 15% | Arvind Limited | 2025-11-15 | 2025-11-22 | 2026-03-11 | Yes
EP | Electrial Packages | Worker Dormitory | 35% | Arvind Limited | 2025-10-10 | 2025-10-20 | 2025-11-10 | Yes
PP | Plumbing Packages | Worker Dormitory | 40% | Arvind Limited | 2025-11-15 | 2025-11-22 | 2026-01-06 | Yes
FP | Fire Protection Packages | Worker Dormitory | 10% | Arvind Limited | 2026-01-27 | 2026-02-03 | 2026-04-09 | Yes
IP | Interior Packages | Worker Dormitory | 30% | Arvind Limited | 2026-01-27 | 2026-02-03 | 2026-03-14 | Yes
EDP | External Development Package | Worker Dormitory | 20% | Arvind Limited | 2025-12-06 | 2025-12-13 | 2026-01-16 | Yes
GL | Gas Line Package | Worker Dormitory | 10% | Arvind Limited | 2026-02-12 | 2026-02-26 | 2026-04-11 | Yes
EEP | External Electric Package | Worker Dormitory | 0% | Arvind Limited | 2026-04-04 | 2026-04-06 | 2026-05-06 | Yes
CFP | Canteen Furniture Package | Worker Dormitory | 0% | Arvind Limited | 2026-05-10 | 2026-05-20 | 2026-05-30 | Yes
Formulas:
CP = [Legends]-10
Legends = [Vednor On Bord]-21

## Weekly Manpower
Type of Manpower | Required Manpower for week | Available | Shortage | [17 empty] | Safety NCR |  |  | Unsafe Act |  |  | Condition
Reinforcement work | 0 | 0 | 0 | [17 empty] | Total | Open | Close | Total | Open | Close | Total | Open | Close
Carpenter | 7 | 7 | 0 | [17 empty] | 2 | 1 | 2 | 10 | 0 | 10 | 10 | 1 | 9
Mason | 28 | 28 | 0
Helper | 7 | 7 | 0
Unskilled Worker | 105 | 105 | 0 | [17 empty] | NCR |  |  | Site Observation |  |  | Site Instructions
Drivers | 7 | 7 | 0 | [17 empty] | Total | Open | Close | Total | Open | Close | Total | Open | Close
Staff | 26 | 26 | 0 | [17 empty] | 1 | 0 | 1 | 38 | 2 | 36 | 41 | 2 | 39
Plumbing | 49 | 28 | 21
Tiles Work | 14 | 14 | 0
Painter | 14 | 14 | 0
Electric Work | 14 | 14 | 0
Fabricator | 0 | 0 | 0
Flush Door - Carpenter | 0 | 0 | 0
PreCast | 25 | 25 | 0
WPC | 0 | 0 | 0
Fire Fighting | 0 | 0 | 0
Gas Line | 0 | 0 | 0
Wardrobe | 0 | 0 | 0
Bed and Platform | 0 | 0 | 0
Windows | 0 | 0 | 0
Total of Above | 296 | 275 | 21
Available
Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff | Plumbing | Tiles | Painter | Ele. | Fabricator | Flush Door | PreCast | WPC | Fire | Gas | Wardrobe | Bed | Windows
2026-06-11 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-12 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-13 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-14 | 0 | 1 | 4 | 1 | 15 | 1 | 2 | 4 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-15 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-16 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-17 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 7 | 28 | 7 | 105 | 7 | 26 | 28 | 14 | 14 | 14 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
Required
Date | Rein. work | Carpenter | Mason | Helper | Unskilled | Drivers | staff | Plumbing | Tiles | Painter | Ele | Fabricator | Flush Door | PreCast | WPC | Fire | Gas | Wardrobe | Bed | Windows
2026-06-11 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 7 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-12 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 7 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-13 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 7 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-14 | 0 | 1 | 4 | 1 | 15 | 1 | 2 | 7 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-15 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 7 | 2 | 2 | 2 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-16 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 7 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-17 | 0 | 1 | 4 | 1 | 15 | 1 | 4 | 7 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 7 | 28 | 7 | 105 | 7 | 26 | 49 | 14 | 14 | 14 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0

## Project Cashflow
Month |  | Budgeted work | Planned Work | Actual Work
August | RA 01 |  | 5000000 | 1063955
September | RA 02 |  | 7200000 | 7797193
October | RA 03 |  | 5000000 | 168333
November | RA 04 |  | 7500000 | 2376171
December | RA 05 |  | 8000000 | 12765763
January | RA 06 |  | 9000000 | 2906803.74
February | RA 07 |  | 12596861.8 | 9418848.1
March | RA 08 |  | 12596861.8 | 2123756.45
April | RA 09 |  | 12596861.8 | 8730949.04
May | RA 10 |  | 12596861.8 | 19313808.5
June | RA 11 |  | 12596861.8 | 8306604.76
July | RA 12 |  | 12596861.8 | 5227082.93
Month |  |  | January
Planned
Actual

## HSE Statistic
Sr.No | HSE indicators | Up to Previous Week (PW) | Current Week (CW) | Cumulative | Sr.No. | Oberservation | Total | Open | Close
1 | Safe-manhours | 253648 | 2200 | 255848 | 1 | Unsafe act | 23 | 0 | 23
2 | Safe-man-days | 364 | 7 | 371 | 2 | Unsafe condition | 17 | 0 | 17
3 | Toolbox Talk | 64 | 0 | 64 | 3 | NCR | 4 | 0 | 4
4 | HSE induction | 17 | 0 | 17
5 | HSE trainings | 4 | 0 | 4
6 | Reported Incident/Accident | 0 | 0 | 0
7 | Site safety Instructions | 241 | 0 | 241
8 | NCN Raised | 4 | 0 | 4
9 | SOR Raised | 0 | 0 | 0
10 | FAC | 0 | 0 | 0
11 | Near Miss | 2 | 0 | 2

## Quality Statistic
Sr.no. | Observation | Total | Open | Close
1 | Site Observation | 89 | 0 | 89
2 | Site Instruction | 89 | 0 | 89
3 | NCR | 4 | 0 | 4

## Cube Test
No of sample | Compressive strength at 7 days | IS code lower limit
1 | 17.97 | 17
2 | 20.23 | 17
3 | 19.5 | 17
4 | 21.32 | 17
5 | 19.85 | 17
6 | 18.45 | 17
IS Code Lower limit - 25Mpa

## Planned Vs Actual
Planned Vs Actual Previous Week to Current Week (Date: 23-07-2026 to 29-07-2026)
Description | [5 empty] | Qty Planed | [6 empty] | Against GFC | Agianst Weekly Planed |  | Cumlative | Cumlative
Sr.No. | Tower | Activity | Planned Start Date by Contractor | Planned End Date by Contractor | Unit | As per BOQ total Quantity | Total GFC Qty | Executed qty till 22-07-2026 | Balance Qty. | Weekly planned Qty. | Weekly actual Qty. | Cumulative Qty. | % Balance Qty ( Remaining ) Against GFC Qty | % Planned Against Balance Qty | % Achieved Against Actual Qty | % Completed (Total against the GFC ) | % Completed (Total against the GFC )
1 | Upto Plinth | Excavation | 2025-12-18 | 2025-12-24 | CUM | 3925 | 1826 | 1826.2 | -0.2 | 0 | 0 | 1826.2 | -0.01095% | 0% | 0% | Delay | 100%
2 |  | Footing PCC | 2025-12-18 | 2025-12-24 | CUM | 265 | 91.31 | 91.31 | 0 | 0 | 0 | 91.31 | 0% | 0% | 0% | On time | 100%
3 |  | Yellow Soil Filling | 2025-12-18 | 2025-12-24 | CUM | 10000 | 1123.22 | 1123.22 | 0 | 0 | 0 | 1123.22 | 0% | 0% | 0% |  | 100%
4 |  | Rubble Soling | 2025-12-18 | 2025-12-24 | CUM | 195.5 | 173.81 | 173.81 | 0 | 0 | 0 | 173.81 | 0% | 0% | 0% |  | 100%
5 |  | Footing Shuttering | 2025-12-18 | 2025-12-24 | SMT | 1075 | 441.908 | 441.91 | -0.002 | 0 | 0 | 441.91 | -0.0004526% | 0% | 0% |  | 100% |  |  |  | 94430.726
6 |  | Footing RCC | 2025-12-18 | 2025-12-24 | CUM | 380 | 292.764 | 292.76 | 0.004 | 0 | 0 | 292.76 | 0.001366% | 0% | 0% | On time | 100%
7 |  | Padestal Upto Plinth Top Shuttering | 2025-12-18 | 2025-12-24 | SMT | 1075 | 664 | 664 | 0 | 0 | 0 | 664 | 0% | 0% | 0% |  | 100%
8 |  | Padestal Upto Plinth Top RCC | 2025-12-18 | 2025-12-24 | CUM | 380 | 62.65 | 62.65 | 0 | 0 | 0 | 62.65 | 0% | 0% | 0% |  | 100%
9 |  | GB Excavation | 2025-12-18 | 2025-12-24 | CUM | 3925 | 11.795 | 11.795 | 0 | 0 | 0 | 11.795 | 0% | 0% | 0% |  | 100%
10 |  | GB PCC | 2025-12-18 | 2025-12-24 | CUM | 265 | 7.944 | 7.944 | 0 | 0 | 0 | 7.944 | 0% | 0% | 0% |  | 100%
11 |  | GB Shuttering | 2025-12-18 | 2025-12-24 | SMT | 1075 | 142.938 | 142.85 | 0.088 | 0 | 0 | 142.85 | 0.06157% | 0% | 0% |  | 99.94%
12 |  | GB RCC | 2025-12-18 | 2025-12-24 | CUM | 380 | 23.994 | 23.98 | 0.014 | 0 | 0 | 23.98 | 0.05835% | 0% | 0% |  | 99.94%
13 |  | Masonry Above GB | 2025-12-18 | 2025-12-24 | CUM | 130 | 86.294 | 86.294 | 0 | 0 | 0 | 86.294 | 0% | 0% | 0% |  | 100%
14 |  | Plinth Beam PCC | 2025-12-18 | 2025-12-24 | CUM | 265 | 18.07 | 18.07 | 0 | 0 | 0 | 18.07 | 0% | 0% | 0% |  | 100%
15 |  | Plinth Beam Shuttering | 2025-12-18 | 2025-12-24 | SMT | 1075 | 387.1 | 387.1 | 0 | 0 | 0 | 387.1 | 0% | 0% | 0% |  | 100%
16 |  | Plinth Beam RCC | 2025-12-18 | 2025-12-24 | CUM | 380 | 45.72 | 45.72 | 0 | 0 | 0 | 45.72 | 0% | 0% | 0% |  | 100%
17 |  | Plinth Plaster | 2025-12-18 | 2025-12-24 | SMT | 5235 | 92.29 | 92.29 | 0 | 0 | 0 | 92.29 | 0% | 0% | 0% |  | 100%
18 |  | Masonry above PB | 2025-12-18 | 2025-12-24 | CUM | 130 | 16.168 | 16.17 | -0.002 | 0 | 0 | 16.17 | -0.01237% | 0% | 0% |  | 100%
19 |  | Floor PCC | 2025-12-18 | 2025-12-24 | CUM | 265 | 86.9 | 86.9 | 0 | 0 | 0 | 86.9 | 0% | 0% | 0% |  | 100%
20 |  | Floor RCC Shuttering | 2025-12-18 | 2025-12-24 | SMT | 1075 | 15.3 | 15.3 | 0 | 0 | 0 | 15.3 | 0% | 0% | 0% |  | 100%
21 |  | Floor RCC | 2025-12-18 | 2025-12-24 | CUM | 380 | 88.03 | 88.03 | 0 | 0 | 0 | 88.03 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 100%
22 | Ground Floor | Plinth to GF slab column shuttering | 2026-05-28 | 2026-06-03 | SQM | 1680 | 427.554 | 427.554 | 0 | 0 | 0 | 427.554 | 0% | 0% | 0% |  | 100%
23 |  | GF beam shuttering | 2026-05-28 | 2026-06-03 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
24 |  | GF Slab shuttering | 2026-05-28 | 2026-06-03 | SQM |  | 664.23 | 664.23 | 0 | 0 | 0 | 664.23 | 0% | 0% | 0% |  | 100%
25 |  | GF staircase shuttering | 2026-05-28 | 2026-06-03 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
26 |  | GF lintel shuttering | 2026-05-28 | 2026-06-03 | SQM |  | 70.36 | 70.36 | 0 | 0 | 0 | 70.36 | 0% | 0% | 0% |  | 100%
27 |  | Plinth to GF slab column concrete | 2026-05-28 | 2026-06-03 | CUM | 210 | 32.82 | 32.82 | 0 | 0 | 0 | 32.82 | 0% | 0% | 0% |  | 100%
28 |  | GF beam Concrete | 2026-05-28 | 2026-06-03 | CUM |  | 61.75 | 61.75 | 0 | 0 | 0 | 61.75 | 0% | 0% | 0% |  | 100%
29 |  | GF Slab Concrete | 2026-05-28 | 2026-06-03 | CUM |  | 101.98 | 101.98 | 0 | 0 | 0 | 101.98 | 0% | 0% | 0% |  | 100%
30 |  | GF staircase concrete | 2026-05-28 | 2026-06-03 | CUM |  | 8.52 | 8.52 | 0 | 0 | 0 | 8.52 | 0% | 0% | 0% |  | 100% |  | 132.72
31 |  | GF lintel Concrete | 2026-05-28 | 2026-06-03 | CUM |  | 6.92 | 6.92 | 0 | 0 | 0 | 6.92 | 0% | 0% | 0% |  | 100% |  | 21.36
32 |  | Brick masonary GF (230 mm) | 2026-05-28 | 2026-06-03 | CUM | 80 | 75.25 | 75.25 | 0 | 0 | 0 | 75.25 | 0% | 0% | 0% |  | 100% |  | 26.64
33 |  | Brick masonary GF (115 mm) | 2026-05-28 | 2026-06-03 | SMT | 1170 | 404.61 | 404.61 | 0 | 0 | 0 | 404.61 | 0% | 0% | 0% |  | 100%
34 |  | Internal Plaster | 2026-05-28 | 2026-06-03 | SMT | 1591.21 | 1812.85 | 1812.85 | 0 | 0 | 0 | 1812.85 | 0% | 0% | 0% |  | 100%
35 |  | Flooring | 2026-05-28 | 2026-06-03 | SMT | 830 | 895.5 | 895.5 | 0 | 0 | 0 | 895.5 | 0% | 0% | 0% |  | 100% |  | 10
36 |  | Skirting | 2026-05-28 | 2026-06-03 | RMT | 1865 | 716 | 716 | 0 | 0 | 0 | 716 | 0% | 0% | 0% |  | 100% |  | 2254
37 |  | Toilet Dado | 2026-05-28 | 2026-06-03 | SMT | 416 | 132.72 | 132.72 | 0 | 0 | 0 | 132.72 | 0% | 0% | 0% |  | 100% |  | 3167.72
38 |  | Toilet Floor | 2026-05-28 | 2026-06-03 | SMT | 400 | 21.36 | 21.36 | 0 | 0 | 0 | 21.36 | 0% | 0% | 0% |  | 100% |  | 756
39 |  | Kitchen dado | 2026-05-28 | 2026-06-03 | SMT | 416 | 26.64 | 26.64 | 0 | 0 | 0 | 26.64 | 0% | 0% | 0% |  | 100%
40 |  | Flush Door /Fire Dorr | 2026-06-04 | 2026-06-10 | SMT | 201.6 | 22.05 | 22.05 | 0 | 0 | 0 | 22.05 | 0% | 0% | 0% |  | 100%
41 |  | Groove Filling | 2026-07-23 | 2026-07-29 | RMT | 2254 | 2254 | 2254 | 0 | 0 | 0 | 2254 | 0% | 0% | 0% |  | 100%
42 |  | Interior Paint | 2026-07-23 | 2026-07-29 | SMT | 17190 | 3167.72 | 3167.72 | 0 | 0 | 0 | 3167.72 | 0% | 0% | 0% |  | 100%
43 |  | Exterior Paint | 2026-07-23 | 2026-07-29 | SMT | 5235 | 756 | 756 | 0 | 0 | 0 | 756 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 100%
44 | First Floor | GF to FF slab column shuttering | 2026-05-21 | 2026-05-27 | SQM | 1680 | 427.554 | 427.55 | 0.004 | 0.004 | 0 | 427.55 | 0.0009356% | 100% | 0% |  | 100%
45 |  | FF beam shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 700.59 | 701 | -0.41 | 0 | 0 | 701 | -0.05852% | 0% | 0% |  | 100.1%
46 |  | FF Slab shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 664.23 | 664.26 | -0.03 | 0 | 0 | 664.26 | -0.004517% | 0% | 0% |  | 100%
47 |  | FF Staircase Shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
48 |  | FF lintel shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 111.23 | 111.225 | 0.005 | 0 | 0 | 111.225 | 0.004495% | 0% | 0% |  | 100%
49 |  | GF to FF slab column concrete | 2026-05-21 | 2026-05-27 | CUM | 210 | 32.822 | 32.82 | 0.002 | 0 | 0 | 32.82 | 0.006093% | 0% | 0% |  | 99.99%
50 |  | FF Staircase Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
51 |  | FF beam Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
52 |  | FF Slab Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
53 |  | FF lintel Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 0% | 0% | 0% |  | 100%
54 |  | Brick masonary FF (230 mm) | 2026-05-21 | 2026-05-27 | CUM | 80 | 77.3 | 77.3 | 0 | 0 | 0 | 77.3 | 0% | 0% | 0% |  | 100%
55 |  | Brick masonary FF (115 mm) | 2026-05-21 | 2026-05-27 | SMT | 1170 | 691.13 | 691.13 | 0 | 0 | 0 | 691.13 | 0% | 0% | 0% |  | 100%
56 |  | Internal Plaster | 2026-05-21 | 2026-05-27 | SMT | 1591.21 | 2167.33 | 2167.33 | 0 | 0 | 0 | 2167.33 | 0% | 0% | 0% |  | 100%
57 |  | Flooring | 2026-05-21 | 2026-05-27 | SMT | 830 | 670.5 | 670.5 | 0 | 0 | 0 | 670.5 | 0% | 0% | 0% |  | 100%
58 |  | Skirting | 2026-05-21 | 2026-05-27 | RMT | 1865 | 716 | 716 | 0 | 0 | 0 | 716 | 0% | 0% | 0% |  | 100%
59 |  | Toilet Dado | 2026-05-21 | 2026-05-27 | SMT | 416 | 265.44 | 265.44 | 0 | 0 | 0 | 265.44 | 0% | 0% | 0% |  | 100% |  | 3167.72
60 |  | Toilet Floor | 2026-05-21 | 2026-05-27 | SMT | 400 | 42.72 | 42.72 | 0 | 0 | 0 | 42.72 | 0% | 0% | 0% |  | 100% |  | 756
61 |  | Kitchen dado | 2026-05-21 | 2026-05-27 | SMT | 416 | 53.28 | 53.28 | 0 | 0 | 0 | 53.28 | 0% | 0% | 0% |  | 100%
62 |  | Flush Door | 2026-07-23 | 2026-07-29 | SMT | 201.6 | 18 | 18 | 0 | 0 | 0 | 18 | 0% | 0% | 0% |  | 100%
63 |  | Groove Filling | 2026-07-23 | 2026-07-29 | RMT | 0 | 2254 | 2254 | 0 | 0 | 0 | 2254 | 0% | 0% | 0% |  | 100%
64 |  | Interior Paint | 2026-07-23 | 2026-07-29 | SMT | 17190 | 3167.72 | 3167.72 | 0 | 0 | 0 | 3167.72 | 0% | 0% | 0% |  | 100%
65 |  | Exterior Paint | 2026-07-23 | 2026-07-29 | SMT | 5235 | 756 | 756 | 0 | 0 | 0 | 756 | 0% | 0% | 0% |  | 100%
66 |  | Windows Sill | 2026-05-21 | 2026-05-27 | SMT | 0 | 28.26 | 28.26 | 0 | 0 | 0 | 28.26 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 100%
67 | Second Floor | FF to SF slab column shuttering | 2026-05-21 | 2026-05-27 | SQM | 1680 | 427.554 | 427.554 | 0 | 0 | 0 | 427.554 | 0% | 0% | 0% |  | 100% | -116.554
68 |  | SF Staircase Shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
69 |  | SF beam shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
70 |  | SF Slab shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 664.23 | 664.26 | -0.03 | 0 | 0 | 664.26 | -0.004517% | 0% | 0% |  | 100%
71 |  | SF lintel shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 111.23 | 111.23 | 0 | 0 | 0 | 111.23 | 0% | 0% | 0% |  | 100%
72 |  | FF to SF slab column concrete | 2026-05-21 | 2026-05-27 | CUM | 210 | 32.822 | 32.822 | 0 | 0 | 0 | 32.822 | 0% | 0% | 0% |  | 100%
73 |  | SF Staircase Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
74 |  | SF beam Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
75 |  | SF Slab Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
76 |  | SF lintel Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 0% | 0% | 0% |  | 100%
77 |  | Brick masonary SF (230 mm) | 2026-05-21 | 2026-05-27 | CUM | 80 | 77.3 | 77.3 | 0 | 0 | 0 | 77.3 | 0% | 0% | 0% |  | 100%
78 |  | Brick masonary SF (115 mm) | 2026-05-21 | 2026-05-27 | SMT | 1170 | 691.13 | 691.13 | 0 | 0 | 0 | 691.13 | 0% | 0% | 0% |  | 100%
79 |  | Internal Plaster | 2026-05-21 | 2026-05-27 | SMT | 1591.21 | 2167.33 | 2167.33 | 0 | 0 | 0 | 2167.33 | 0% | 0% | 0% |  | 100%
80 |  | Flooring | 2026-05-21 | 2026-05-27 | SMT | 830 | 670.5 | 670.5 | 0 | 0 | 0 | 670.5 | 0% | 0% | 0% |  | 100%
81 |  | Skirting | 2026-05-21 | 2026-05-27 | RMT | 1865 | 716 | 716 | 0 | 0 | 0 | 716 | 0% | 0% | 0% |  | 100%
82 |  | Toilet Dado | 2026-06-04 | 2026-06-10 | SMT | 416 | 265.44 | 265.44 | 0 | 0 | 0 | 265.44 | 0% | 0% | 0% |  | 100% |  | 3167.72
83 |  | Toilet Floor | 2026-06-04 | 2026-06-10 | SMT | 400 | 42.72 | 42.72 | 0 | 0 | 0 | 42.72 | 0% | 0% | 0% |  | 100% |  | 756
84 |  | Kitchen dado | 2026-06-04 | 2026-06-10 | SMT | 416 | 53.28 | 53.28 | 0 | 0 | 0 | 53.28 | 0% | 0% | 0% |  | 100%
85 |  | Flush Door | 2026-07-23 | 2026-07-29 | SMT | 201.6 | 18 | 18 | 0 | 0 | 0 | 18 | 0% | 0% | 0% |  | 100%
86 |  | Groove Filling | 2026-07-23 | 2026-07-29 | RMT | 0 | 2254 | 2254 | 0 | 0 | 0 | 2254 | 0% | 0% | 0% |  | 100%
87 |  | Interior Paint | 2026-07-23 | 2026-07-29 | SMT | 17190 | 3167.72 | 3168 | 0 | 0 | 0 | 3168 | 0% | 0% | 0% |  | 100%
88 |  | Exterior Paint | 2026-07-23 | 2026-07-29 | SMT | 5235 | 756 | 756 | 0 | 0 | 0 | 756 | 0% | 0% | 0% |  | 100%
89 |  | Windows Sill | 2026-06-04 | 2026-06-10 | SMT | 0 | 28.26 | 28.26 | 0 | 0 | 0 | 28.26 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 100%
90 | Third Floor | SF to TF slab column shuttering | 2026-05-21 | 2026-05-27 | SQM | 1680 | 427.554 | 427.55 | 0.004 | 0 | 0 | 427.55 | 0.0009356% | 0% | 0% |  | 100% | 0.004
91 |  | TF Staircase Shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
92 |  | TF beam shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
93 |  | TF Slab shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 664.23 | 664.26 | -0.03 | 0 | 0 | 664.26 | -0.004517% | 0% | 0% |  | 100%
94 |  | TF lintel shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 111.23 | 111.23 | 0 | 0 | 0 | 111.23 | 0% | 0% | 0% |  | 100%
95 |  | SF to TF slab column concrete | 2026-05-21 | 2026-05-27 | CUM | 210 | 32.822 | 32.822 | 0 | 0 | 0 | 32.822 | 0% | 0% | 0% |  | 100% | 0
96 |  | TF Staircase Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
97 |  | TF beam Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
98 |  | TF Slab Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
99 |  | TF lintel Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 0% | 0% | 0% |  | 100%
100 |  | Brick masonary SF (230 mm) | 2026-06-04 | 2026-06-10 | CUM | 80 | 77.3 | 77.3 | 0 | 0 | 0 | 77.3 | 0% | 0% | 0% |  | 100%
101 |  | Brick masonary SF (115 mm) | 2026-06-04 | 2026-06-10 | SMT | 1170 | 691.13 | 691.13 | 0 | 0 | 0 | 691.13 | 0% | 0% | 0% |  | 100%
102 |  | Internal Plaster | 2026-06-04 | 2026-06-10 | SMT | 1591.21 | 2167.33 | 2167.33 | 0 | 0 | 0 | 2167.33 | 0% | 0% | 0% |  | 100%
103 |  | Flooring | 2026-06-18 | 2026-06-24 | SMT | 830 | 670.5 | 670.5 | 0 | 0 | 0 | 670.5 | 0% | 0% | 0% |  | 100%
104 |  | Skirting | 2026-06-18 | 2026-06-24 | RMT | 1865 | 716 | 716 | 0 | 0 | 0 | 716 | 0% | 0% | 0% |  | 100%
105 |  | Toilet Dado | 2026-06-18 | 2026-06-24 | SMT | 416 | 265.44 | 265.44 | 0 | 0 | 0 | 265.44 | 0% | 0% | 0% |  | 100% |  | 3167.72
106 |  | Toilet Floor | 2026-06-18 | 2026-06-24 | SMT | 400 | 42.72 | 42.72 | 0 | 0 | 0 | 42.72 | 0% | 0% | 0% |  | 100% |  | 756
107 |  | Kitchen dado | 2026-06-18 | 2026-06-24 | SMT | 416 | 53.28 | 53.28 | 0 | 0 | 0 | 53.28 | 0% | 0% | 0% |  | 100%
108 |  | Flush Door | 2026-06-18 | 2026-06-24 | SMT | 201.6 | 18 | 0 | 18 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
109 |  | Groove Filling | 2026-07-23 | 2026-07-29 | RMT | 0 | 2254 | 2254 | 0 | 0 | 0 | 2254 | 0% | 0% | 0% |  | 100%
110 |  | Interior Paint | 2026-07-23 | 2026-07-29 | SMT | 17190 | 3167.72 | 3167.72 | 0 | 0 | 0 | 3167.72 | 0% | 0% | 0% |  | 100%
111 |  | Exterior Paint | 2026-07-23 | 2026-07-29 | SMT | 5235 | 756 | 756 | 0 | 0 | 0 | 756 | 0% | 0% | 0% |  | 100%
112 |  | Windows Sill | 2026-06-04 | 2026-06-10 | SMT | 0 | 28.26 | 28.26 | 0 | 0 | 0 | 28.26 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 95.65%
113 | Fourth Floor | TF to FF slab column shuttering | 2026-05-21 | 2026-05-27 | SQM | 1680 | 427.554 | 427.554 | 0 | 0 | 0 | 427.554 | 0% | 0% | 0% |  | 100% | -0.004
114 |  | FF Staircase Shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 57.39 | 57.39 | 0 | 0 | 0 | 57.39 | 0% | 0% | 0% |  | 100%
115 |  | FF beam shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 700.59 | 700.59 | 0 | 0 | 0 | 700.59 | 0% | 0% | 0% |  | 100%
116 |  | FF Slab shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 664.23 | 664.23 | 0 | 0 | 0 | 664.23 | 0% | 0% | 0% |  | 100%
117 |  | FF lintel shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 111.23 | 111.23 | 0 | 0 | 0 | 111.23 | 0% | 0% | 0% |  | 100%
118 |  | TF to FF slab column concrete | 2026-05-21 | 2026-05-27 | CUM | 210 | 32.822 | 32.822 | 0 | 0 | 0 | 32.822 | 0% | 0% | 0% |  | 100% | 0
119 |  | FF Staircase Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 8.53 | 8.53 | 0 | 0 | 0 | 8.53 | 0% | 0% | 0% |  | 100%
120 |  | FF beam Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 61.76 | 61.76 | 0 | 0 | 0 | 61.76 | 0% | 0% | 0% |  | 100%
121 |  | FF Slab Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 101.99 | 101.99 | 0 | 0 | 0 | 101.99 | 0% | 0% | 0% |  | 100%
122 |  | FF lintel Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 0% | 0% | 0% |  | 100%
123 |  | Brick masonary FF (230 mm) | 2026-05-21 | 2026-05-27 | CUM | 80 | 77.3 | 77.3 | 0 | 0 | 0 | 77.3 | 0% | 0% | 0% |  | 100%
124 |  | Brick masonary FF (115 mm) | 2026-05-21 | 2026-05-27 | SMT | 1170 | 691.13 | 603 | 88.13 | 88.13 | 88.13 | 691.13 | 12.75% | 100% | 100% |  | 100%
125 |  | Internal Plaster | 2026-06-18 | 2026-06-24 | SMT | 1591.21 | 2167.33 | 2167.33 | 0 | 0 | 0 | 2167.33 | 0% | 0% | 0% |  | 100%
126 |  | Flooring | 2026-06-18 | 2026-06-24 | SMT | 830 | 670.5 | 670.5 | 0 | 0 | 0 | 670.5 | 0% | 0% | 0% |  | 100%
127 |  | Skirting | 2026-06-18 | 2026-06-24 | RMT | 1865 | 716 | 716 | 0 | 0 | 0 | 716 | 0% | 0% | 0% |  | 100%
128 |  | Toilet Dado | 2026-06-18 | 2026-06-24 | SMT | 416 | 265.44 | 265.44 | 0 | 0 | 0 | 265.44 | 0% | 0% | 0% |  | 100% |  | 3167.72
129 |  | Toilet Floor | 2026-06-18 | 2026-06-24 | SMT | 400 | 42.72 | 42.72 | 0 | 0 | 0 | 42.72 | 0% | 0% | 0% |  | 100% |  | 756
130 |  | Kitchen dado | 2026-06-18 | 2026-06-24 | SMT | 416 | 53.28 | 53.28 | 0 | 0 | 0 | 53.28 | 0% | 0% | 0% |  | 100%
131 |  | Flush Door | 2026-07-23 | 2026-07-29 | SMT | 201.6 | 18 | 18 | 0 | 0 | 0 | 18 | 0% | 0% | 0% |  | 100%
132 |  | Groove Filling | 2026-07-23 | 2026-07-29 | RMT | 0 | 2254 | 2254 | 0 | 0 | 0 | 2254 | 0% | 0% | 0% |  | 100%
133 |  | Interior Paint | 2026-07-23 | 2026-07-29 | SMT | 17190 | 3167.72 | 3168 | -0.28 | -0.28 | 0 | 3168 | -0.008839% | 0% | 0% |  | 100%
134 |  | Exterior Paint | 2026-07-23 | 2026-07-29 | SMT | 5235 | 756 | 756 | 0 | 0 | 0 | 756 | 0% | 0% | 0% |  | 100%
135 |  | Windows Sill | 2026-06-04 | 2026-06-10 | SMT | 0 | 28.26 | 19.8 | 8.46 | 8.46 | 8.46 | 28.26 | 29.94% | 100% | 100% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 100%
136 | Terrace Floor | Terrace Floor column shuttering | 2026-05-21 | 2026-05-27 | SQM | 1680 | 98.52 | 98.52 | 0 | 0 | 0 | 98.52 | 0% | 0% | 0% |  | 100% | 329.034
137 |  | Terrace Floor beam shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 65 | 65 | 0 | 0 | 0 | 65 | 0% | 0% | 0% |  | 100%
138 |  | Terrace floor Slab shuttering | 2026-05-21 | 2026-05-27 | SQM |  | 60 | 60 | 0 | 0 | 0 | 60 | 0% | 0% | 0% |  | 100%
139 |  | Terrace Floor column concrete | 2026-05-21 | 2026-05-27 | CUM | 210 | 6.26 | 6.26 | 0 | 0 | 0 | 6.26 | 0% | 0% | 0% |  | 100% | 26.562
140 |  | Stair Cabin beam Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 5.42 | 5.42 | 0 | 0 | 0 | 5.42 | 0% | 0% | 0% |  | 100%
141 |  | Stair Cabin Slab Concrete | 2026-05-21 | 2026-05-27 | CUM |  | 8.98 | 8.98 | 0 | 0 | 0 | 8.98 | 0% | 0% | 0% |  | 100%
142 |  | Brick masonary FF (230 mm) | 2026-05-21 | 2026-05-27 | CUM | 80 | 68.073 | 68.07 | 0.003 | 0.003 | 0 | 68.07 | 0.004407% | 100% | 0% |  | 100%
143 |  | Brick masonary FF (115 mm) | 2026-07-23 | 2026-07-29 | SMT | 1170 | 19.16 | 19.16 | 0 | 0 | 0 | 19.16 | 0% | 0% | 0% |  | 100%
144 |  | Internal Plaster | 2026-07-23 | 2026-07-29 | SMT | 1591.21 | 262.66 | 262.66 | 0 | 0 | 0 | 262.66 | 0% | 0% | 0% |  | 100%
145 |  | Waterproofing of Slab | 2026-07-23 | 2026-07-29 | SMT | 850 | 841.1628 | 841.1628 | 0 | 0 | 0 | 841.1628 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 100%
146 | UGWT | Excavation | 2026-05-21 | 2026-05-27 | CUM | 3925 | 273.29 | 273.29 | 0 | 0 | 0 | 273.29 | 0% | 0% | 0% |  | 100% | 417.84
147 |  | PCC | 2026-05-21 | 2026-05-27 | CUM | 110 | 13.66 | 13.66 | 0 | 0 | 0 | 13.66 | 0% | 0% | 0% |  | 100%
148 |  | Raft RCC | 2026-05-21 | 2026-05-27 | CUM | 380 | 17.07 | 17.07 | 0 | 0 | 0 | 17.07 | 0% | 0% | 0% |  | 100%
149 |  | Rcc wall | 2026-05-21 | 2026-05-27 | CUM |  | 37.812 | 37.812 | 0 | 0 | 0 | 37.812 | 0% | 0% | 0% |  | 100% | 60.708
150 |  | RCC slab Concrete | 2026-07-23 | 2026-07-29 | CUM |  | 12.33 | 12.33 | 0 | 0 | 0 | 12.33 | 0% | 0% | 0% |  | 100%
151 |  | Raft shuttering | 2026-07-23 | 2026-07-29 | SMT | 1680 | 7.54 | 0 | 7.54 | 0 | 0 | 0 | 100% | 0% | 0% |  | 0%
152 |  | Rcc wall shuttering | 2026-07-23 | 2026-07-29 | SMT |  | 607.672 | 607.672 | 0 | 0 | 0 | 607.672 | 0% | 0% | 0% |  | 100%
153 |  | RCC slab shuttering | 2026-07-23 | 2026-07-29 | SMT |  | 82.202 | 82.202 | 0 | 0 | 0 | 82.202 | 0% | 0% | 0% |  | 100%
154 |  | Waterproofing plaster | 2026-07-23 | 2026-07-29 | SMT | 675 | 398.29 | 398.29 | 0 | 0 | 0 | 398.29 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 88.89%
155 | Compound Wall | Excavation | 2026-07-23 | 2026-07-29 | CUM | 1585 | 387.55 | 387.55 | 0 | 0 | 0 | 387.55 | 0% | 0% | 0% |  | 100% | -368.39
156 |  | PCC (Footing+Beam) | 2026-07-23 | 2026-07-29 | CUM | 65 | 47.3 | 47.3 | 0 | 0 | 0 | 47.3 | 0% | 0% | 0% |  | 100%
157 |  | Footing RCC | 2026-07-23 | 2026-07-29 | CUM | 165 | 29.97 | 29.97 | 0 | 0 | 0 | 29.97 | 0% | 0% | 0% |  | 100%
158 |  | Padestal RCC | 2026-07-23 | 2026-07-29 | CUM |  | 51.575 | 51.575 | 0 | 0 | 0 | 51.575 | 0% | 0% | 0% |  | 100% | -37.915
159 |  | Beam RCC | 2026-07-23 | 2026-07-29 | CUM |  | 47.504 | 47.504 | 0 | 0 | 0 | 47.504 | 0% | 0% | 0% |  | 100%
160 |  | Footing shuttering | 2026-07-23 | 2026-07-29 | SMT | 965 | 95 | 95 | 0 | 0 | 0 | 95 | 0% | 0% | 0% |  | 100%
161 |  | Padestal shuttering | 2026-07-23 | 2026-07-29 | SMT |  | 616.644 | 616.644 | 0 | 0 | 0 | 616.644 | 0% | 0% | 0% |  | 100%
162 |  | Beam shuttering | 2026-07-23 | 2026-07-29 | SMT |  | 271.453 | 271.453 | 0 | 0 | 0 | 271.453 | 0% | 0% | 0% |  | 100%
163 |  | Masonry | 2026-07-23 | 2026-07-29 | CUM | 229 | 203.59 | 203.59 | 0 | 0 | 0 | 203.59 | 0% | 0% | 0% |  | 100%
164 |  | Plaster | 2026-07-23 | 2026-07-29 | SMT | 940 | 891.92 | 891.92 | 0 | 0 | 0 | 891.92 | 0% | 0% | 0% |  | 100%
165 |  | Precast Panels | 2026-07-23 | 2026-07-29 | SMT | 322 | 322 | 322 | 0 | 0 | 0 | 322 | 0% | 0% | 0% |  | 100%
Avreage Achivement : - | [13 empty] | 0% | 0% | #DIV/0! | 100%
166 | Road | Plot Filling | 2026-07-23 | 2026-07-29 | CUM | 1500 | 4265.47 | 4265.47 | 0 | 0 | 0 | 4265.47 | 0% | 0% | 0% |  | 100% | -3867.18
167 |  | PCC | 2026-07-23 | 2026-07-29 | CUM | 168 | 68.7 | 68.7 | 0 | 0 | 0 | 68.7 | 0% | 0% | 0% |  | 100%
168 |  | RCC | 2026-07-23 | 2026-07-29 | CUM | 138 | 95 | 95 | 0 | 0 | 0 | 95 | 0% | 0% | 0% |  | 100%
169 |  | Kerbing | 2026-07-23 | 2026-07-29 | CUM | 516 | 494.48 | 443 | 51.48 | 20 | 10 | 453 | 10.41% | 38.85% | 19.43% |  | 91.61% | -401.425
170 |  | Paver | 2026-07-23 | 2026-07-29 | CUM | 300 | 603.6 | 430 | 173.6 | 100 | 10 | 440 | 28.76% | 57.6% | 5.76% |  | 72.9% |  |  | 300
Avreage Achivement : - | [13 empty] | 19.29% | 5.037% | #DIV/0! | 92.9%
Cumulative Avreage Achivement : - | [13 empty] | 19.29% | 5.037% | #DIV/0! | 98.28%
2

## Value Addition (hidden)
Sr.No. | Block | Package | Planning | Suggestions | Value Engineering Points | Cost | Time | Quality | Approval | Earlier quotated | Final Price
1 | Infra | Utility |  | Vendor Name | Provide vendor details for Hume pipe procurement and negotiate total cost hjkhf | 33600 |  |  | Client | 51100 | 17500 | 33600
2 | Infra | Vastu Compound Wall |  | Rate Assesment | Provide well-defined rate analysis for rate as per VMS vol 1 & 2 | 587500 |  |  | Client | 925000 | 337500 | 587500
3 | MFB | RMC Mix Design |  | Observation on Quality Standards | The cement content has to meet the standard specifications & also consider only 20% of fly ash in their mix design | 819600 |  |  | PMC | Cement Bag (1 cum) | 8 | 6
[10 empty] | Total cum of M25 | 1366 | 1366
[11 empty] | 10928 | 8196
[10 empty] | Cement Bag rate | 300 | 300
[11 empty] | 3278400 | 2458800
819600

## As per drawing status (hidden)
Weekly Executed Plan
Sr.No. | Tower | Activity | Unit | As per BOQ total Quantity | As per GFC total Quantity | Weekly planned Qty. | Weekly actual Qty. | Total Achieved Qty.
1 | Worker Dormitory | Footing Excavation | CUM | 3925 | 1826 | 0 | 0 | 1826.2
2 | Worker Dormitory | GB Excavation | CUM |  | 11.795 | 0 | 0 | 11.795
3 | Worker Dormitory | Yellow Soil Filling | CUM | 10000 | 1123.22 | 0 | 0 | 1123.22
4 | Worker Dormitory | Rubble Soling | CUM | 195.5 | 173.81 | 0 | 0 | 173.81
5 | Worker Dormitory | Footing PCC | CUM | 265 | 91.31 | 0 | 0 | 91.31
6 | Worker Dormitory | GB PCC | CUM |  | 7.944 | 0 | 0 | 7.944
7 | Worker Dormitory | Floor PCC | CUM |  | 86.9 | 0 | 0 | 86.9
8 | Worker Dormitory | Plinth Beam PCC | CUM |  | 18.07 | 0 | 0 | 18.07
9 | Worker Dormitory | Footing RCC | CUM | 380 | 292.764 | 0 | 0 | 292.76
10 | Worker Dormitory | Pedestal RCC | CUM |  | 62.65 | 0 | 0 | 62.65
11 | Worker Dormitory | GB RCC | CUM |  | 23.994 | 0 | 0 | 23.98
12 | Worker Dormitory | Plinth Beam RCC | CUM |  | 45.72 | 0 | 0 | 45.72
13 | Worker Dormitory | Floor RCC | CUM |  | 88.03 | 0 | 0 | 88.03
14 | Worker Dormitory | Masonry Above GB | CUM | 130 | 86.294 | 0 | 0 | 86.294
15 | Worker Dormitory | Masonry above PB | CUM |  | 16.168 | -0.002 | 0 | 16.17
16 | Worker Dormitory | Plinth Plaster | SMT | 5235 | 92.29 | 0 | 0 | 92.29
17 | Worker Dormitory | Footing Shuttering | SMT | 1075 | 441.908 | 0 | 0 | 0
18 | Worker Dormitory | Padestal Upto Plinth Top Shuttering | SMT |  | 664 | 0 | 0 | 664
19 | Worker Dormitory | GB Shuttering | SMT |  | 142.938 | 0 | 0 | 142.85
20 | Worker Dormitory | Plinth Beam Shuttering | SMT |  | 387.1 | 0 | 0 | 387.1
21 | Worker Dormitory | Floor RCC Shuttering | SMT |  | 15.3 | 0 | 0 | 15.3
22 | Worker Dormitory | Plinth to GF slab column shuttering | SQM | 1680 | 427.554 | 0 | 0 | 427.554
23 | Worker Dormitory | GF beam shuttering | SQM |  | 700.59 | 0 | 0 | 700.59
24 | Worker Dormitory | GF Slab shuttering | SQM |  | 664.23 | 0 | 0 | 664.23
25 | Worker Dormitory | GF staircase shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
26 | Worker Dormitory | GF lintel shuttering | SQM |  | 70.36 | 0 | 0 | 70.36
27 | Worker Dormitory | Plinth to GF slab column concrete | CUM | 210 | 32.82 | 0 | 0 | 32.82
28 | Worker Dormitory | GF beam Concrete | CUM |  | 61.75 | 0 | 0 | 61.75
29 | Worker Dormitory | GF Slab Concrete | CUM |  | 101.98 | 0 | 0 | 101.98
30 | Worker Dormitory | GF staircase concrete | CUM |  | 8.52 | 0 | 0 | 8.52
31 | Worker Dormitory | GF lintel Concrete | CUM |  | 6.92 | 0 | 0 | 6.92
32 | Worker Dormitory | Brick masonary GF (230 mm) | CUM | 80 | 75.25 | 0 | 0 | 75.25
33 | Worker Dormitory | Brick masonary GF (115 mm) | SMT | 1170 | 404.61 | 0 | 0 | 404.61
34 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 1812.85 | 0 | 0 | 1812.85
35 | Worker Dormitory | Flooring | SMT | 830 | 895.5 | 0 | 0 | 895.5
36 | Worker Dormitory | Toilet Dado | SMT | 416 | 132.72 | 0 | 0 | 132.72
37 | Worker Dormitory | GF to FF slab column shuttering | SQM | 1680 | 427.554 | 0.004 | 0 | 427.55
38 | Worker Dormitory | FF beam shuttering | SQM |  | 700.59 | 0 | 0 | 701
39 | Worker Dormitory | FF Slab shuttering | SQM |  | 664.23 | 0 | 0 | 664.26
40 | Worker Dormitory | FF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
41 | Worker Dormitory | FF lintel shuttering | SQM |  | 111.23 | 0 | 0 | 111.225
42 | Worker Dormitory | GF to FF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 32.82
43 | Worker Dormitory | FF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
44 | Worker Dormitory | FF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
45 | Worker Dormitory | FF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
46 | Worker Dormitory | FF lintel Concrete | CUM |  | 7.5 | 7.5 | 0 | 0
47 | Worker Dormitory | Brick masonary FF (230 mm) | CUM | 80 | 77.3 | 77.3 | 0 | 0
48 | Worker Dormitory | Brick masonary FF (115 mm) | SMT | 1170 | 691.13 | 691.13 | 0 | 0
49 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 2167.33 | 2167.33 | 0 | 0
50 | Worker Dormitory | Flooring | SMT | 830 | 670.5 | 670.5 | 0 | 0
51 | Worker Dormitory | Skirting | RMT | 1865 | 716 | 716 | 0 | 0
52 | Worker Dormitory | FF to SF slab column shuttering | SQM | 1680 | 427.554 | 0 | 0 | 101.99
53 | Worker Dormitory | SF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 427.554
54 | Worker Dormitory | SF beam shuttering | SQM |  | 700.59 | 0 | 0 | 57.39
55 | Worker Dormitory | SF Slab shuttering | SQM |  | 664.23 | 0 | 0 | 57.39
56 | Worker Dormitory | SF lintel shuttering | SQM |  | 111.23 | 0 | 0 | 700.59
57 | Worker Dormitory | FF to SF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 32.822
58 | Worker Dormitory | SF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
59 | Worker Dormitory | SF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
60 | Worker Dormitory | SF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
61 | Worker Dormitory | SF lintel Concrete | CUM |  | 7.5 | 0 | 0 | 7.5
62 | Worker Dormitory | Brick masonary SF (230 mm) | CUM | 80 | 77.3 | 0 | 0 | 77.3
63 | Worker Dormitory | Brick masonary SF (115 mm) | SMT | 1170 | 691.13 | 0 | 0 | 691.13
64 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 2167.33 | 0 | 0 | 2167.33
65 | Worker Dormitory | Flooring | SMT | 830 | 670.5 | 0 | 0 | 670.5
66 | Worker Dormitory | Skirting | RMT | 1865 | 716 | 0 | 0 | 716
67 | Worker Dormitory | SF to TF slab column shuttering | SQM | 1680 | 427.554 | 0 | 0 | 427.55
68 | Worker Dormitory | TF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
69 | Worker Dormitory | TF beam shuttering | SQM |  | 700.59 | 0 | 0 | 700.59
70 | Worker Dormitory | TF Slab shuttering | SQM |  | 664.23 | 0 | 0 | 664.26
71 | Worker Dormitory | TF lintel shuttering | SQM |  | 111.23 | 0 | 0 | 111.23
72 | Worker Dormitory | SF to TF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 32.822
73 | Worker Dormitory | TF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
74 | Worker Dormitory | TF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
75 | Worker Dormitory | TF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
76 | Worker Dormitory | TF lintel Concrete | CUM |  | 7.5 | 0 | 0 | 7.5
77 | Worker Dormitory | Brick masonary SF (230 mm) | CUM | 80 | 77.3 | 0 | 0 | 77.3
78 | Worker Dormitory | Brick masonary SF (115 mm) | SMT | 1170 | 691.13 | 0 | 0 | 691.13
79 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 2167.33 | 0 | 0 | 2167.33
80 | Worker Dormitory | Flooring | SMT | 830 | 670.5 | 0 | 0 | 670.5
81 | Worker Dormitory | Skirting | RMT | 1865 | 716 | 0 | 0 | 716
82 | Worker Dormitory | TF to FF slab column shuttering | SQM | 1680 | 427.554 | 0 | 0 | 427.554
83 | Worker Dormitory | FF Staircase Shuttering | SQM |  | 57.39 | 0 | 0 | 57.39
84 | Worker Dormitory | FF beam shuttering | SQM |  | 700.59 | 0 | 0 | 700.59
85 | Worker Dormitory | FF Slab shuttering | SQM |  | 664.23 | 0 | 0 | 664.23
86 | Worker Dormitory | FF lintel shuttering | SQM |  | 111.23 | 0 | 0 | 111.23
87 | Worker Dormitory | TF to FF slab column concrete | CUM | 210 | 32.822 | 0 | 0 | 32.822
88 | Worker Dormitory | FF Staircase Concrete | CUM |  | 8.53 | 0 | 0 | 8.53
89 | Worker Dormitory | FF beam Concrete | CUM |  | 61.76 | 0 | 0 | 61.76
90 | Worker Dormitory | FF Slab Concrete | CUM |  | 101.99 | 0 | 0 | 101.99
91 | Worker Dormitory | FF lintel Concrete | CUM |  | 7.5 | 0 | 0 | 7.5
92 | Worker Dormitory | Brick masonary FF (230 mm) | CUM | 80 | 77.3 | 0 | 0 | 77.3
93 | Worker Dormitory | Brick masonary FF (115 mm) | SMT | 1170 | 691.13 | 88.13 | 88.13 | 691.13
94 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 2167.33 | 0 | 0 | 2167.33
95 | Worker Dormitory | Flooring | SMT | 830 | 670.5 | 0 | 0 | 670.5
96 | Worker Dormitory | Skirting | RMT | 1865 | 716 | 0 | 0 | 716
97 | Worker Dormitory | Terrace Floor column shuttering | SQM | 1680 | 98.52 | 0 | 0 | 98.52
98 | Worker Dormitory | Terrace Floor beam shuttering | SQM |  | 65 | 0 | 0 | 65
99 | Worker Dormitory | Terrace floor Slab shuttering | SQM |  | 60 | 0 | 0 | 60
100 | Worker Dormitory | Terrace Floor column concrete | CUM | 210 | 6.26 | 0 | 0 | 6.26
101 | Worker Dormitory | Stair Cabin beam Concrete | CUM |  | 5.42 | 0 | 0 | 5.42
102 | Worker Dormitory | Stair Cabin Slab Concrete | CUM |  | 8.98 | 0 | 0 | 8.98
103 | Worker Dormitory | Brick masonary FF (230 mm) | CUM | 80 | 68.073 | 0.003 | 0 | 68.07
104 | Worker Dormitory | Brick masonary FF (115 mm) | SMT | 1170 | 19.16 | 0 | 0 | 19.16
105 | Worker Dormitory | Internal Plaster | SMT | 1591.21 | 262.66 | 0 | 0 | 262.66
106 | Worker Dormitory | Waterproofing of Slab | SMT | 850 | 841.1628 | 0 | 0 | 841.1628
107 | Worker Dormitory | Excavation | CUM | 3925 | 273.29 | 0 | 0 | 273.29
108 | Worker Dormitory | PCC | CUM | 110 | 13.66 | 0 | 0 | 13.66
109 | Worker Dormitory | Raft RCC | CUM | 380 | 17.07 | 0 | 0 | 17.07
110 | Worker Dormitory | Rcc wall | CUM |  | 37.812 | 0 | 0 | 37.812
111 | Worker Dormitory | RCC slab Concrete | CUM |  | 12.33 | 0 | 0 | 12.33
112 | Worker Dormitory | Raft shuttering | SMT | 1680 | 7.54 | 0 | 0 | 0
113 | Worker Dormitory | Rcc wall shuttering | SMT |  | 607.672 | 0 | 0 | 607.672
114 | Worker Dormitory | RCC slab shuttering | SMT |  | 82.202 | 0 | 0 | 82.202
115 | Worker Dormitory | Waterproofing plaster | SMT | 675 | 398.29 | 0 | 0 | 398.29
116 | Worker Dormitory | Excavation | CUM | 1585 | 387.55 | 0 | 0 | 387.55
117 | Worker Dormitory | PCC (Footing+Beam) | CUM | 65 | 47.3 | 0 | 0 | 47.3
118 | Worker Dormitory | Footing RCC | CUM | 165 | 29.97 | 0 | 0 | 29.97
119 | Worker Dormitory | Padestal RCC | CUM |  | 51.575 | 0 | 0 | 51.575
120 | Worker Dormitory | Beam RCC | CUM |  | 47.504 | 0 | 0 | 47.504
121 | Worker Dormitory | Footing shuttering | SMT | 965 | 95 | 0 | 0 | 95
122 | Worker Dormitory | Padestal shuttering | SMT |  | 616.644 | 0 | 0 | 616.644
123 | Worker Dormitory | Beam shuttering | SMT |  | 271.453 | 0 | 0 | 271.453
124 | Worker Dormitory | Masonry | CUM | 229 | 203.59 | 0 | 0 | 203.59
125 | Worker Dormitory | Plaster | SMT | 940 | 891.92 | 0 | 0 | 891.92
126 | Worker Dormitory | Precast Panels | SMT | 322 | 322 | 0 | 0 | 322

## Design status
DESIGN STATUS
Project: Arvind Limited,Santej
Client: | Arvind Limited
Consultants: | AK.Consultant
PMC: | Sharnam Project Develoment & Consultants & Co
Sr. No. | Status | Status (In Percentage) | Planned End Date | Remark
1 | Architectural | 100% | - | As Per Approved MockUp sample Further Drawings were not required | 0.91176
2 | Structural | 100% | - | As Per Approved MockUp sample Further Drawings were not required | 0.96552
3 | Electrical | 100% |  |  | 1
4 | Plumbing | 100% |  |  | 1
5 | Fire Protection | 100% |  |  | 1