## Dashboard
Budget Dashboard - Project # - Week #
Revision Date: | 2026-01-22 |  | Baseline Cost | 104684308.9558 | Current Cost | 100626103.0926 | Remaining/Overrun Cost | -4058205.8632
Row Labels | Sum of Saving Amount
8 | 479225.9556
16 | 398136.0595
20 | 317154.6675
12 | 238683.363
10 | 83423.184
Grand Total | 1516623.2296
Row Labels | Sum of Basic Rate Amount | Sum of Purchase Rate Amount
1st Purchase | 336000 | 321093.9
2nd Purchase | 196000 | 177734.55
3rd Purchase | 392000 | 335169.45
4th Purchase | 336000 | 277118.7
Grand Total | 1260000 | 1111116.6
Saving in Concrete
1.49 Lakh
Saving in Steel
15.17 Lakh
Project Health
1.12

## Tracking
Revised on - 16-02-2023 | Project Budget with Cash-Flow
Month | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Planned Budget (EXCLUDING GST) | 6485619.2327 | 8564401.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327
YY | Work Done - Cost Status
Prgress Percentage(As per Schedule) | 90% | 90% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0!
Work Description | MONTH
| 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Project Development Consultancy | 2025-10-01: 100000; 2025-11-01: 100000; 2025-12-01: 100000; 2026-01-01: 100000
Civil Works | 2025-10-01: 3000000; 2025-11-01: 3000000; 2025-12-01: 3000000; 2026-01-01: 3000000
Anti Termite Service | 2025-10-01: 0; 2025-11-01: 35532; 2025-12-01: 0; 2026-01-01: 0
Road development | 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 200000; 2026-01-01: 200000
Borewell | 2025-10-01: 0; 2025-11-01: 1000000; 2025-12-01: 0; 2026-01-01: 0
External Electrification ( power connection cost ) | 2025-10-01: 300000; 2025-11-01: 200000; 2025-12-01: 200000; 2026-01-01: 200000
Temporary Power Connection | 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0
UG Tank | 2025-10-01: 50000; 2025-11-01: 100000; 2025-12-01: 100000; 2026-01-01: 100000
External Drainage network & STP | 2025-10-01: 50000; 2025-11-01: 100000; 2025-12-01: 100000; 2026-01-01: 100000
Soil filling (within Plot area) | 2025-10-01: 1000000; 2025-11-01: 1000000; 2025-12-01: 63250; 2026-01-01: 0
Compound wall (Precast) | 2025-10-01: 0; 2025-11-01: 50000; 2025-12-01: 80000; 2026-01-01: 80000
Electrical Package | 2025-10-01: 300000; 2025-11-01: 300000; 2025-12-01: 300000; 2026-01-01: 300000
Plumbing Package | 2025-10-01: 500000; 2025-11-01: 500000; 2025-12-01: 500000; 2026-01-01: 500000
Furniture Package | 2025-10-01: 300000; 2025-11-01: 300000; 2025-12-01: 300000; 2026-01-01: 300000
Aluminum Package | 2025-10-01: 50000; 2025-11-01: 50000; 2025-12-01: 50000; 2026-01-01: 50000
Fire Package | 2025-10-01: 10000; 2025-11-01: 10000; 2025-12-01: 10000; 2026-01-01: 10000
Actual Work Done (EXCLUDING GST) | 5650000 | 6735532 | 4993250 | 4930000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned Value | 5837057.3094 | 7707961.1094 | 5975619.2327 | 5378057.3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
CPI | 2025-10-01: 1.0331; 2025-11-01: 1.1444; 2025-12-01: 1.1967; 2026-01-01: 1.0909 | 1.1163
XX - YY | 2025-10-01: Difference (Planned Vs Actual)
Month | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Difference | 2025-10-01: 835619.2327; 2025-11-01: 1828869.2327; 2025-12-01: 982369.2327; 2026-01-01: 1045619.2327; 2026-02-01: 5975619.2327; 2026-03-01: 5975619.2327; 2026-04-01: 5975619.2327; 2026-05-01: 5975619.2327
Invoice Month | 2025-10-01: Civil Construction Works
| RA BILL |  |  |  | Deduction |  |  | Hold |  | Taxes |  | COP for Amount
| Vendor | RA Bill | Type of Work | Work Done Amount | Retention (5%/10% of work done cost) | Advance (6.25% on Prorata basis) | Others | Amount | Release | SGST@9% | CGST@9%
2025-10-01 | M/S Bhavna Infra | ADVANCE | Mobilization | 3000000 | 150000 | 0 | 0 | 0 | 0 | 270000 | 270000 | 3390000
2025-11-01 | M/S Bhavna Infra | RA 01 | Dormatory | 3000000 | 150000 | 187500 | 0 | 0 | 0 | 270000 | 270000 | 3202500
2025-12-01 | M/S Bhavna Infra | RA 02 | KB-02 Works | 3000000 | 150000 | 187500 | 0 | 0 | 0 | 270000 | 270000 | 3202500
2026-01-01 | M/S Bhavna Infra | RA 03 | Temporary Road and Culvert Works | 3000000 | 150000 | 187500 | 0 | 0 | 0 | 270000 | 270000 | 3202500
2026-02-01 | bar: 2025-10-01 to 2026-04-01; 2026-07-01 to 2026-09-01
2026-03-01 | bar: 2025-10-01 to 2026-04-01; 2026-07-01 to 2026-09-01
2026-04-01 | bar: 2025-10-01 to 2026-04-01; 2026-07-01 to 2026-09-01
2026-05-01 | bar: 2025-10-01 to 2026-04-01; 2026-07-01 to 2026-09-01
2026-06-01 | bar: 2025-10-01 to 2026-04-01; 2026-07-01 to 2026-09-01
2026-07-01 | bar: 2025-10-01 to 2026-04-01; 2026-07-01 to 2026-09-01
Total - Civil Works | 2026-01-01: 12000000; 2026-02-01: 600000; 2026-03-01: 562500; 2026-04-01: 0; 2026-05-01: 0; 2026-06-01: 0; 2026-07-01: 1080000; 2026-08-01: 1080000; 2026-09-01: 12997500

## Cash Flow Chart - INR
Month | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | Total
Planned Budget (EXCLUDING GST) | 6485619.2327 | 8564401.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 104684308.9558
Planned Budget (EXCLUDING GST) Cumulative |  | 15050020.4654 | 21025639.6981 | 27001258.9308 | 32976878.1635 | 38952497.3962 | 44928116.6289 | 50903735.8616 | 56879355.0943 | 62854974.3269 | 68830593.5596 | 74806212.7923 | 80781832.025 | 86757451.2577 | 92733070.4904 | 98708689.7231 | 104684308.9558
Actual Work Done (EXCLUDING GST) | 5650000 | 6735532 | 4993250 | 4930000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22308782
Actual Work Done (EXCLUDING GST) Cumulative |  | 12385532 | 17378782 | 22308782 | [13 empty] | 52073096
44928116.6289

## Cash Flow - Forecast
TENTATIVE CASH FLOW IN (INR)
|  |  | Q3-2022 | Q4-2025 |  |  | Q1-2026 |  |  | Q2-2026 |  |  | Q3-2026 |  |  | Q4-2026 |  |  | Q1-2027
Sr. No. | Structure |  | 2022-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2024-03-22 | Total
0
1 | Project Development Consultancy | 2400000 |  | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 | 141176.4706 |  | 2400000
2 | Civil Works | 57100726.9558 |  | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 3358866.2915 | 57100726.9558 | 0
3 | Anti Termite Service | 35532 |  | 10000 | 25532 | [15 empty] | 2090.1176 | 35532 | 0
4 | Road development | 3600000 |  | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 211764.7059 | 3600000 | 0
3 | Borewell | 1000000 |  | 500000 | 500000 | [15 empty] | 58823.5294 | 1000000
4 | External Electrification ( power connection cost ) | 5000000 |  | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 5000000
5 | Temporary Power Connection | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | UG Tank | 6000000 |  | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 352941.1765 | 6000000
5 | External Drainage network & STP | 5000000 |  | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 294117.6471 | 5000000
6 | Soil filling (within Plot area) | 2063250 |  | 0 | 2063250 | [15 empty] | 121367.6471 | 2063250
7 | Compound wall (Precast) | 1449000 |  | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 85235.2941 | 1449000
8 | Electrical Package | 5258950 |  | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 5258950
7 | Plumbing Package | 5258950 |  | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 309350 | 5258950
8 | Furniture Package | 9146000 |  | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 538000 | 9146000
9 | Aluminum Package | 1143250 |  | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 67250 | 1143250
10 | Fire Package | 228650 |  | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 13450 | 228650
AMOUNT IN INR |  | 104684308.9558 | 0 | 6485619.2327 | 8564401.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 | 5975619.2327 |  | 104684308.9558 | 104684308.9558
Note: Above amounts are excluding of contingency
#REF!
790000000
549000000

## Budget
Budget WBS |  |  | Budgeted Amount | Work Order Amount | Certifed Amount | FORECASTED / NON TENDERED ITEMS |  |  | Basic Rate Diffrence ( BRD ) |  |  |  | Total
Sr No | Description | Name of Stackholder | Amount | Actual WO Amount (Basic ) | Certified Amount ( Basic ) | Fore Casted ( Based on GFC ) |  | Non Tendered Items | Steel ( Till Date ) |  | Cement ( Till Date ) |  | Gross Total Amount ( Projected )
[6 empty] | Addition | Reduction |  | Excess | Saving | Excess | Saving
1 | Project Development Consultancy | SPDC | 2400000 | 1720000 | 722795.1 | 0 | 0 | 0 |  |  |  |  | 1720000
2 | Project Consultant | AK Consultant |  | 740000 | 250000 | 0 | 0 | 0 |  |  |  |  | 740000
2.1 | Project Consultant | Vishwas Patel |  | 750000 | 750000 | 0 | 0 | 0 |  |  |  |  | 750000
3 | Project Package | [11 empty] | 0
3.1 | Construction cost for Dormitory blocks | M/s Bhavna Infra | 57100726.9558 | 57673579 | 20483680 | 5521220.1684 | 13474470.9062 | 1592674.46 | 0 | 1516623.2296 | 0 | 148883.4 | 49647496.0926
3.1.1 | Anti-termite service | M/s Surti Pest-Control | 35532 | 35532 | [8 empty] | 35532
3.2 | Road development |  | 3600000 |  | 0 | 0 | 0 | 0 |  |  |  |  | 3600000
3.3 | Borewell |  | 1000000 | 1790460 | 895230 | 0 | 0 | 0 |  |  |  |  | 1790460
3.4 | External Electrification ( power connection cost ) |  | 5000000 |  | 0 | 0 | 0 | 0 |  |  |  |  | 4649950
3.4.1 | Temporary Power Connection | M/s. Indian Electricals |  | 350050 | 333900 | 0 | 0 | 0 |  |  |  |  | 350050
3.5 | UG Tank |  | 6000000 |  | 0 | 0 | 0 | 0 |  |  |  |  | 6000000
3.6 | External Drainage network & STP |  | 5000000 |  | 0 | 0 | 0 | 0 |  |  |  |  | 5000000
3.7 | Soil filling (within Plot area) |  | 2063250 |  | 0 | 0 | 0 | 0 |  |  |  |  | 2063250
3.8 | Compound wall (Precast) |  | 1449000 |  | 0 | 0 | 0 | 0 |  |  |  |  | 1449000
4 | Electrical Package | Pearl Electricals | 5258950 | 7053515 | 0 | 0 | 0 | 0 |  |  |  |  | 7053515
5 | Plumbing Package |  | 5258950 |  | 0 | 0 | 0 | 0 |  |  |  |  | 5258950
6 | Furniture Package |  | 9146000 |  | 0 | 0 | 0 | 0 |  |  |  |  | 9146000
7 | Aluminum Package |  | 1143250 |  | 0 | 0 | 0 | 0 |  |  |  |  | 1143250
8 | Fire Package |  | 228650 |  | 0 | 0 | 0 | 0 |  |  |  |  | 228650
Total Net Project Cost : |  |  | 104684308.9558 | 70113136 | 23435605.1 | 5521220.1684 | 13474470.9062 | 1592674.46 | 0 | 1516623.2296 | 0 | 148883.4 | 100626103.0926
GST 18 % : |  |  | 18843175.612 | 12620364.48 | 4218408.918 | 993819.6303 | 2425404.7631 | 286681.4028 | 0 | 272992.1813 | 0 | 26799.012 | 18112698.5567
Total Project Cost : |  |  | 123527484.5679 | 82733500.48 | 27654014.018 | 6515039.7988 | 15899875.6693 | 1879355.8628 | 0 | 1789615.4109 | 0 | 175682.412 | 118738801.6493
Expected Over Budget/ Reaminaing in Project Compare to Budget Value : |  |  | Reamaining Amount From Budget ( Basic Amount ) : -4058206
| Total Cost | 104684308.9558
| Actual WO Amount | 70113136
| Total Certified Amount | 23435605.1
| Baseline Cost | 104684308.9558
| Current Budget | 100626103.0926
| Cost Saving | -4058205.8632
Note on F9: Administrator: P.O Amedement

## Monitoring
ITEM NO. | Item of Work | UOM | RATE | BOQ Qty | Extra Itmes Qty | GFC Qty | Achived QTY | Excess Qty ( BOQ Vs GFC ) | Saving Qty ( BOQ Vs GFC ) | Certifed Qty ( Inoice ) | BOQ Cost | Extra Item Cost | GFC Cost | Achived Cost | Excess ( BOQ Vs GFC ) Cost | Saving ( BOQ Vs GFC ) Cost | Certified Invoice Cost | % of Progress against BOQ | % of Progress against GFC | % of Progress against Achived | % of Progress against Certified Qty | Earned Value ( EV) agaisnt BOQ cost | Earned Value ( EV) agaisnt GFC cost | Earned Value ( EV) agaisnt Certifed Invoice cost | Actual Cost (AC) | CPI ( Cost Perfromance Index ) | CPI Status | ETC ( Against BOQ ) | ETC ( Against GFC ) | ETC ( Against Certified Invoice ) ) | EAC | VAC | Variance ( BOQ vs GFC) | Variance ( GFC vs Achived) | Variance ( GFC vs Certified Invoice) | Cost Over turn (BOQ Vs Variance ) | Cost Over turn (GFC Vs Variance ) | Cost Over turn (GFC Vs Certifed Invoice )
|  |  |  | Qty | [6 empty] | Cost | [6 empty] | Progress |  |  |  | Earned Value |  |  | Cost Tracking & Monitor |  |  | Estimate to Complete |  |  | Estimate at Completion | Variance at Completion | Variations |  |  | Cost Over run
1 | Excavation in all types of soil viz., sand, clay, gravel, Clayton, mud, slush other than rock for foundation of walls, columns, cable trenches, equipment foundation, etc. as per the Drawing, including shorting, dewatering subsoil water/Rain water wherever required and disposing off surplus materials (after utilization of back filling) selected earth within the site (Maximum lead 500mtr) at locations as directed by the engineer-in-charge including Back filling in foundation with approved materials inclusive of spreading in layers 150 mm thick, consolidating each layer by ramming, watering, Compacting the same with Vibro roller or in space constraints vibrating plate compactor etc. complete. (Minimum 1.60 gms / Cu.cm.) ( PCC area will be measured and paid for excavation & Backfilling )
2 | -do 0.0 mt to 1.5 mt | Cmt | 178 | 1750 | 0 | 924.8445 | 924.85 | 0 | 825.1555 |  | 311500 | 0 | 164622.3228 | 164623.3 | 0 | 146877.6772 |  | 52.8486 | 100.0006 | 52.85% |  | 164623.3 | 164623.3 | 0 | 164623.3 | 1 | On Budget | 146876.7 | -0.97722 |  | 311500 | 0 | 146877.6772 | -0.97722 |  | 0.47152 | -5.9361e-06 | 0
3 | -do 1.5 mt to 3.0 mt | Cmt | 268 | 1625 | 0 | 913.05 | 913.05 | 0 | 711.95 |  | 435500 | 0 | 244697.4 | 244697.4 | 0 | 190802.6 |  | 56.1877 | 100 | 56.19% |  | 244697.4 | 244697.4 | 0 | 244697.4 | 1 | On Budget | 190802.6 | 0 |  | 435500 | 0 | 190802.6 | 0 |  | 0.43812 | 0 | 0
4 | -do 3.0 mt to 4.5 mt | Cmt | 375 | 550 | 0 | 0 | 0 | 0 | 550 |  | 206250 | 0 | 0 | 0 | 0 | 206250 |  | 0 |  | 0%
5 | Filling in plinth with approved materials like yellow earth/murrum in layers of 150 mm thickness, consolidating each layer by ramming and watering and rolling with vibro roller for a compaction to the modified proctor density of 95 percent of approved borrow pit. (Minimum 1.60 gms / Cu.cm.) - Approved Good quality Earth brought from Outside | Cmt | 495 | 110 | 0 | 0 | 0 | 0 | 110 |  | 54450 | 0 | 0 | 0 | 0 | 54450 |  | 0 |  | 0%
6 | 'Filling in plinth/plot with approved materials like yellow earth/murrum in layers of 150 mm thickness, consolidating each layer by ramming and watering and rolling with vibro roller for a compaction to the modified proctor density of 95 percent of approved borrow pit. (Minimum 1.60 gms / Cu.cm.) Selected earth obtained from available plote area - cutting and filling | Cmt | 200 | 10000 | 0 | 1123.219 | 1123.22 | 0 | 8876.781 |  | 2000000 | 0 | 224643.8028 | 224644 | 0 | 1775356.1972 |  | 11.2322 | 100.0001 | 11.23%
7 | Providing and laying of avg 0.23 mm thick rubble soling using avg 90 mm thick rubble , including Compacting and filling the interstices with good quality approved earth/stone dust as binding material, spreading, watering, and consolidation of binding materials as directed by the Engineer-in charge | Cmt | 2000 | 195.5 | 0 | 173.8094 | 173.81 | 0 | 21.6906 |  | 391000 | 0 | 347618.78 | 347620 | 0 | 43381.22 |  | 88.9054 | 100.0004 | 88.91%
8 | Providing, mixing and laying plain cement concrete with avg 20-40 mm nominal size graded aggregates of approved quality as a levelling course under the column foundation, wall foundation, cable trenches, other trenches, machinery foundations, raft foundations, pipe supports, plinth beam, as floor sub base, etc. including ramming, levelling, curing etc. complete at any level (i.e. up to any depth or height from ground level). Please consider the cost of form work if required any. - M10 | Cmt | 3925 | 265 | 0 | 223.5505 | 223.55 | 0 | 41.4495 |  | 1040125 | 0 | 877435.6536 | 877433.75 | 0 | 162689.3464 |  | 84.3585 | 99.9998 | 84.36% |  | 877433.75 | 877433.75 | 0 | 877433.75 | 1 | On Budget | 162691.25 | 1.9036 |  | 1040125 | 0 | 162689.3464 | 1.9036 |  | 0.15641 | 2.1695e-06 | 0
9 | Providing, mixing, Batching, Transporting through Transit Mixers, Pumping and laying plain / Reinforced cement concrete M:25 with 20 mm and downsized aggregate in all type of works such as foundation and superstructures, footings, pile caps, raft beams, columns, runners, coping beam, walls, slabs, lintels, tie-beams, canopies, staircase, fins, ledge, etc. in any pattern & shapes all including making openings, leaving sleeves in pedestals, columns, beams, slabs,pocket etc. complete as per the drawing and specification excluding the cost of formwork. and excluding the cost of Reinforcement. NOTE: Minimum Cement content 350Kgs/Cum. For Moderate condition -up to PL | Cmt | 5350 | 380 | 0 | 519.0008 | 513.14 | 139.0008 | 0 |  | 2033000 | 0 | 2776654.1128 | 2745299 | 743654.1128 | 0 |  | 135.0368 | 98.8708 | 135% |  | 2745299 | 2745299 | 0 | 2745299 | 1 | On Budget | -712299 | 31355.1128 |  | 2033000 | 0 | -743654.1128 | 31355.1128 |  | -0.36579 | 0.011292 | 0
10 | -do PL to G.F. Slab | Cmt | 5400 | 210 | 0 | 208.2771 | 206.57 | 0 | 1.7229 |  | 1134000 | 0 | 1124696.3562 | 1115478 | 0 | 9303.6438 |  | 98.3667 | 99.1804 | 98.37%
11 | -do G.F. to F.F. Slab | Cmt | 5550 | 210 | 0 | 208.2771 | 189.56 | 0 | 1.7229 |  | 1165500 | 0 | 1155937.9217 | 1052058 | 0 | 9562.0783 |  | 90.2667 | 91.0134 | 90.27%
12 | -do F.F. to S.F. Slab | Cmt | 5700 | 210 | 0 | 208.2771 | 172.28 | 0 | 1.7229 |  | 1197000 | 0 | 1187179.4871 | 981996 | 0 | 9820.5129 |  | 82.0381 | 82.7167 | 82.04%
13 | -do S.F. to T.F. Slab | Cmt | 5800 | 210 | 0 | 208.2771 | 22.68 | 0 | 1.7229 |  | 1218000 | 0 | 1208007.1974 | 131544 | 0 | 9992.8026 |  | 10.8 | 10.8893 | 10.8%
14 | -do T.F. to F.F. Slab | Cmt | 5900 | 210 | 0 | 208.2771 | 0 | 0 | 1.7229 |  | 1239000 | 0 | 1228834.9077 | 0 | 0 | 10165.0923 |  | 0 | 0 | 0%
15 | Providing, cutting, bending, binding, laying, transporting and fixing in position at up to any levels (depth & height) reinforcement bars for all concrete works including 16 gauge annealed M.S. wire, spacer blocks of C.M. 1:2 with embedded binding wire of suitable length, protective coat of neat cement slurry to be applied as per Engineer-in-charge etc. complete. Bar bending schedule to be prepared by contractor. Any variation in reinforcement will be adjusted as per B.B.S. (Bar bending schedule) subject to approval and joint record by Engineer-in-Charge.- FE 500 TMT | M.T. | 69100 | 153.0332 | 0 | 177.4449 | 153.05 | 24.4117 | 0 |  | 10574597.2965 | 0 | 12261445.9394 | 10575755 | 1686848.6428 | 0 |  | 100.0109 | 86.2521 | 100% |  | 10575755 | 10575755 | 0 | 10575755 | 1 | On Budget | -1157.7035 | 1685690.9394 |  | 10574597.2965 | 0 | -1686848.6428 | 1685690.9394 |  | -0.15952 | 0.13748 | 0
16 | Providing & fixing in position and removing any pattern and shape of good quality plastic coated high density shuttering plywood/MS formwork for all plain / reinforced concrete works including necessary centering and shuttering, applying approved shuttering oil, etc. complete as directed. No extra to be paid for curved, circular shuttering and staging for direct height if required for any level. | Smt | 415 | 1075 | 0 | 1651.2538 | 1651.25 | 576.2538 | 0 |  | 446125 | 0 | 685270.3063 | 685268.75 | 239145.3063 | 0 |  | 153.6047 | 99.9998 | 153.6% |  | 685268.75 | 685268.75 | 0 | 685268.75 | 1 | On Budget | -239143.75 | 1.5563 |  | 446125 | 0 | -239145.3063 | 1.5563 |  | -0.53605 | 2.271e-06 | 0
17 | -do PL to G.F. Slab | Smt | 430 | 1680 | 0 | 1933.9838 | 1905.76 | 253.9838 | 0 |  | 722400 | 0 | 831613.034 | 819476.8 | 109213.034 | 0 |  | 113.4381 | 98.5406 | 113.4%
18 | -do G.F. to F.F. Slab | Smt | 455 | 1680 | 0 | 1933.9838 | 1735.58 | 253.9838 | 0 |  | 764400 | 0 | 879962.629 | 789688.9 | 115562.629 | 0 |  | 103.3083 | 89.7412 | 103.3%
19 | -do F.F. to S.F. Slab | Smt | 480 | 1680 | 0 | 1933.9838 | 1389.23 | 253.9838 | 0 |  | 806400 | 0 | 928312.224 | 666830.4 | 121912.224 | 0 |  | 82.6923 | 71.8326 | 82.69%
20 | -do S.F. to T.F. Slab | Smt | 505 | 1680 | 0 | 1933.9838 | 846.42 | 253.9838 | 0 |  | 848400 | 0 | 976661.819 | 427442.1 | 128261.819 | 0 |  | 50.3821 | 43.7656 | 50.38%
21 | -do T.F. to F.F. Slab | Smt | 530 | 1680 | 0 | 1933.9838 | 0 | 253.9838 | 0 |  | 890400 | 0 | 1025011.414 | 0 | 134611.414 | 0 |  | 0 | 0 | 0%
22 | Providing and laying first class brick masonry works in C.M. 1:6 for foundation up to any depth from ground level and plinth up to any height from ground level including scaffolding, watering, racking out joints, etc. complete in all respect. (Minimum compressive strength of the brick shall be 50 kg./Sq.Cm.) - do up to PL | Cmt | 5790 | 130 | 0 | 102.4617 | 100.38 | 0 | 27.5383 |  | 752700 | 0 | 593252.994 | 581200.2 | 0 | 159447.006 |  | 77.2154 | 97.9684 | 77.22%
23 | -do PL to G.F. Slab | Cmt | 5790 | 80 | 0 | 73.4798 | 43.86 | 0 | 6.5202 |  | 463200 | 0 | 425448.1868 | 253949.4 | 0 | 37751.8132 |  | 54.825 | 59.6899 | 54.83%
24 | -do G.F. to F.F. Slab | Cmt | 5940 | 80 | 0 | 73.4798 | 28.63 | 0 | 6.5202 |  | 475200 | 0 | 436470.1605 | 170062.2 | 0 | 38729.8395 |  | 35.7875 | 38.9631 | 35.79%
25 | -do F.F. to S.F. Slab | Cmt | 6090 | 80 | 0 | 73.4798 | 0 | 0 | 6.5202 |  | 487200 | 0 | 447492.1343 | 0 | 0 | 39707.8657 |  | 0 | 0 | 0%
26 | -do S.F. to T.F. Slab | Cmt | 6240 | 80 | 0 | 73.4798 | 0 | 0 | 6.5202 |  | 499200 | 0 | 458514.108 | 0 | 0 | 40685.892 |  | 0 | 0 | 0%
27 | -do T.F. to F.F. Slab | Cmt | 6390 | 80 | 0 | 92.8191 | 0 | 12.8191 | 0 |  | 511200 | 0 | 593114.3366 | 0 | 81914.3366 | 0 |  | 0 | 0 | 0%
28 | Providing and laying brick masonry work for a 115 mm thick partition wall in C.M. 1:4 at all depth & heights including laying horizontally 2 nos. 8 mm. Dia. Reinforcement BARS at every 4th course including scaffolding, curing, etc. complete in all respect. (Reinforcement Bars to be paidseparately). (Minimum compressive strength of the brick shall be 50 kg. /Sq.Cm).- do up to GF | Smt | 785 | 1170 | 0 | 767.8539 | 356.26 | 0 | 402.1461 |  | 918450 | 0 | 602765.3115 | 279664.1 | 0 | 315684.6885 |  | 30.4496 | 46.3968 | 30.45%
29 | -do G.F. to F.F. Slab | Smt | 805 | 1170 | 0 | 767.8539 | 174.55 | 0 | 402.1461 |  | 941850 | 0 | 618122.3895 | 140512.75 | 0 | 323727.6105 |  | 14.9188 | 22.7322 | 14.92%
30 | -do F.F. to S.F. Slab | Smt | 825 | 1170 | 0 | 767.8539 | 0 | 0 | 402.1461 |  | 965250 | 0 | 633479.4675 | 0 | 0 | 331770.5325 |  | 0 | 0 | 0%
31 | -do S.F. to T.F. Slab | Smt | 845 | 1170 | 0 | 767.8539 | 0 | 0 | 402.1461 |  | 988650 | 0 | 648836.5455 | 0 | 0 | 339813.4545 |  | 0 | 0 | 0%
32 | -do T.F. to F.F. Slab | Smt | 865 | 1170 | 0 | 767.8539 | 0 | 0 | 402.1461 |  | 1012050 | 0 | 664193.6235 | 0 | 0 | 347856.3765 |  | 0 | 0 | 0%
33 | -do F.F. to Terrace | Smt | 885 | 215 | 0 | 328.67 | 0 | 113.67 | 0 |  | 190275 | 0 | 290872.95 | 0 | 100597.95 | 0 |  | 0 | 0 | 0%
34 | Providing and laying 12 mm thick cement plaster to all surfaces of brick masonry, and R.C.C. in C.M. 1:4 finished smooth with cement punning including scaffolding, racking of joints, racking of RCC surface, curing, etc. complete including providing and fixing G.I. chicken wire mesh either side of joint of the junction of R.C.C. / P.C.C. and masonry, Bonding chemical etc. as directed by Engineer-in-Charge. The item is inclusive of grooves up to 12 x 12mm, drip moulds (50 mm wide x 12 mm thick), bands of any width etc. complete.- do up to PL | Smt | 270 | 140 | 0 | 0 | 0 | 0 | 140 |  | 37800 | 0 | 0 | 0 | 0 | 37800
35 | -do PL to G.F. Slab | Smt | 285 | 3325 | 0 | 1733.7925 | 663 | 0 | 1591.2075 |  | 947625 | 0 | 494130.8625 | 188955 | 0 | 453494.1375 |  | 19.9398 | 38.2399 | 19.94%
36 | -do G.F. to F.F. Slab | Smt | 305 | 3325 | 0 | 1733.7925 | 0 | 0 | 1591.2075 |  | 1014125 | 0 | 528806.7125 | 0 | 0 | 485318.2875 |  | 0 | 0 | 0%
37 | -do F.F. to S.F. Slab | Smt | 325 | 3325 | 0 | 1733.7925 | 0 | 0 | 1591.2075 |  | 1080625 | 0 | 563482.5625 | 0 | 0 | 517142.4375 |  | 0 | 0 | 0%
38 | -do S.F. to T.F. Slab | Smt | 345 | 3325 | 0 | 1733.7925 | 0 | 0 | 1591.2075 |  | 1147125 | 0 | 598158.4125 | 0 | 0 | 548966.5875 |  | 0 | 0 | 0%
39 | -do T.F. to F.F. Slab | Smt | 365 | 3325 | 0 | 1733.7925 | 0 | 0 | 1591.2075 |  | 1213625 | 0 | 632834.2625 | 0 | 0 | 580790.7375 |  | 0 | 0 | 0%
40 | -do F.F. to Terrace | Smt | 385 | 425 | 0 | 326.816 | 0 | 0 | 98.184 |  | 163625 | 0 | 125824.16 | 0 | 0 | 37800.84 |  | 0 | 0 | 0%
41 | Providing and laying 20 mm thick. Double coat sand faced plaster in 2 coats over masonry surfaces, concrete surfaces, etc. First coat 15 mm thick in C.M. 1:4 & second coat of min. 5 mm thick in C.M. 1:2 at all heights including scaffolding, racking of concrete / masonry surfaces, curing, etc. complete including providing and fixing G.I. chicken wire mesh of 150mm overlap either side of joint of the junction of R.C.C. / P.C.C. and masonry, Bonding chemical as directed by Engineer-in-Charge. The item is inclusive of grooves up to 12 x 12mm, drip moulds (50x12 mm), bands of any width etc. complete. Approved by the consultant.(i.e. up to any depth or height from ground level) | Smt | 510 | 5235 | 0 | 3780.035 | 59.85 | 0 | 1454.965 |  | 2669850 | 0 | 1927817.85 | 30523.5 | 0 | 742032.15 |  | 1.1433 | 1.5833 | 1.143%
42 | Providing avg 20 mm th. Water proof cement plaster in c.m. (1:3) and pure cement finish using approved quality water proofing compound at the rate of 1 kg per bag of cement incl. watering, curing and making water proof giving the test of water proofness etc. comp. as directed. | Smt | 675 | 0 | 0 | 559.2 |  | 559.2 | 0 |  | 0 | 0 | 377460 | 0 | 377460 | 0
43 | Providing and applying two coats of acrylic exterior weather paint on out side of wall surface of approved quality paint like "APEX" ULTIMA brand make & required shade after thoroughly brushing the surface free from mortar & scrapping old white wash/snow sem or oil painted surface inc. scaffolding, cleaning the wall & preparing the surface even & smooth, filling the cracks incl. applying one coat of white priming coat of reputed brand as suggested by Engg. etc. comp.as directed. | Smt | 157 | 5235 | 0 | 3780.035 | 0 | 0 | 1454.965 |  | 821895 | 0 | 593465.495 | 0 | 0 | 228429.505 |  | 0 | 0 | 0%
44 | Providing & applying two coat of apporved quality oil bound distemper to give an even shade using Asian, Nerolac, Burger or equivallent brand of required shade approved by Higher Authority incl. applying two coats of approved quality putty after throughly brushing the surface to clean the mortar drops or any other foreign materials to give smooth surface to the wall incl. applying one coat of approved quality primer cleaning the putty suface by using sand paper etc. comp. as directed. (Rate includes cost of colour, primer, required scaffolding, watering, sand paper or any other equipments required to given an even & good look)includingApplying Two Coats of Birla (white cement based) or Asian Acrylic Lappy (Putty) and two coats of primer of approved brand and manufacture on New Wall Surface and ceiling to give an even shade including thoroughly brushing the surface free from mortar dropping and other foreign matter and sand papered smooth. | Smt | 157 | 17190 | 0 | 15553.438 | 0 | 0 | 1636.562 |  | 2698830 | 0 | 2441889.766 | 0 | 0 | 256940.234 |  | 0 | 0 | 0%
45 | Prov. & laying Digital 24" x 24" double charge mat Finish Vitrified 10 mm thick tiles flooring laid on bed of 20mm (Average) base of Cement Mortar 1:6 (1-Cement : 6 Coarse Sand) on new surface and jointed with colour cement slurry including finished with flush pointing & cleaning the surface etc. completed of any shade approved by Higher Authority of approved brands like Somani ,Rak, Asian, Varmora etc. - up to GF | Smt | 985 | 830 | 0 | 655.3705 | 55.15 | 0 | 174.6295 |  | 817550 | 0 | 645539.9425 | 54322.75 | 0 | 172010.0575 |  | 6.6446 | 8.4151 | 6.645%
46 | -do G.F. to F.F. Slab | Smt | 1015 | 830 | 0 | 655.3705 | 0 | 0 | 174.6295 |  | 842450 | 0 | 665201.0575 | 0 | 0 | 177248.9425 |  | 0 | 0 | 0%
47 | -do F.F. to S.F. Slab | Smt | 1045 | 830 | 0 | 655.3705 | 0 | 0 | 174.6295 |  | 867350 | 0 | 684862.1725 | 0 | 0 | 182487.8275 |  | 0 | 0 | 0%
48 | -do S.F. to T.F. Slab | Smt | 1075 | 830 | 0 | 655.3705 | 0 | 0 | 174.6295 |  | 892250 | 0 | 704523.2875 | 0 | 0 | 187726.7125 |  | 0 | 0 | 0%
49 | -do T.F. to F.F. Slab | Smt | 1105 | 830 | 0 | 655.3705 | 0 | 0 | 174.6295 |  | 917150 | 0 | 724184.4025 | 0 | 0 | 192965.5975 |  | 0 | 0 | 0%
50 | -do F.F. to Terrace | Smt | 1135 | 830 | 0 | 10.1625 | 0 | 0 | 819.8375 |  | 942050 | 0 | 11534.4375 | 0 | 0 | 930515.5625 |  | 0 | 0 | 0%
51 | Providing & laying Digital 24" x 24" double charge Glossy, mat or Rustic Vitrified 10mm thick tiles in Skirting, dedo, wall, riser etc as per approved pattern & design & laid over previously prepared 12 mm th. cement plaster in cement mortar (1:3) surface joint with white/coloured cement slurry complete. Shade & Size as per detailed drawing and approved by Higher authority of approved brands like Somani ,Rak, City, Sun Heart,Marbito as directed by Engineer in charge. - up to GF | Rmt | 145 | 1865 | 0 | 613.46 | 45 | 0 | 1251.54 |  | 270425 | 0 | 88951.7 | 6525 | 0 | 181473.3 |  | 2.4129 | 7.3354 | 2.413%
52 | -do G.F. to F.F. Slab | Rmt | 155 | 1865 | 0 | 613.46 | 0 | 0 | 1251.54 |  | 289075 | 0 | 95086.3 | 0 | 0 | 193988.7 |  | 0 | 0 | 0%
53 | -do F.F. to S.F. Slab | Rmt | 165 | 1865 | 0 | 613.46 | 0 | 0 | 1251.54 |  | 307725 | 0 | 101220.9 | 0 | 0 | 206504.1 |  | 0 | 0 | 0%
54 | -do S.F. to T.F. Slab | Rmt | 175 | 1865 | 0 | 613.46 | 0 | 0 | 1251.54 |  | 326375 | 0 | 107355.5 | 0 | 0 | 219019.5 |  | 0 | 0 | 0%
55 | -do T.F. to F.F. Slab | Rmt | 185 | 1865 | 0 | 613.46 | 0 | 0 | 1251.54 |  | 345025 | 0 | 113490.1 | 0 | 0 | 231534.9 |  | 0 | 0 | 0%
56 | Providing & laying Antiskid Vitrified 10mm thick tiles flooring, treads of steps and landing laid on bed of 20mm (Average) base of Cement Mortar 1:6 (1-Cement : 6 Coarse Sand) on new surface and jointed with colour cement slurry including finished with flush pointing & cleaning the surface etc. completed of any Shade and approved by Higher Authority of approved brands like Somani ,Rak, City, Sun Heart etc. & Size as per detailed drawing and as directed by Engineer in charge. | Smt | 1095 | 416 | 0 | 213.832 | 0 | 0 | 202.168 |  | 455520 | 0 | 234146.04 | 0 | 0 | 221373.96 |  | 0 | 0 | 0%
57 | Providing & laying Antiskid Vitrified 10mm thick tiles in Skirting, dedo, wall, riser etc as per approved pattern & design & laid over previously prepared 12 mm th. cement plaster in cement mortar (1:3) surface joint with white/coloured cement slurry complete. Shade and approved by Higher Authority of approved brands like Somani ,Rak, City, Sun Heart etc. & Size as per detailed drawing and as directed by Engineer in charge. | Smt | 1095 | 400 | 0 | 1489.2 | 0 | 1089.2 | 0 |  | 438000 | 0 | 1630674 | 0 | 1192674 | 0 |  | 0 | 0 | 0%
58 | Providing & laying avg 20 mm thick polished Kotah stone in single piece in Step/Riser,seal & james of doors & windows laid over 10 mm th. Cement mortar 1:3 & joint with colour cement slurry with mathcing pigment incl. rubbing & polishing incl. rounding the edges etc. comp. as directed. | Smt | 1340 | 100 | 0 | 378.455 | 0 | 278.455 | 0 |  | 134000 | 0 | 507129.7 | 0 | 373129.7 | 0 |  | 0 | 0 | 0%
59 | Providing and laying china mosaic type water proofing treatment on terrace incl. (a) applying neat cement slurry 2.75 kg/ sqm. of cement admixed with water proofing compound after cleaning the surface (b) laying cement concrete using brick bats 25 to 100 mm size with 50 % of C.M. 1:5 (1 cement : 5 coarse sand) admised with water proofing compound over 20 mm thick layer of C.M. 1.5 to required slope including rounding of junctions of walls and slab (c) After two days of proper curing, a second coat of cement slurry (d) & laying white glazed china mozaic flooring using of first quality white glazed tiles (should not less than 6 mm thick) of proper gradient over 20 mm th. cement mortar (1:1) floor bedding with neat cement slurry incl. jointing with white cement incl. watering, curing (e) After finishing the whole terrace shall be flooded with water for a period of two weeks, Stamp paper guarantee of 10 years to be furnished before receiving any payment from the cilent. (Only surface area should be measure for payment) |  |  |  | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| P/L Inida type Water proofing | Smt | 800 | 850 | 0 | 812.3686 | 0 | 0 | 37.6314 |  | 680000 | 0 | 649894.88 | 0 | 0 | 30105.12 |  | 0 | 0 | 0%
60 | Providing & fixing 35mm.th. Flush Door Solid Double Core type Both Face water proof Commarcial/Marin Ply & 1.5 mm th.laminate shall be pasted on both side with adhesives as specified by the manufacturers. The laminate shall be as per approved shade & texture, of make incl. Sal wood frames of finished size 12cm x 7cm.incl. S.S. Hinges ,S.S. Handle,Aldrop,Tower Bolt with nessary screws & Anodized aluminum fixtures & fastenings as per Drawing, Approve by Architect/EIC. For all Floor | Smt | 5125 | 201.6 | 0 | 224.28 | 0 | 22.68 | 0 |  | 1033200 | 0 | 1149435 | 0 | 116235 | 0 |  | 0 | 0 | 0%
61 | Providing & fixing M.S. Pipe railing of 50mm dia pipe not less than 18guage, in 3 rows supported by M.S. Pipe of 50mm dia at every corners & 1.5 mt C/C incl. concrete block incl. 16 guage M.S. sheet using required cutting, jointing, welding, threading, drilling & fixing etc. comp. as directed.(For Staircase) | Rmt | 1550 | 55 | 0 | 41.58 | 0 | 0 | 13.42 |  | 85250 | 0 | 64449 | 0 | 0 | 20801 |  | 0 | 0 | 0%
62 | Providing, fixing and construction of sand witch type platform of 18 mm thick Granite polished stone top, 100 mm wide edge moulded Facia Patti with 25mm thick prepolished Kota stone of uniform size and colour for bottom & supports at 75 cm interval including necessary cement mortar 1:2 Kota shall be fixed in cement joints and pointing as specified in Kitchen / Pantry / Counter / Laboratory etc with necessary making of edges, polishing curing daily mopping with water and kerosene etc comp as directed of Engineer-in-charge. (Measured only vision finished top plan area) | Smt | 3450 | 160 | 0 | 90 | 0 | 0 | 70 |  | 552000 | 0 | 310500 | 0 | 0 | 241500 |  | 0 | 0 | 0%
[13 empty] | 0 | 0
| Extra Items : | [11 empty] | 0 | 0
1 | Providing and applying anti-termite treatment by chemical emulsion (Chlorpyrifos 20% EC @ 1% concentration / Imidacloprid 30.5% SC @ 0.05%) as per IS:6313 (Part II) to bottom and sides of foundation trenches, plinth fillings, sunken floor slabs, and other vulnerable areas, at the rate of 5 to 7.5 litres/sqm, complete with materials, labour, tools, safety measures, and as directed by Engineer-in-Charge. | Sqm | 60 | 0 | 748.051 |  |  | 0 | 748.051 |  | 0 | 44883.06 | 0 | 0 | 0 | 44883.06 |  | 0 |  | 0%
2 | Providing and filling in sunken floor areas with clean river sand conforming to IS:383, in layers not exceeding 200 mm, each layer well-watered, rammed and compacted, surface dressed and finished to required slopes and levels, including cost of materials, transportation, labour, royalties, taxes, and all leads & lifts complete as per specifications and direction of Engineer-in-Charge. | Cum | 1100 | 0 | 81.174 |  |  | 0 | 81.174 |  | 0 | 89291.4 | 0 | 0 | 0 | 89291.4 |  | 0 |  | 0%
3 | Fabricating, supplying, and fixing MS duct grills of approved design, made from MS angle/flat sections as per IS:2062, including cutting, welding, grinding, drilling, anchoring with holdfasts, alignment, and proper fixing, surface cleaned and painted with one coat of red oxide zinc chromate primer (IS:2074) and two coats of synthetic enamel paint (IS:2932) of approved shade, complete in all respects as per drawing, specifications, and direction of Engineer-in-Charge. | MT | 110000 | 0 | 6.51 |  |  | 0 | 6.51 |  | 0 | 716100 | 0 | 0 | 0 | 716100 |  | 0 |  | 0%
4 | Supply, fabrication and fixing of factory-made Solid PVC/uPVC single-leaf door with 45 mm thick multi-chamber uPVC shutter, uPVC frame (50×70 mm) with GI/MS reinforcement and EPDM seals, shutter reinforced with GI inserts, fitted with stainless steel hardware (3 hinges, 1 mortise lock with handle set, 1 tower bolt), all joints sealed with silicone, laminated/plain finish with protective film, including all materials, labour, installation, alignment and handover as per manufacturer’s specification. | Smt | 3200 |  | 232 |  |  | 0 | 232 |  | 0 | 742400 | 0 | 0 | 0 | 742400 |  | 0 |  | 0%
| Total Amount | [9 empty] | 57673792.2965 | 1592674.46 | 51313216.0187 | 23555570.3 | 5521220.1684 | 13474470.9062 | 0 |  |  |  |  | 15293077.2 | 15293077.2 | 0 | 23555570.3 | 0.64923 | Cost Overrun | -452229.9035 | 1717048.5348 | 0 | 14840847.2965 | 0 | -2169278.4383 | 1717048.5348 | 0
[6 empty] | 10 | 14.652 | 4.884 | 23.976
[6 empty] | 31.28 | 10 | 6 | 13.2
[6 empty] | 41.28 | 24.652 | 10.884 | 37.176
[6 empty] | 3302.4 | 1972.16 | 870.72 | 371.76

## STEEL RATE DIFFRENCE
Sr.No | Description | Vendor Name | Purchase No | Steel Purchase Details
|  |  |  | Dia Of Bar | Qty. | Basic Rate | Purchase Rate | Basic Rate Amount | Purchase Rate Amount | Excess Amount | Saving Amount
1 | TMT Bars Fe500 | Vasupujya Enterprise | 1st Purchase | 8 | 4.02 | 53000 | 46593.22 | 213060 | 187304.7444 | 0 | 25755.2556
2 |  |  |  | 10 | 4.02 | 53000 | 45067.8 | 213060 | 181172.556 | 0 | 31887.444
3 |  |  |  | 12 | 3.02 | 53000 | 44050.85 | 160060 | 133033.567 | 0 | 27026.433
4 |  |  |  | 16 | 1.93 | 53000 | 44050.85 | 102290 | 85018.1405 | 0 | 17271.8595
5 |  |  |  | 20 | 11.05 | 53000 | 44050.85 | 585650 | 486761.8925 | 0 | 98888.1075
6 | TMT Bars Fe500 | Steel Solution | 2nd Purchase | 8 | 1.01 | 53000 | 47203 | 53530 | 47675.03 | 0 | 5854.97
7 |  |  |  | 10 | 1.9 | 53000 | 45678 | 100700 | 86788.2 | 0 | 13911.8
8 |  |  |  | 12 | 1.97 | 53000 | 44661 | 104410 | 87982.17 | 0 | 16427.83
9 |  |  |  | 16 | 5.02 | 53000 | 44661 | 266060 | 224198.22 | 0 | 41861.78
10 | TMT Bars Fe550 | Vasupujya Enterprise | 3rd Purchase | 8 | 3.63 | 53000 | 46560 | 192390 | 169012.8 | 0 | 23377.2
11 |  |  |  | 10 | 1.07 | 53000 | 45030 | 56710 | 48182.1 | 0 | 8527.9
12 |  |  |  | 12 | 4.51 | 53000 | 44020 | 239030 | 198530.2 | 0 | 40499.8
13 |  |  |  | 16 | 3.44 | 53000 | 44020 | 182320 | 151428.8 | 0 | 30891.2
10 | TMT Bars Fe550 | Steel House | 4th Purchase | 8 | 2.5 | 53000 | 46272 | 132500 | 115680 | 0 | 16820
11 |  |  |  | 10 | 0.52 | 53000 | 44916 | 27560 | 23356.32 | 0 | 4203.68
12 |  |  |  | 16 | 5.21 | 53000 | 44068 | 276130 | 229594.28 | 0 | 46535.72
13 |  |  |  | 20 | 4.93 | 53000 | 44068 | 261290 | 217255.24 | 0 | 44034.76
14 | TMT Bars Fe550 | Steel House | 5th Purchase | 8 | 12.09 | 53000 | 45423 | 640770 | 549164.07 | 0 | 91605.93
15 |  |  |  | 10 | 0.22 | 53000 | 44237 | 11660 | 9732.14 | 0 | 1927.86
16 |  |  |  | 12 | 3.65 | 53000 | 43390 | 193450 | 158373.5 | 0 | 35076.5
17 |  |  |  | 16 | 5.81 | 53000 | 43390 | 307930 | 252095.9 | 0 | 55834.1
18 |  |  |  | 20 | 7.02 | 53000 | 43220 | 372060 | 303404.4 | 0 | 68655.6
14 | TMT Bars Fe550 | Vasupujya Enterprise | 6th Purchase | 8 | 12.86 | 53000 | 44070 | 681580 | 566740.2 | 0 | 114839.8
15 |  |  |  | 10 | 1 | 53000 | 42880 | 53000 | 42880 | 0 | 10120
16 |  |  |  | 12 | 3.52 | 53000 | 42030 | 186560 | 147945.6 | 0 | 38614.4
17 |  |  |  | 16 | 6.21 | 53000 | 42030 | 329130 | 261006.3 | 0 | 68123.7
18 |  |  |  | 20 | 6.75 | 53000 | 41700 | 357750 | 281475 | 0 | 76275
19 | TMT Bars Fe550 | Steel House | 7th Purchase | 8 | 16.16 | 53000 | 44830 | 856480 | 724452.8 | 0 | 132027.2
20 |  |  |  | 10 | 0.95 | 53000 | 43640 | 50350 | 41458 | 0 | 8892
21 |  |  |  | 12 | 4.61 | 53000 | 42800 | 244330 | 197308 | 0 | 47022
22 |  |  |  | 16 | 7.74 | 53000 | 42800 | 410220 | 331272 | 0 | 78948
23 |  |  |  | 20 | 2.78 | 53000 | 42460 | 147340 | 118038.8 | 0 | 29301.2
24 | TMT Bars Fe550 | Vasupujya Enterprise | 8th Purchase | 8 | 10.51 | 53000 | 46440 | 557030 | 488084.4 | 0 | 68945.6
25 |  |  |  | 10 | 0.51 | 53000 | 45250 | 27030 | 23077.5 | 0 | 3952.5
26 |  |  |  | 12 | 3.96 | 53000 | 44410 | 209880 | 175863.6 | 0 | 34016.4
27 |  |  |  | 16 | 6.83 | 53000 | 44410 | 361990 | 303320.3 | 0 | 58669.7
Total : - |  |  |  |  | 172.93 |  |  | 9165290 | 7648666.7704 | 0 | 1516623.2296 | 15.1662
Total Saving | 1516623.2296

## CEMENT RATE DIFFRENCE
Sr.No | Description | Vendor Name |  | Cement Purchase Details
|  |  | Purchase No | Qty. | Basic Rate | Purchase Rate | Basic Rate Amount | Purchase Rate Amount | Excess Amount | Saving Amount
1 | Cement Bags | UltraTech Cement Limited | 1st Purchase | 600 | 280 | 269.5315 | 168000 | 161718.9 | 0 | 6281.1
2 | Cement Bags | UltraTech Cement Limited | 1st Purchase | 600 | 280 | 265.625 | 168000 | 159375 | 0 | 8625
3 | Cement Bags | UltraTech Cement Limited | 2nd Purchase | 700 | 280 | 253.9065 | 196000 | 177734.55 | 0 | 18265.45
4 | Cement Bags | UltraTech Cement Limited | 3rd Purchase | 700 | 280 | 241.5255 | 196000 | 169067.85 | 0 | 26932.15
5 | Cement Bags | UltraTech Cement Limited | 3rd Purchase | 700 | 280 | 237.288 | 196000 | 166101.6 | 0 | 29898.4
6 | Cement Bags | UltraTech Cement Limited | 4th Purchase | 600 | 280 | 233.051 | 168000 | 139830.6 | 0 | 28169.4
7 | Cement Bags | UltraTech Cement Limited | 4th Purchase | 600 | 280 | 228.8135 | 168000 | 137288.1 | 0 | 30711.9
Total : - |  |  |  | 4500 |  |  | 1260000 | 1111116.6 | 0 | 148883.4 | 1.4888