## 00_READ_ME
RFI - REQUEST FOR INFORMATION ¦ FORM, REGISTER & DASHBOARD
Sharnam Project Development Consultants & Co. (SPDC), Vadodara
A. WHAT THIS IS
Scope | The design query trail: a contractor or site engineer asks a question about a drawing or specification, a consultant answers it, and SPDC certifies the answer released the work front. Not the same as a Request for Inspection, which is the separate site QA form.
Structure | One register, one printable form and one dashboard. The form is a view of the register, not a separate document - pick an RFI number on 03_RFI_FORM and the whole sheet fills from the register row.
B. SHEETS
01_CONTROL | Project particulars, form number, priority-to-response-days table, all pick-lists, and the house rules.
03_RFI_FORM | One-page A4 printable RFI. Choose the number in the yellow cell at the top. Print it, get it signed, file it against the number.
04_RFI_REGISTER | One row per RFI, 33 columns. Reply-required date, days taken, SLA status and age bucket are all computed.
05_DASHBOARD | Headline counts, ageing, and breakdowns by discipline and by responsible party.
C. THE SIX FIELDS THAT MAKE AN RFI REGISTER WORK
1. Drawing ref AND revision | Roughly half of all discrepancy RFIs turn out to be someone working from a superseded sheet. Recording the revision settles that in one line instead of a meeting.
2. Contractor's proposed solution | The party at the workface usually knows the practical answer. Requiring a proposal converts the RFI from a question into something the consultant can approve or amend, which is far faster. An RFI without one is returned.
3. Priority set by the PMC | Not by the originator - otherwise everything arrives marked CRITICAL. Priority drives the response days, which drives the reply-required date, which drives the overdue flag.
4. Responsible party | The single most useful column in the file. It is what turns a list of open queries into an accountable one, and it is what section D of the dashboard reports on.
5. Date responded, separate from date closed | Answered means the consultant replied. Closed means SPDC verified the reply is workable and released the front. Collapsing the two hides SPDC's own backlog.
6. Change / VO reference | An RFI is not a variation. When a response changes scope, raise a change notice and cross-reference it here. A priced change buried inside an RFI response is a dispute waiting to happen.
D. HOW THE SLA CLOCK WORKS
Reply required by | Date raised plus the response days for the priority - CRITICAL 3, HIGH 7, NORMAL 14, LOW 21. Adjust the table on 01_CONTROL to match the contract if it specifies its own periods.
SLA status column | While unanswered it counts down, then flips to OVERDUE with the number of days. Once answered it records whether the reply landed on time or late - which is the record you need if delay is ever argued.
A caution | The clock in this file runs from the date raised. Most contracts run it from the date received by the consultant. If the two differ materially on your project, add a received-date column before the first dispute, not after.
E. BEFORE FIRST USE
Delete the samples | Eight worked examples are loaded in peach. They are drawn from the shed project and show a closed RFI, one answered late, one awaiting close-out, and one with cost and time impact claimed.
Confirm the response periods | The 3 / 7 / 14 / 21 day table is an SPDC standard, not a contract term. Check the contract's information-release clause and align it.
Fix the numbering | SPDC-RFI-nnn, sequential, never reused, never renumbered. Superseded queries are marked Void with a reason and a fresh number is raised.

## 01_CONTROL
RFI CONTROL, MASTERS & RESPONSE STANDARDS
Project particulars, numbering, priority response times and the pick-lists that drive the register. Blue cells are inputs.
1. PROJECT PARTICULARS (these print on every RFI form)
PROJECT | Industrial Shed 50,000 sqft, Package-1 Civil & Package-2 PEB
EMPLOYER | Enter employer / client name
CONTRACT_NO | Enter contract / work order no
PMC | Sharnam Project Development Consultants & Co., Vadodara
FORM_NO | SPDC/QMS/F-RFI-01 | SPDC form number printed on the RFI
FORM_REV | R0
RFI_PREFIX | SPDC-RFI | Numbering: PREFIX-nnn, sequential, never reused
2. PRIORITY & RESPONSE TIME (the contractual clock this register runs on)
PRIORITY | RESPONSE DAYS | WHEN TO USE
CRITICAL | 3 | Work is stopped at the front, or a pour / erection sequence cannot proceed without the answer
HIGH | 7 | Work starts within two weeks and cannot be sequenced around the query
NORMAL | 14 | Standard design clarification with float in the programme
LOW | 21 | Future work fronts, finishes selections, non-critical detail
3. PICK-LISTS
DISCIPLINE | CATEGORY | RESPONSIBLE | STATUS
Architectural | Drawing discrepancy | Architect | Open
Structural | Missing information | Structural Consultant | Under review
Civil | Design clarification | MEP Consultant | Answered
PEB | Specification conflict | PEB Vendor | Closed
Electrical | Site constraint | PMC (SPDC) | Void / withdrawn
Plumbing | Material substitution | Employer
Firefighting | Statutory requirement | Statutory Authority
HVAC | Interface / coordination
External Infra
General
4. HOUSE RULES - APPLY THESE OR THE REGISTER STOPS BEING USEFUL
- | One question per RFI. Bundled queries get partially answered and then sit open forever.
- | An RFI without the contractor's proposed solution is returned unanswered. The party at the workface usually knows the practical answer.
- | The response clock starts on the date received by the consultant, not the date the contractor wrote it.
- | An RFI is not a variation. If the answer changes scope, raise a change notice and cross-reference it - never let a priced change hide inside an RFI response.
- | Priority is set by the PMC, not by the originator. Everything arrives marked CRITICAL otherwise.
- | Close-out is a separate act from answering. Answered means the consultant replied; Closed means the reply was adequate and the work front is released.
- | Never reuse or renumber an RFI. Superseded queries are marked Void with the reason, and a new number is raised.
- | Every RFI that touches a drawing must name the drawing number AND its revision - half of all discrepancy RFIs are someone working from a superseded sheet.

## 03_RFI_FORM
SHARNAM PROJECT DEVELOPMENT CONSULTANTS & CO.
REQUEST FOR INFORMATION (RFI)
Form No: SPDC/QMS/F-RFI-01 |  |  | Form Rev: R0
SELECT RFI NO | SPDC-RFI-001 | Pick a number - every field below fills from the register
1. PROJECT PARTICULARS
Project | Industrial Shed 50,000 sqft, Package-1 Civil & Package-2 PEB
Employer / Client | Enter employer / client name | Contract No |  | Enter contract / work order no
Project Management | Sharnam Project Development Consultants & Co., Vadodara | Package |  | P1-CIVIL
2. RFI PARTICULARS
RFI No | SPDC-RFI-001 | Revision |  | 0
Date raised | 2026-06-02 | Priority |  | CRITICAL
Reply required by | 2026-06-05 | Response time (days) |  | 3
Originator | Contractor QS | Discipline |  | Structural
Category | Drawing discrepancy | Responsible party |  | Structural Consultant
Subject | Pile cap PC-F1 top level differs between foundation layout and section
Location / grid / level | Zone-1, Grid B/3
Drawing ref | 2601-F-101 | Drawing rev |  | R2
Specification clause | Cl. 5.2
3. QUERY RAISED
Foundation layout 2601-F-101 R2 shows pile cap top at -1.200 m from FFL. Section A-A on 2601-F-105 R1 shows -1.350 m for the same cap. Which level governs?
4. SOLUTION PROPOSED BY ORIGINATOR (an RFI without this is returned unanswered)
Adopt -1.350 m as per the section, since it maintains the 75 mm cover over the pile projection shown on the pile schedule.
5. IMPACT CLAIMED BY ORIGINATOR
Cost impact claimed | No | Estimated amount (INR) |  | 0
Time impact claimed | No | Estimated delay (days) |  | 0
A claimed impact does not create an entitlement. If the response changes scope, a change notice is raised separately and cross-referenced below.
6. RESPONSE
Section A-A governs. Cap top level is -1.350 m from FFL. Layout drawing to be revised to R3.
Responded by | S. Mehta | Date of response |  | 2026-06-04
7. PMC REVIEW & CLOSE-OUT
Status | Closed | Date closed |  | 2026-06-05
Days taken | 2 | SLA status |  | Answered on time
Change / VO reference | 0 | Attachments |  | Mark-up sketch
PMC remarks | Layout reissued R3 on 08-Jun
8. SIGNATURES
Raised by (Contractor) | Reviewed by (SPDC PMC) | Responded by (Consultant) |  | Accepted & closed by (SPDC PMC)
Name Signature Date | Name Signature Date | Name Signature Date |  | Name Signature Date
Distribution: Contractor / Design Consultant / Employer's Representative / SPDC Document Control. This form is a controlled record - file the signed copy against the RFI number in the project document register.

## 04_RFI_REGISTER
RFI REGISTER
One row per RFI. Ageing, SLA status and bucket columns are computed - do not type into them.
RFI NO | REV | PACKAGE | DISCIPLINE | CATEGORY | SUBJECT | LOCATION / GRID | DWG REF | DWG REV | SPEC CLAUSE | QUERY RAISED | CONTRACTOR'S PROPOSED SOLUTION | ORIGINATOR | DATE RAISED | PRIORITY | SLA DAYS | REPLY REQUIRED BY | RESPONSIBLE PARTY | DATE RESPONDED | RESPONSE | RESPONDED BY | STATUS | DATE CLOSED | DAYS TAKEN | SLA STATUS | AGE BUCKET | COST IMPACT | EST. COST (INR) | TIME IMPACT | EST. DELAY (d) | CHANGE / VO REF | ATTACHMENTS | PMC REMARKS
SPDC-RFI-001 | 0 | P1-CIVIL | Structural | Drawing discrepancy | Pile cap PC-F1 top level differs between foundation layout and section | Zone-1, Grid B/3 | 2601-F-101 | R2 | Cl. 5.2 | Foundation layout 2601-F-101 R2 shows pile cap top at -1.200 m from FFL. Section A-A on 2601-F-105 R1 shows -1.350 m for the same cap. Which level governs? | Adopt -1.350 m as per the section, since it maintains the 75 mm cover over the pile projection shown on the pile schedule. | Contractor QS | 2026-06-02 | CRITICAL | 3 | 2026-06-05 | Structural Consultant | 2026-06-04 | Section A-A governs. Cap top level is -1.350 m from FFL. Layout drawing to be revised to R3. | S. Mehta | Closed | 2026-06-05 | 2 | Answered on time |  | No | 0 | No | 0 |  | Mark-up sketch | Layout reissued R3 on 08-Jun
SPDC-RFI-002 | 0 | P1-CIVIL | Structural | Missing information | Anchor bolt template dimensions not shown for pedestal type PED-C2 | Zone-2, Grid F/12 | 2601-F-102 | R1 | - | Pedestal schedule gives bolt circle for PED-C1 only. PED-C2 carries a different base plate per PEB GA. Template dimensions required before pedestal shuttering. | Issue template dimensions from the PEB vendor's base plate drawing BP-04. | Site Engineer | 2026-06-15 | CRITICAL | 3 | 2026-06-18 | PEB Vendor | 2026-06-19 | Template dimensions issued vide BP-04 R1. Bolt circle 450 mm, 4 nos M30 x 750, projection 90 mm. | PEB Design Cell | Closed | 2026-06-22 | 4 | Answered late |  | No | 0 | Yes | 2 |  | BP-04 R1 | Two-day delay to Zone-2 pedestals absorbed in float
SPDC-RFI-003 | 0 | P1-CIVIL | Civil | Design clarification | Saw-cut joint layout for industrial flooring not issued | Zone-1 & 2, full floor | 2601-C-210 | R0 | Cl. 9.4 | Flooring drawing shows 150 mm VDF but no joint layout. Panel size, joint depth and dowel details required to plan the pour sequence. | Adopt 4.5 m x 4.5 m panels with saw-cut to one-fourth depth and 12 mm dowels at construction joints. | Contractor QS | 2026-07-06 | HIGH | 7 | 2026-07-13 | Structural Consultant |  |  |  | Under review |  | 44 | OVERDUE 37 d | over 30 d | No | 0 | No | 0 |  | Proposed layout sketch | Chased twice; the flooring pour front is now waiting on this
SPDC-RFI-004 | 0 | P1-CIVIL | Architectural | Specification conflict | Toilet dado tile height - BOQ says full height, drawing shows 1200 mm | Toilet block, GF | 2601-A-140 | R1 | Cl. 12.3 | BOQ item 12.03 reads full height glazed dado. Drawing 2601-A-140 R1 shows dado to 1200 mm only. Confirm which applies for measurement and ordering. | Adopt full height as per BOQ, since tile ordering is already based on the BOQ quantity. | Contractor QS | 2026-07-12 | NORMAL | 14 | 2026-07-26 | Architect | 2026-07-20 | Full height dado applies. Drawing to be corrected at next revision. No change in BOQ quantity. | R. Desai | Closed | 2026-07-22 | 8 | Answered on time |  | No | 0 | No | 0
SPDC-RFI-005 | 0 | P2-PEB | PEB | Interface / coordination | Base plate shim pack thickness where pedestal top is 8 mm low | Zone-1, Grid C/5 | BP-02 | R1 | - | Joint anchor bolt survey records pedestal top 8 mm below design at three locations. Confirm permissible shim pack and whether grouting detail changes. | Provide 8 mm MS shim pack in two plates under base plate and increase GP2 grout thickness accordingly. | Site Engineer | 2026-07-18 | HIGH | 7 | 2026-07-25 | PEB Vendor | 2026-07-27 | Shim pack acceptable up to 10 mm total in maximum two plates, plates to be 100 x 100 minimum. Grout thickness to suit. Torque unchanged. | PEB Design Cell | Answered |  | 9 | Answered late |  | No | 0 | No | 0 |  | Survey record | Awaiting PMC close-out after site verification
SPDC-RFI-006 | 0 | P1-CIVIL | Civil | Site constraint | Storm water drain invert clashes with existing GIDC line at chainage 180 | External, Ch. 180 | 2601-C-310 | R0 | - | Existing 450 mm GIDC line encountered at 1.1 m depth, clashing with the proposed drain invert of 1.35 m. Realignment or level change required. | Lower the drain locally to 1.6 m and provide a crossing chamber, or divert 6 m north of the existing line. | Site Engineer | 2026-08-04 | HIGH | 7 | 2026-08-11 | PMC (SPDC) |  |  |  | Open |  | 15 | OVERDUE 8 d | 15-30 d | Yes | 185000 | Yes | 5 | CN-07 raised | Survey of existing line | Cost and time impact claimed - to be assessed under CN-07
SPDC-RFI-007 | 0 | P1-CIVIL | Architectural | Material substitution | Alternative make proposed for two-hour fire rated doors | Toilet & office block | 2601-A-152 | R0 | Cl. 14.2 | Specified make has a 12-week lead time against a required date of 20-Sep. Alternative make offered with equivalent two-hour certification. | Approve the alternative make against submitted test certificate and CBRI listing, at no change in rate. | Contractor QS | 2026-08-10 | NORMAL | 14 | 2026-08-24 | Architect |  |  |  | Open |  | 9 | 5 d left | 8-14 d | No | 0 | Yes | 0 |  | Test certificate | Lead time is the real issue - escalate in writing this week
SPDC-RFI-008 | 0 | P1-CIVIL | Structural | Design clarification | Lap position permitted in grade beam bottom bars | Zone-1, GB-01 | 2601-F-103 | R1 | Cl. 5.8 | Grade beam length 6.0 m exceeds a single 12 m bar only in continuous runs. Confirm permitted lap zones for bottom reinforcement. | Lap bottom bars within the middle third of the span, staggered by 600 mm, as per general notes. | Contractor QS | 2026-08-14 | NORMAL | 14 | 2026-08-28 | Structural Consultant |  |  |  | Open |  | 5 | 9 d left | 0-7 d | No | 0 | No | 0 |  |  | Affects RA-03 lap certification
Formulas:
REPLY REQUIRED BY = IF([RFI NO]="","",IF([DATE RAISED]="","",[DATE RAISED]+[SLA DAYS]))
DAYS TAKEN = IF([RFI NO]="","",IF([DATE RAISED]="","",IF([DATE RESPONDED]="",TODAY()-[DATE RAISED],[DATE RESPONDED]-[DATE RAISED])))

## 05_DASHBOARD
RFI DASHBOARD
Live from the register. Read this before every design coordination meeting.
A. HEADLINE
Total RFIs raised |  |  | 8
Awaiting response (no reply yet) |  |  | 4
OVERDUE against SLA |  |  | 2
Answered but not yet closed |  |  | 1
Closed |  |  | 3
Average days to respond (answered only) |  |  | 5.8
RFIs with cost impact claimed |  |  | 1
Value of cost impact claimed (INR) |  |  | 185000
RFIs with time impact claimed |  |  | 3
B. AGEING OF RFIs AWAITING RESPONSE
AGE BUCKET | COUNT | COMMENT
0-7 d | 1 | Within normal turnaround
8-14 d | 1 | Chase the consultant
15-30 d | 1 | Escalate at the weekly design meeting
over 30 d | 1 | Escalate in writing - this is a programme risk, not a paperwork issue
C. BY DISCIPLINE
DISCIPLINE | RAISED | AWAITING RESPONSE | OVERDUE | CLOSED
Architectural | 2 | 1 | 0 | 1
Structural | 3 | 1 | 0 | 2
Civil | 2 | 2 | 2 | 0
PEB | 1 | 0 | 0 | 0
Electrical | 0 | 0 | 0 | 0
Plumbing | 0 | 0 | 0 | 0
Firefighting | 0 | 0 | 0 | 0
HVAC | 0 | 0 | 0 | 0
External Infra | 0 | 0 | 0 | 0
General | 0 | 0 | 0 | 0
D. BY RESPONSIBLE PARTY - who is holding the project up
RESPONSIBLE PARTY | RAISED | AWAITING RESPONSE | OVERDUE | AVG DAYS TO RESPOND
Architect | 2 | 1 | 0 | 8
Structural Consultant | 3 | 2 | 1 | 2
MEP Consultant | 0 | 0 | 0 | -
PEB Vendor | 2 | 0 | 0 | 6.5
PMC (SPDC) | 1 | 1 | 1 | -
Employer | 0 | 0 | 0 | -
Statutory Authority | 0 | 0 | 0 | -
E. WHAT TO DO WITH THIS SHEET
- | Section D is the one that changes behaviour. Bring it to the design coordination meeting as it stands - a consultant with four overdue RFIs argues differently when the number is on the screen.
- | Anything in the over-30-day bucket goes into the monthly report as a programme risk with the affected activity named, not into a list of open items.
- | An RFI marked Answered but not Closed means SPDC has not yet verified the reply is workable. That is SPDC's own backlog - clear it before chasing anyone else.
- | Cost and time impacts here are claimed, not agreed. Reconcile the claimed column against the change notices actually raised, monthly.