## PEB Supply Material
VIATRIX ENGINEERING & PLASTIC LLP, BAMANGAM
PEB SUPPLY MATERIAL
Sr. No. | Recieved Date | Description of Goods | Vecicle No. | Tax Invoice No. | Invoice Date | Challan No. | Vehical Weight as per Viatrix |  |  | Vehical Weight as per Sankalp |  | Wooden Weight (Kg) | Total Invoice value with GST | Total Invoice value without GST | Recoveries ( 20% Advance Agains GA Drawing ) | Advance ( 10 % Advance Along with LOA ) | Recoveries 5 %(after erection of primary steel, secondary steel, alignment and bolt-tightening of structure and before starting the roof /side sheeting work.l.) | Recoveries(5 % against erection of roof sheeting) | Retentions (5%) | Net Amount Payable Against This Bill With Advanced Amount
[7 empty] | Gross | Tare | Net
1 | 2025-08-18 | 10% OF Advance Along with LOA |  | SPSPL/PRO/25-26/26 | 2025-08-18 | [8 empty] | 3890000
2 | 2025-10-30 | 20% Advance against the approval of the GA design. |  | SPSPL/PRO/25-26/40 | 2025-10-30 | [8 empty] | 7780000
1 | 29.09.2025 | PEB Material | GJ06XX1811 | 8822500205 | 29.09.2025 | 9992308660 |  |  | 3380 | 3380 | 0 | 0 | 529919.6 | 449084.4068 | 89816.8814 | 44908.4407 | 22454.2203 | 22454.2203 | 22454.2203 | 327831.6169
2 | 12.12.2025 | PEB Material | GJ06AX4577 | 8822500433 | 11.12.2025 | 9992309199 | 25480 | 16640 | 8840 | 9000 | 160 | 300 | 897453.72 | 760554 | 152110.8 | 76055.4 | 38027.7 | 38027.7 | 38027.7 | 555204.42
3 | 12.12.2025 | PEB Material | GJ05BT3193 | 8822500432 | 11.12.2025 | 9992309198 | 30460 | 12990 | 17470 | 17410 | -60 | 510 | 1702819.32 | 1443067.2203 | 288613.4441 | 144306.722 | 72153.361 | 72153.361 | 72153.361 | 1053439.0708
4 | 12.12.2025 | PEB Material | GJ01ET5958 | 8822500431 | 11.12.2025 | 9992309195 | 29400 | 12990 | 16410 | 16380 | -30 | 400 | 1704053.38 | 1444113.0339 | 288822.6068 | 144411.3034 | 72205.6517 | 72205.6517 | 72205.6517 | 1054202.5147
|  |  |  | 8822500430 | 12.11.2025 | 9992309194 |  |  |  |  | 0 |  | 920.4 | 780 | 156 | 78 | 39 | 39 | 39 | 569.4
5 | 24.12.2025 | PEB Material | GJ16AU6360 | 8822500483 | 24.12.2025 | 9992309318 | 12720 | 4810 | 7910 | 7890 | -20 |  | 810222.1 | 686628.8983 | 137325.7797 | 68662.8898 | 34331.4449 | 34331.4449 | 34331.4449 | 501239.0958
6 | 24.12.2025 | PEB Material | GJ06AX9288 | 8822500488 | 24.12.2025 | 9992309329 | 19780 | 11280 | 8500 | 8420 | -80 | 200 | 862503.3 | 730935 | 146187 | 73093.5 | 36546.75 | 36546.75 | 36546.75 | 533582.55
7 | 25.12.2025 | PEB Material | GJ06AV3379 | 8822500489 | 24.12.2025 | 9992309331 | 26640 | 12670 | 13970 | 13910 | -60 | 500 | 1436709.68 | 1217550.5763 | 243510.1153 | 121755.0576 | 60877.5288 | 60877.5288 | 60877.5288 | 888811.9207
8 | 25.12.2025 | PEB Material | GJ16V6687 | 8822500485 | 24.12.2025 | 9992309320 | 21410 | 11230 | 10180 | 10140 | -40 | 400 | 1016312.76 | 861282 | 172256.4 | 86128.2 | 43064.1 | 43064.1 | 43064.1 | 628735.86
9 | 26.12.2025 | PEB Material | GJ06AV7978 | 8822500496 | 25.12.2025 | 9992309345 | 20890 | 12610 | 8280 | 8210 | -70 | 210 | 844619.22 | 715779 | 143155.8 | 71577.9 | 35788.95 | 35788.95 | 35788.95 | 522518.67
10 | 26.12.2025 | PEB Material | GJ01ET5958 | 8822500495 | 25.12.2025 | 9992309344 | 21420 | 12990 | 8430 | 8410 | -20 | 280 | 834084.18 | 706851 | 141370.2 | 70685.1 | 35342.55 | 35342.55 | 35342.55 | 516001.23
11 | 27.12.2025 | PEB Material | GJ06AV3379 | 8822500501 | 26.12.2025 | 9992309353 | 20990 | 12770 | 8220 | 8200 | -20 | 280 | 828285.66 | 701937 | 140387.4 | 70193.7 | 35096.85 | 35096.85 | 35096.85 | 512414.01
12 | 27.12.2025 | PEB Material | GJ06AV6862 | 8822500503 | 26.12.2025 | 9992309363 | 26910 | 12500 | 14410 | 14300 | -110 | 500 | 1425724.38 | 1208241 | 241648.2 | 120824.1 | 60412.05 | 60412.05 | 60412.05 | 882015.93
13 | 30.12.2025 | PEB Material | RJ27GC1327 | 8822500510 | 29.12.2025 | 9992309385 | 21060 | 12870 | 8190 | 8290 | 100 | 225 | 844258.14 | 715473 | 143094.6 | 71547.3 | 35773.65 | 35773.65 | 35773.65 | 522295.29
14 | 30.12.2025 | PEB Material | GJ12AT7474 | 8822500512 | 29.12.2025 | 9992309388 | 25530 | 11930 | 13600 | 13510 | -90 | 220 | 1426799.14 | 1209151.8136 | 241830.3627 | 120915.1814 | 60457.5907 | 60457.5907 | 60457.5907 | 882680.8239
15 | 30.12.2025 | PEB Material | RJ14GG8825 | 8822500509 | 29.12.2025 | 9992309380 | 24640 | 12040 | 12600 | 12570 | -30 | 800 | 1188006.3 | 1006785 | 201357 | 100678.5 | 50339.25 | 50339.25 | 50339.25 | 734953.05
16 | 31.12.2025 | PEB Material | GJ01ET5958 | 8822500520 | 30.12.2025 | 9992309404 | 28650 | 13020 | 15630 | 15580 | -50 | 450 | 1598328.06 | 1354515.3051 | 270903.061 | 135451.5305 | 67725.7653 | 67725.7653 | 67725.7653 | 988796.1727
17 | 31.12.2025 | PEB Material | GJ27TD9148 | 8822500514 | 30.12.2025 | 9992309391 | 27520 | 13360 | 14160 | 14110 | -50 | 525 | 1379017.62 | 1168659 | 233731.8 | 116865.9 | 58432.95 | 58432.95 | 58432.95 | 853121.07
18 | 31.12.2025 | PEB Material | GJ27V8125 | 8822500515 | 30.12.2025 | 9992309394 | 32190 | 13190 | 19000 | 18870 | -130 | 450 | 1914540.64 | 1622492.0678 | 324498.4136 | 162249.2068 | 81124.6034 | 81124.6034 | 81124.6034 | 1184419.2095
19 | 01.01.2026 | PEB Material | GJ16AV3034 | 8822500528 | 31.12.2025 | 9992309411 | 12990 | 4630 | 8360 | 7680 | -680 | 150 | 759858.86 | 643948.1864 | 128789.6373 | 64394.8186 | 32197.4093 | 32197.4093 | 32197.4093 | 470082.1761
20 | 01.01.2026 | PEB Material | GJ06XX8001 | 8822500525 | 31.12.2025 | 9992309408 | 25390 | 12870 | 12520 | 12490 | -30 | 500 | 1267744.44 | 1074359.6949 | 214871.939 | 107435.9695 | 53717.9847 | 53717.9847 | 53717.9847 | 784282.5773
21 | 01.01.2026 | PEB Material | GJ16AU6360 | 8822500524 | 31.12.2025 | 9992309407 | 12580 | 4820 | 7760 | 7720 | -40 | 120 | 665024.4 | 563580 | 112716 | 56358 | 28179 | 28179 | 28179 | 411413.4
|  |  |  | 8822500526 | 31.12.2025 | 9992309409 |  |  |  |  | 0 |  | 131302.46 | 111273.2712 | 22254.6542 | 11127.3271 | 5563.6636 | 5563.6636 | 5563.6636 | 81229.488
22 | 02.01.2026 | PEB Material | GJ06AV7978 | 8822500534 | 02.01.2025 | 9992309416 | 25410 | 12640 | 12770 | 12790 | 20 | 350 | 1348708.14 | 1142973 | 228594.6 | 114297.3 | 57148.65 | 57148.65 | 57148.65 | 834370.29
23 | 03.01.2026 | PEB Material | GJ06AV4544 | 8822500540 | 03.01.2025 | 9992309423 | 32600 | 12530 | 20070 | 20020 | -50 | 520 | 2094402.06 | 1774917 | 354983.4 | 177491.7 | 88745.85 | 88745.85 | 88745.85 | 1295689.41
24 | 05.01.2026 | PEB Material | GJ06AV7978 | 8822500544 | 05.01.2025 | 9992309431 | 29550 | 12610 | 16940 | 16910 | -30 | 280 | 1736901 | 1471950 | 294390 | 147195 | 73597.5 | 73597.5 | 73597.5 | 1074523.5
|  |  |  | 8822500545 | 05.01.2025 | 9992309432 |  |  |  |  | 0 |  | 4163.04 | 3528 | 705.6 | 352.8 | 176.4 | 176.4 | 176.4 | 2575.44
25 | 06.01.2026 | PEB Material | GJ06AV7978 | 8822500551 | 06.01.2025 | 9992309438 | 25500 | 12600 | 12900 | 12910 | 10 | 300 | 1309711.5 | 1109925 | 221985 | 110992.5 | 55496.25 | 55496.25 | 55496.25 | 810245.25
26 | 10.01.2026 | Wooden material return | GJ06YY6488 | - | - | SPSPL/25-26/026 |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 13.01.2026 | PEB Insulation Material | HR38W2207 | 8822500618 | 13.01.2026 | 9992309536 | - | - | - |  |  |  | 1594298 | 1351100 | 270220 | 135110 | 67555 | 67555 | 67555 | 986303
28 | 23.01.2026 | PEB Insulation Material | GJ35T2423 | 8822500668 | 23.01.2026 | 9992309632 | - | - | - |  |  |  | 677576.66 | 574217.5085 | 114843.5017 | 57421.7508 | 28710.8754 | 28710.8754 | 28710.8754 | 419178.7812
29 | 28.01.2026 | PEB Material | GJ19X4381 | 8822500699 | 28.01.2026 | 9992309691 | 8810 | 5280 | 3530 | 3500 | -30 | 48 | 353805.3 | 299835 | 59967 | 29983.5 | 14991.75 | 14991.75 | 14991.75 | 218879.55
|  |  |  | 8822500700 |  | 9992309692 |  |  |  |  | 0 |  | 64006.74 | 54243 | 10848.6 | 5424.3 | 2712.15 | 2712.15 | 2712.15 | 39597.39
30 | 29.01.2026 | PEB Material | GJ06AV3379 | 8822500704 | 28.01.2026 | 9992309696 | 24200 | 12650 | 11550 | 11430 | -120 | 300 | 78540.22 | 66559.5085 | 13311.9017 | 6655.9508 | 3327.9754 | 3327.9754 | 3327.9754 | 48588.4412
|  |  |  | 8822500705 | 28.01.2026 | 9992309697 |  |  |  |  | 0 |  | 1072330.1 | 908754.322 | 181750.8644 | 90875.4322 | 45437.7161 | 45437.7161 | 45437.7161 | 663390.6551
31 | 29.01.2026 | PEB Material | GJ06YY6488 | 8822500708 | 29.01.2026 | 9992309701 | 7270 | 3480 | 3790 | 3790 | 0 | 160 | 387884.88 | 328716 | 65743.2 | 32871.6 | 16435.8 | 16435.8 | 16435.8 | 239962.68
| 29.01.2027 | PEB Material |  | 8822500709 | 29.01.2026 | [5 empty] | 0 |  | 19619.4 | 16626.6102 | 3325.322 | 1662.661 | 831.3305 | 831.3305 | 831.3305 | 12137.4254
32 | 31.01.2026 | PEB Material | GJ06BX1210 | 8822500721 | 30.01.2026 | 9992309730 | 19820 | 5880 | 13940 | 13900 | -40 | 0 | 1428921 | 1210950 | 242190 | 121095 | 60547.5 | 60547.5 | 60547.5 | 883993.5
33 | 31.01.2026 | PEB Material | GJ06BX1210 | 8822500727 | 31.01.2026 | 9992309738 | 18280 | 5870 | 12410 | 12370 | -40 | 0 | 1279710 | 1084500 | 216900 | 108450 | 54225 | 54225 | 54225 | 791685
34 | 03.02.2026 | PEB Material | GJ16AU6360 | 8822500738 | 03.02.2026 | 9992309748 | 10420 | 4810 | 5610 | 5600 | -10 | 50 | 678645.41 | 575123.2288 | 115024.6458 | 57512.3229 | 28756.1614 | 28756.1614 | 28756.1614 | 419839.957
35 | 04.02.2026 | PEB Material | GJ06YY6488 | 8822500741 | 04.02.2026 | 9992309755 | 5640 | 3470 | 2170 | 2170 | 0 | 0 | 224082 | 189900 | 37980 | 18990 | 9495 | 9495 | 9495 | 138627
36 | 06.02.2026 | PEB Material | GJ06YY6488 | 8822500757 | 06.02.2026 | 9992309786 | 8370 | 3470 | 4900 | 4890 | -10 | 95 | 528010.48 | 447466.5085 | 89493.3017 | 44746.6508 | 22373.3254 | 22373.3254 | 22373.3254 | 326650.5512
37 | 06.02.2026 | PEB Material | GJ06BY2481 | 8822500760 | 06.02.2026 | 9992309790 | 10660 | 6020 | 4640 | 4630 | -10 | 70 | 124956 | 105894.9153 | 21178.9831 | 10589.4915 | 5294.7458 | 5294.7458 | 5294.7458 | 77303.2881
|  |  |  | 8822500761 |  | 9992309789 |  |  |  |  | 0 |  | 417880.57 | 354136.0763 | 70827.2153 | 35413.6076 | 17706.8038 | 17706.8038 | 17706.8038 | 258519.3357
38 | 25.02.2026 | PEB Material | GJ06YY6488 | 8822500933 | 25.02.2026 | 9992310045 | 7960 | 3450 | 4510 | 4520 | 10 | 40 | 13381.2 | 11340 | 2268 | 1134 | 567 | 567 | 567 | 8278.2
|  |  |  | 8822500934 |  | 9992310046 |  |  |  |  | 0 |  | 42008.48 | 35600.4068 | 7120.0814 | 3560.0407 | 1780.0203 | 1780.0203 | 1780.0203 | 25988.2969
|  |  |  | 8822500935 |  | 9992310047 |  |  |  |  | 0 |  | 441886.54 | 374480.1186 | 74896.0237 | 37448.0119 | 18724.0059 | 18724.0059 | 18724.0059 | 273370.4866
39 | 26.02.2026 | PEB Material | GJ17XX9444 | 8822500937 | 25.02.2026 | 9992310052 | 28160 | 13000 | 15160 | 15160 | 0 | 180 | 152456.44 | 129200.3729 | 25840.0746 | 12920.0373 | 6460.0186 | 6460.0186 | 6460.0186 | 94316.2722
|  |  |  | 8822500939 |  | 9992310053 |  |  |  |  | 0 |  | 1476678.14 | 1251422.1525 | 250284.4305 | 125142.2153 | 62571.1076 | 62571.1076 | 62571.1076 | 913538.1714
|  |  |  | 8822500940 |  | 9992310054 |  |  |  |  | 0 |  | 4779 | 4050 | 810 | 405 | 202.5 | 202.5 | 202.5 | 2956.5
40 | 28.02.2026 | PEB Material/WOOD | GJ06BT2931 | - | - | Not received yet |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 12.03.2026 | PEB Material | GJ06YY4284 | 8822500984 | 12.03.2026 | 9992310249 | 6770 | 3600 | 3170 | 3170 | 0 | 55 | 250546.59 | 212327.6186 | 42465.5237 | 21232.7619 | 10616.3809 | 10616.3809 | 10616.3809 | 154999.1616
|  |  |  | 8822500985 |  | 9992310250 |  |  |  |  | 0 |  | 171217.76 | 145099.7966 | 29019.9593 | 14509.9797 | 7254.9898 | 7254.9898 | 7254.9898 | 105922.8515
42 | 14.03.2026 | PEB Material | GJ06AV3379 | 8822500999 | 13.03.2026 | 9992310278 | 23500 | 12720 | 10780 | 10620 | -160 | 700 | 1359141.38 | 1151814.7288 | 230362.9458 | 115181.4729 | 57590.7364 | 57590.7364 | 57590.7364 | 840824.752
43 | 17.03.2026 | PEB Material | GJ01ET6625 | 8822501011 | 16.03.2026 | 9992310305 | 24200 | 12380 | 11820 | 11600 | -220 | 510 | 1518891.34 | 1287196.0508 | 257439.2102 | 128719.6051 | 64359.8025 | 64359.8025 | 64359.8025 | 939653.1171
44 | 20.03.2026 | PEB Material | GJ01HT8059 | 8822501022 | 19.03.2026 | 9992310328 | 10680 | 6050 | 4630 | 4530 | -100 | 120 | 588732.01 | 498925.4322 | 99785.0864 | 49892.5432 | 24946.2716 | 24946.2716 | 24946.2716 | 364215.5655
45 | 11.04.2026 | PEB Material | GJ06VV5320 | 8822600048 | 11.04.2026 | 9992600106 | 4890 | 3540 | 1350 | 1320 | -30 | 20 | 141114.34 | 119588.4237 | 23917.6847 | 11958.8424 | 5979.4212 | 5979.4212 | 5979.4212 | 87299.5493
46 | 11.04.2026 | PEB Material RETURN | GJ06VV5320 | Viatrix-26-27/001-R | 11.04.2026 | - |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 18.04.2026 | PEB Material | GJ06BY0113 | 8822600097 | 18.04.2026 | 9992600179 | 2850 | 2140 | 710 | 710 | 0 | 20 | 37444 | 31732.2034 | 6346.4407 | 3173.2203 | 1586.6102 | 1586.6102 | 1586.6102 | 23164.5085
|  |  |  | 8822600098 |  | 9992600180 |  |  |  |  | 0 |  | 78812.14 | 66789.9492 | 13357.9898 | 6678.9949 | 3339.4975 | 3339.4975 | 3339.4975 | 48756.6629
48 | 02.05.2026 | PEB Material RETURN | GJ06AT1904 | - | - | SPSPL/26-27/003 |  |  |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 04.05.2026 | PEB Material | GJ01AT8059 | 8822600177 | 04.05.2026 | 9992600328 | 7260 | 5870 | 1390 | 1360 | -30 | - | 143118.34 | 121286.7288 | 24257.3458 | 12128.6729 | 6064.3364 | 6064.3364 | 6064.3364 | 88539.312
50 | 07.05.2026 | PEB Material | GJ06BT7418 | 8822600201 | 07.05.2026 | 9992600379 | 2390 | 1700 | 690 | 700 | 10 | 25 | 35701.58 | 30255.5763 | 6051.1153 | 3025.5576 | 1512.7788 | 1512.7788 | 1512.7788 | 22086.5707
|  |  |  | 8822600202 |  | 9992600380 |  |  |  |  | 0 |  | 53637.38 | 45455.4068 | 9091.0814 | 4545.5407 | 2272.7703 | 2272.7703 | 2272.7703 | 33182.4469
51 | 23.05.2026 | PEB Material | GJ06BT7418 | 8822600302 | 23.05.2026 | 9992600581 | 1910 | 1690 | 180 | 210 | 30 | - | 34128.44 | 28922.4068 | 5784.4814 | 2892.2407 | 1446.1203 | 1446.1203 | 1446.1203 | 21113.3569
|  |  |  | 8822600303 |  | 9992600582 |  |  |  |  | 0 |  | 5548.92 | 4702.4746 | 940.4949 | 470.2475 | 235.1237 | 235.1237 | 235.1237 | 3432.8064
|  |  |  | 8822600304 |  | 9992600583 |  |  |  |  | 0 |  | 4248 | 3600 | 720 | 360 | 180 | 180 | 180 | 2628
52 | 28.05.2026 | PEB Material | GJ05BT3193 | 8822600324 | 27.05.2026 | 9992600631 | 15710 | 12030 | 3680 | 3660 | -20 |  | 4248 | 3600 | 720 | 360 | 180 | 180 | 180 | 2628
|  |  |  | 8822600325 |  | 9992600632 |  |  |  |  | 0 |  | 351355.38 | 297758.7966 | 59551.7593 | 29775.8797 | 14887.9398 | 14887.9398 | 14887.9398 | 217363.9215
53 | 19.06.2026 | PEB Material | GJ06BT3316 | 8822600474 | 19.06.2026 | 9992600875 | 7130 | 5920 | 1210 | 1200 | -10 | 50 | 12213 | 10350 | 2070 | 1035 | 517.5 | 517.5 | 517.5 | 7555.5
|  |  |  | 8822600475 |  | 9992600876 |  |  |  |  | 0 |  | 1093.28 | 926.5085 | 185.3017 | 92.6508 | 46.3254 | 46.3254 | 46.3254 | 676.3512
|  |  |  | 8822600476 |  | 9992600877 |  |  |  |  | 0 |  | 3200.4 | 2712.2034 | 542.4407 | 271.2203 | 135.6102 | 135.6102 | 135.6102 | 1979.9085
|  |  |  | 8822600477 |  | 9992600878 |  |  |  |  | 0 |  | 26956.19 | 22844.2288 | 4568.8458 | 2284.4229 | 1142.2114 | 1142.2114 | 1142.2114 | 16676.287
|  |  |  | 8822600478 |  | 9992600879 |  |  |  |  | 0 |  | 50322.86 | 42646.4915 | 8529.2983 | 4264.6492 | 2132.3246 | 2132.3246 | 2132.3246 | 31131.9388
|  |  |  | 8822600479 |  | 9992600880 |  |  |  |  | 0 |  | 690.3 | 585 | 117 | 58.5 | 29.25 | 29.25 | 29.25 | 427.05
54 | 2026-05-05 | PEB Material | gj06bw7576 | 8822600187 | 2026-05-05 |  |  |  | 320 | 320 | 0 |  | 33984 | 28800 | 5760 | 2880 | 1440 | 1440 | 1440 | 21024 | Remark: This bill has not been received at the site; therefore, the copy is pending.
55 | 2026-06-24 | PEB Material | GJ06BX5575 | 8822600524 | 2026-06-26 | [7 empty] | 1320278.4 | 1118880 | 223776 | 111888 | 55944 | 55944 | 55944 | 816782.4 | Remark: This bill has not been received at the site; therefore, the copy is pending.
Total | [8 empty] | 422.64 | 420.46 | -2.18 | 10.913 | 47850474.09 | 40551249.2288 | 8110249.8458 | 4055124.9229 | 2027562.4614 | 2027562.4614 | 2027562.4614 | 29602411.937
[15 empty] | 330249.8458 | 165124.9229 | 2027562.4614 | 2027562.4614
1 | 2025-08-18 | 10% OF Advance Along with LOA |  | SPSPL/PRO/25-26/26 | 2025-08-18 | 3890000
2 | 2025-10-30 | 20% Advance against the approval of the GA design. |  | SPSPL/PRO/25-26/40 | 2025-10-30 | 7780000 | [11 empty] | 4550499.6915
3 |  | Net Amount Payable Against raised Bill |  |  |  | 29602411.937
|  | Net Amount Payable Against This Bill With Advanced Amount |  |  | Total | 41272411.937
| Note | As per the LOA, the total PEB steel weight is 307.690 MT with a contract value of ₹3,89,00,002 excluding GST. However, after carrying out detailed calculations, it was found that the actual steel weight is coming to approximately 405 MT. No PO amendment has been issued for this additional quantity and weight difference. Therefore, clarification and necessary action are requested regarding the excess steel quantity beyond the approved LOA scope.

## PEB ERECTION
VIATRIX ENGINEERING & PLASTIC LLP, BAMANGAM
ERECTION
Sr. No. | Recieved Date | Description of Goods | Tax Invoice No. | Invoice Date | Total Invoice value without GST | Total Invoice value with GST
1 | 2025-12-29 | 20 % Against Mobilization | 8822500508 | 2025-12-29 | 660000 | 778800
2 | 2026-01-12 | 40 % of the contract value for erection work shall be released upon of Primary structure, Secondary structure & final alignment of building with completion of all bolt tightening. | 8822500604 | 2026-01-12 | 990000 | 1168200
Total |  |  |  |  | 1650000 | 1947000
|  | As per the LOA, the total PEB steel weight is 307.690 MT with a material supply value of ₹3,89,00,002 excluding GST. The erection value is ₹32,00,000 excluding GST. |  |  | Total value without GST | Total value with GST
|  |  | 1 | LOA value | 3200000 | 3776000
|  |  | 2 | Raised Value | 1650000 | 1947000
|  |  |  | balance Amount |  | 1829000

## CIVIL RA Bill
VIATRIX ENGINEERING & PLASTIC LLP, BAMANGAM
CIVIL RA BILL
Sr. No. | Description of Goods | Tax Invoice No. | Invoice Date | Against bill Raised | Price Variation of material | Total Invoice value without GST | Steel advance 85% adjusted as per consumption | Total Invoice value withGST | Retentions (5%) | Net Amount Payable Against This Bill With Advanced Amount
1 | RA-01 | 114/2025-26 | 2025-11-14 | 3152382 | 148043 | 3004339 | 792833.25 | 3545120.02 | 150216.95 | 2602069.82
2 | RA-02 | 170/2025-26 | 2026-01-13 | 4286581 | 201117 | 4085464 | 991988 | 4820847.52 | 204273.2 | 3624586.32
3 | RA-03 | 193/2025-26 | 2026-02-13 | 5999728 | 99451 | 5900277 | 503918 | 6962326.86 | 295013.85 | 6163395.01
4 | RA-04 | 229/2025-26 | 2026-03-25 | 5274039 | 38490 | 5235549 | 255769 | 6177947.82 | 261777.45 | 5660401.37
5 | RA-05 | 14/2026-27 | 2026-04-22 | 11685557 | 65396 | 11620161 | 1587022 | 13711789.98 | 581008.05 | 11543759.93
6 | RA-06 | 27/2026-27 | 2026-05-22 | 2605027 | 28734 | 2576293 | 342490.75 | 3040025.74 | 128814.65 | 2568720.34
7 | RA-07 | 45/2026-27 | 2026-07-01 | 6432564 | 122670 | 6309894 | 424864 | 7445674.92 | 315494.7 | 6705316.22
Total | [5 empty] | 38731977 |  | 45703732.86 | 1936598.85 | 38868249.01

## Summary Civil
SUMMARY OF COST
PROJECT NAME: Proposed Factory Building and Associated Work for Viatrix Engineering & Plastic LLP at Bamangam. |  |  |  | RA BILL: | 7
Name of Contractor : NK Infra |  |  |  | DATE: | 2026-06-25
SR. NO. | DESCRIPTION | AMOUNT AS PER PO | AMOUNT (RS)
|  |  | PREVIOUS BILL | THIS BILL | TOTAL BILL
TENDER ITEM
1 | FACTORY BUILDING | 46686584 | 27094346 | 1355021 | 28449367
2 | RCC ROAD & DRAIN | 11038781 | 0 | 3211560 | 3211560
3 | WATER SUPPLY NETWORK | 1143025 | 0 | 204047 | 204047
4 | SEWAGE DISPOSAL NETWORK | 791685 | 0 | 199365 | 199365
5 | FIRE WATER TANK | 1495745 |  |  | 0
6 | FIRE PUMP ROOM | 1192842.2 |  |  | 0
7 | UG-TANK/Cooling Tower | 812427 | 0 | 645435.8 | 645435.8
8 | TRANSFORMER & OTHER FDN | 1214544 | 178689.22 | 0 | 178689.22
9 | DECORATIVE COMPOUND WALL | 2011523 | 1590605 | 408256 | 1998861
10 | NON DECORATIVE COMPOUND WALL | 2612845 | 4139672 | 408879 | 4548551
TOTAL TENDER ITEAM: |  | 69000001.2 | 33003312 | 6432564 | 39435876
Basic Rate Difference
1 | Cement |  | 0 | 0 | 0
2 | Reinforcement Steel |  | -581231 | -2889 | -584120
3 | Structural Steel |  | 0 | 0 | 0
4 | NP2 300mm dia |  | 0 | -36117 | -36117
5 | Sch - 40 (50mm Dia pipe) |  | 0 | -83664 | -83664
TOTAL NON TENDER ITEAM: |  | 0 | -581231 | -122670 | -703901
TOTAL ITEAM: |  | 69000001.2 | 32422081 | 6309894 | 38731975

## CIVIL STEEL
VIATRIX ENGINEERING & PLASTIC LLP, BAMANGAM
CIVIL STEEL ADVANCE BILL
Sr. No. | Description of Goods | Tax Invoice No. | Invoice Date | Against bill Raised | Total Invoice value without GST
1 | Material Secured Advance @ 85% | 1001 | 2025-10-10 | 489940 | 489940
2 | Material Secured Advance @ 85% | 1003 | 2025-12-13 | 662915 | 662915
3 | Material Secured Advance @ 85% | 1004 | 2026-01-07 | 421218 | 421218
4 | Material Secured Advance @ 85% | 1005 | 2026-02-19 | 295226.25 | 295226.25
5 | Material Secured Advance @ 85% | 1006 | 2026-03-27 | 655435 | 655435
6 | Material Secured Advance @ 85% | 1007 | 2026-04-07 | 796386 | 796386
7 | Material Secured Advance @ 85% | 1009 | 2026-06-29 | 975205 | 975205
Total |  |  |  |  | 4296325.25

## Karmasth Fire
VIATRIX ENGINEERING & PLASTIC LLP, BAMANGAM
Karmasth Fire And Safty Services
Sr. No. | Recieved Date | Description of Goods | Tax Invoice No. | Invoice Date | Total Invoice value without GST | 18%GST | 05%GST | Retentions (10%) of the Contract Value shall be paid upon successful commissioning and handing over of the system to the Owner. | Net Amount Payable
1 | 2026-05-15 | Material supply | 85/26-27 | 2026-05-15 | 1726416 | 310754.88 |  | 172641.6 | 1864529.28
2 | 2026-05-26 | Material supply | 102/26-27 | 2026-05-26 | 788000 | 141840 |  | 78800 | 851040
3 | 2026-05-26 | Material supply | 102/26-27 | 2026-05-26 | 501079.25 | 90194.265 |  | 50107.925 | 541165.59
4 | 2026-06-12 | Material supply | 133/26-27 | 2026-06-12 | 237696 | 42785.28 |  | 23769.6 | 256711.68
5 | 2026-06-12 | Material supply | 133/26-27 | 2026-06-12 | 139776 |  | 6988.8 | 13977.6 | 132787.2
6 | 2026-06-23 | Material supply | 161/26-27 | 2026-06-23 | 891148.8 | 160406.784 |  | 89114.88 | 962440.704
Total |  |  |  |  | 4284116.05 |  |  |  | 4608674.454
[5 empty] | Total value without GST |  |  | Total value with GST
|  |  | 1 | PO value | 6532022.4 |  |  | 7707786.432
|  |  | 2 | Raised Value | 4284116.05 |  |  | 5055256.939
|  |  |  | Balance Amount |  |  |  | 2652529.493
Formulas:
Invoice Date = [Recieved Date]