## Equipment_Planning
QUIPMENT PLANNING & MOBILIZATION CHECKLIST (CIVIL WORK)
Project
| Report No. |  |  |  | Date of Equipment Planning
| Location: |  |  |  | Ref. Codes:
| Contractor Name |  |  |  | Quantity:
Sr. No. | Activity | Equipment Type | Capacity / Model | Purpose of Use | Required Qty | Available Qty | Source (Own / Hire / Vendor) | Mobilization Date | Responsibility | Remarks
1 | Excavation | Excavator / JCB | 0.9 m³ | Excavation & Backfilling |  |  |  |  | Contractor
2 | Excavation | Tractor with Trolley | - | Soil / Debris Shifting |  |  |  |  | Contractor
3 | Leveling / Filling | Dumper | 10 Tonne | Soil Transport |  |  |  |  | Contractor
4 | Foundation Work | Concrete Mixer | 1/2 Bag | RCC Mixing |  |  |  |  | Contractor
5 | Foundation Work | Vibrator | 40mm | Concrete Compaction |  |  |  |  | Contractor
6 | Foundation Work | Plate Compactor | 5 HP | Subgrade Compaction |  |  |  |  | Contractor
7 | Reinforcement | Bar Bending Machine | 32mm | Bar Fabrication |  |  |  |  | Contractor
8 | Reinforcement | Bar Cutting Machine | 32mm | Rebar Cutting |  |  |  |  | Contractor
9 | Shuttering | Scaffolding / Cuplock | - | RCC Support |  |  |  |  | Contractor
10 | RCC Work | Water Pump | 3–5 HP | Dewatering / Curing |  |  |  |  | Contractor
11 | RCC Work | Generator | 25 KVA | Power Supply |  |  |  |  | Contractor
12 | Masonry Work | Cutting Machine | - | Masonry Cutting |  |  |  |  | Contractor
13 | Finishing Work | Grinder / Polisher | - | Surface Finishing |  |  |  |  | Contractor
14 | External Development | Loader / Crane | 20 Tonne | Material Handling |  |  |  |  | Contractor
15 | Miscellaneous Equipment | Welding Machine | - | Fabrication / Cutting |  |  |  |  | Contractor
Corrective action, if any:
Contractor | [5 empty] | PMC
Name: | [5 empty] | Name:
Date: | [5 empty] | Date:
Approved
Not Approved
Approved With Comments