## 1
CHECKLIST FOR MVRV / VRF SYSTEM
Project
Report No. |  |  | Date of Inspection:
Ref.Drg.No.
S.No. | Description of Activity |  |  | YES | NO | Remarks
1 | Outdoor & indoor units placed per drawing with clearance
2 | Refrigerant pipe size/routing/insulation as OEM
3 | Brazed joints with nitrogen purging
4 | Refrigerant piping properly supported vibration-free
5 | Nitrogen pressure test conducted & held
6 | Vacuum test below 500 microns, stable holding
7 | Refrigerant charged as per OEM & recorded
8 | Control cabling between indoor/outdoor units as schematic
9 | Earthing for all indoor/outdoor units
10 | Condensate drain connections sloped & terminated
11 | System commissioning/performance test with OEM/consultant
Corrective Action Any :
Contractor |  |  | PMC
Name: |  |  | Name:
Date: |  |  | Date:
Approved
Not Approved
Approved With Comments