## 1
CHECKLIST FOR TESTING & COMMISSIONING
Project
Report No. |  |  | Date of Inspection:
Ref.Drg.No.
S.No. | Description of Activity |  |  | YES | NO | Remarks
1 | Flushing and hydrostatic test of chilled/condenser water piping witnessed by consultant.
2 | Pneumatic pressure test of refrigerant piping with nitrogen holding test done.
3 | Duct leakage test completed, leakage class acceptable.
4 | Motor rotation direction verified for AHU fans, blowers, pumps, cooling tower fans, and compressors.
5 | System air balancing done (CFM at diffusers, grilles, AHU outlet).
6 | Water balancing completed (GPM/LPM at coils, risers, chillers, cooling towers).
7 | Refrigerant leak test carried out, proper charging confirmed.
8 | Condensate drain flow tested at AHUs, FCUs, VRF indoor units.
9 | Record chiller performance test (inlet/outlet water temp, kW/TR, efficiency).
10 | Record cooling tower performance (range, approach, fan current).
11 | Record air compressor trial (pressure, flow, noise, cut-in/cut-out).
12 | Space temperature and humidity within design limits.
13 | Electrical load (current, voltage, PF) measured for equipment.
14 | BMS/control integration for AHU, Chiller, Cooling Tower, Pumps, VRF, and Air Compressor confirmed.
15 | Safety interlocks tested (fire alarm shutdown, smoke mode, pressure switches, flow switches).
16 | Submit combined testing and commissioning report with OEM certifications, TAB reports, and O&M manuals.
Corrective Action Any :
Contractor |  |  | PMC
Name: |  |  | Name:
Date: |  |  | Date:
Approved
Not Approved
Approved With Comments