## 1
CHECKLIST FOR PRE-CONSTRUCTION & MOBILIZATION - PEB
Project
Report No. |  |  | Date of Inspection:
Ref.Drg.No.
S.No. | Description of Activity |  |  | YES | NO | Remarks
1 | Pedestal & anchor bolts checked and approved
2 | PEB fabrication drawings (IFC) approved
3 | Material test certificates for steel received
4 | Laydown/stacking area prepared with crane access
5 | Major components (columns, rafters, purlins) delivered
6 | Erection sequence and lifting plan approved
7 | Heavy cranes, boom lifts, and rigging gear mobilized
8 | Welding machines, torque wrenches, tools arranged
9 | Method statement & safety checklist submitted
10 | Alignment and bolt tightening procedure approved
11 | Coordination with civil foundation works ensured
Corrective Action Any :
Contractor |  |  | PMC
Name: |  |  | Name:
Date: |  |  | Date:
Approved
Not Approved
Approved With Comments