## CIVIL
CHECKLIST FOR CIVIL HANDING OVER WORK
Project
Report No. |  |  |  | Date of Inspection:
Ref.Drg.No. |  |  |  | Ref. Codes:
Location: |  |  |  | Quantity:
Sr. No. | Item / Activity | Verification / Handover Criteria | Status (OK/Not OK) | Remarks | PMC Sign & Date | Client Sign & Date
1 | Approved as-built drawings submitted | All civil as-built drawings compiled and submitted to client
2 | Completion of structural works | RCC, foundations, columns, beams, slabs, and curing records verified
3 | Masonry works | All block/brick masonry completed as per approved layout
4 | Internal plaster | Plaster completed, surface free of cracks, hollowness, and unevenness
5 | External plaster & finishes | External surfaces completed with proper curing and neat finish
6 | Waterproofing works | Toilets, terraces, basements, and water tanks tested and approved
7 | Flooring & skirting | All flooring, dado, skirting works completed with approved material
8 | Staircases & landings | Construction and finishes completed as per design
9 | Doors & window openings | All openings completed and handed over ready for joinery
10 | Roof works | Roof treatments, waterproofing, and slopes completed
11 | Compound wall & gate civil work | Boundary wall, gate supports, and finishes completed
12 | External development | Paving, kerb stones, pathways, landscaping base civil works completed
13 | Drainage & manholes | Stormwater, chambers, manholes, and covers completed
14 | Water tanks / Septic tank | Civil works, plastering, and covers completed & watertight
15 | Expansion joint treatment | Completed and sealed (if applicable)
16 | Final levels & slopes | Verified for internal and external areas as per design
17 | Painting base work | Surfaces prepared and primer coat applied (civil scope only)
18 | Site cleaning | Debris removed, site handed over in clean condition
19 | Documentation | QA/QC reports, cube test results, approvals handed over
20 | Punch list clearance | All pending observations rectified and cleared
21 | Final joint inspection | Conducted with client/PMC and accepted
22 | Final civil work sign-off | All civil scope handed over to client satisfaction
Corrective action, if any:
Contractor |  |  |  | PMC
Name: |  |  |  | Name:
Date: |  |  |  | Date:
Approved
Not Approved
Approved With Comments