## Fire
CHECKLIST FOR FIRE HANDING OVER WORK
Project
Report No. |  |  |  | Date of Inspection:
Ref.Drg.No. |  |  |  | Ref. Codes:
Location: |  |  |  | Quantity:
Sr. No. | Item / Activity | Verification / Handover Criteria | Status (OK/Not OK) | Remarks | PMC Sign & Date | Client Sign & Date
1 | Approved as-built drawings submitted | Fire fighting layouts, hydraulic calculations, and as-builts compiled and handed over
2 | Underground/overhead fire water tanks | Civil & plumbing completed, watertightness tested, capacity verified
3 | Fire pumps installation | Main pump, jockey pump, standby pump installed, aligned, tested
4 | Pump room piping & valves | Installed as per approved drawing with isolation valves & NRVs
5 | Pump performance test | Flow test, pressure test, and automatic changeover verified
6 | Hydrant piping network | Underground & aboveground piping completed and hydro-tested
7 | Hydrant landing valves | Installed with hose boxes, hoses, and nozzles provided
8 | Sprinkler piping network | Installed as per layout, coverage verified
9 | Sprinkler heads | Correct type & orientation, spacing checked and tested
10 | Fire hose reel system | Hose reels installed at designated points, tested for flow
11 | Fire extinguishers | Installed at approved locations with proper tagging & certificates
12 | Fire alarm & detection system | Detectors, MCPs, sounders, and control panels installed & tested
13 | Control & monitoring | Fire system integrated with FACP / BMS, tested for alarms & signals
14 | Pipe supports & hangers | Installed with proper spacing, painting, and identification
15 | Pressure testing – piping | Hydro / pneumatic test conducted and approved
16 | Painting & identification | Red painting, line marking, and labeling completed
17 | Emergency power supply | Diesel generator / UPS backup connected and tested
18 | Flow test at hydrant points | Verified discharge and pressure at farthest points
19 | Sprinkler system test | Full wet test conducted, results recorded and approved
20 | Safety & access provisions | Pump room ventilation, lighting, signage, and access provided
21 | Site cleaning | Fire fighting debris, scrap, and unused material cleared
22 | Documentation | Test certificates, approvals, O&M manuals, warranty papers submitted
23 | Statutory clearance | Fire NOC / inspection certificate obtained from local authority
24 | Punch list clearance | All pending observations rectified and cleared
25 | Final joint inspection | Conducted with client/PMC and accepted
26 | Final fire fighting work sign-off | Entire fire fighting scope handed over to client satisfaction
Corrective action, if any:
Contractor |  |  |  | PMC
Name: |  |  |  | Name:
Date: |  |  |  | Date:
Approved
Not Approved
Approved With Comments