## Interior
CHECKLIST FOR INTERIOR HANDING OVER WORK
Project
Report No. |  |  |  | Date of Inspection:
Ref.Drg.No. |  |  |  | Ref. Codes:
Location: |  |  |  | Quantity:
Sr. No. | Item / Activity | Verification / Handover Criteria | Status (OK/Not OK) | Remarks | PMC Sign & Date | Client Sign & Date
1 | Approved as-built drawings submitted | Interior layouts, furniture layouts, ceiling & partition drawings submitted
2 | Partitions | Gypsum/wood/glass partitions completed, aligned, and finished
3 | False ceiling | Installed as per design, leveled, with cutouts for services
4 | Flooring works | Tiles, stone, carpet, or vinyl flooring completed with proper finish
5 | Wall finishes | Paint, wall paneling, cladding, or wallpaper installed neatly
6 | Doors & frames | Doors, frames, hardware fitted, aligned, and polished/painted
7 | Windows & glazing | Glass fixed with proper sealing, alignment, and safety checks
8 | Joinery & furniture | Tables, counters, cupboards, workstations installed as per drawings
9 | Loose furniture | Chairs, sofas, storage units placed as per approved layout
10 | Wardrobes & cabinets | Shutters, drawers, handles fitted, smooth operation verified
11 | Modular furniture | Assembled, aligned, and complete with edge banding/finishing
12 | Polishing & painting | Wood polish/paint finishes completed and free of stains or patches
13 | Fixtures & fittings | Mirrors, shelves, curtain rods, blinds installed as per scope
14 | Acoustic works (if any) | Acoustic panels, insulation, or baffles installed and tested
15 | Lighting integration | All cutouts aligned with lights, grills, diffusers, and tested
16 | Electrical & plumbing interface | Interior finishes completed after service points verified
17 | Safety provisions | Fire-retardant materials, exit signage, and access panels provided
18 | Cleaning & snag rectification | Surfaces, floors, and fixtures cleaned; all snags rectified
19 | Mock-up / sample approval | Final finishes match approved mock-ups / samples
20 | Documentation | Material approvals, warranties, and O&M manuals submitted
21 | Punch list clearance | All pending observations rectified and cleared
22 | Final joint inspection | Conducted with client/PMC and accepted
23 | Final interior work sign-off | Entire interior scope handed over to client satisfaction
Corrective action, if any:
Contractor |  |  |  | PMC
Name: |  |  |  | Name:
Date: |  |  |  | Date:
Approved
Not Approved
Approved With Comments