— A S S U R E D   P R O G R E S S —

PROPOSAL 2026 – 27 PROJECT MANAGEMENT CONSULTANCY PROPOSAL Comprehensive Project Development Services

| PREPARED FOR Arvind Limited Santej Road, Taluka, near Khatrej, Kalol, Gujarat 382722 Kind Attn.: Soham Shah | PROJECT Manufacturing Facility Sartej , Ahmedabad Project Development & Management Consultancy (PMC) Services |
| --- | --- |

| REFERENCE SPDC/26-27/INQ/78 Date: 29th July 2026 | SUBMITTED BY Mr. Nirav Parekh — Director Sharnam Project Development Consultants & Co |
| --- | --- |

SHARNAM PROJECT DEVELOPMENT CONSULTANTS & CO. First Floor, Status Plaza, FF 09, Plot No. 18, near Akshar Chowk, Munjmahuda, Vadodara, Gujarat 390007 ✆ +91 81607 57201 ✉ nirav@spdc.in

# Letter from the Director

Ref: SPDC/26-27/INQ/78	Date: 29th July 2026

To,

Arvind Limited

Santej Road, Taluka, near Khatrej, Kalol, Gujarat 382722

Kind Attention: Mr. Soham Shah

Subject: Proposal for Comprehensive Project Development & Management Consultancy Services — Manufacturing Facility at Satej , Vadodara.

Respected Sir,

I trust this message finds you in good health and spirits. I am writing to follow up on our recent discussions regarding the opportunity for our firm to provide comprehensive Project Development services for the upcoming Manufacturing facility at Satej, Ahmedabad

At the outset, please allow me to express our sincere gratitude for considering our expertise. We highly value the prospect of partnering with Arvind Limited on this prestigious initiative, which includes the proposed facility alongside its associated infrastructure works.

With our extensive experience and proven track record in project development, we are confident in our ability to contribute meaningfully to the successful realization of your vision. Our approach is rooted in delivering superior quality outcomes by applying industry-leading practices, rigorous quality control, and innovative design solutions tailored to your specific operational and aesthetic requirements.

We are committed to delivering a facility and supporting infrastructure that are not only functionally robust and efficient, but also architecturally distinguished — reflecting the ethos and future ambitions of your organisation. Our team will work closely with you to ensure that the project timeline, budget, and quality expectations are met with utmost precision and transparency.

Thank you once again for this opportunity. We are eager to move forward and collaborate closely to bring this significant project at Arvind limited to fruition. Please feel free to reach out for any further clarifications or discussions. We look forward to your positive response and the chance to contribute our expertise towards your success.

Warm Regards,

Mr. Nirav Parekh

Director

Sharnam Project Development Consultants & Co,

# Table of Contents

| Document Control | Details | Document Control | Details |
| --- | --- | --- | --- |
| Document Title | PMC Proposal — Manufacturing Facility at Satej | Reference No. | SPDC/26-27/INQ/78 |
| Prepared For | Arvind Limited, Satej | Date of Issue | 29th July, 2026 |
| Prepared By | Sharnam Project Development Consultants & Co. | Revision | R1 — For Client |
| Approved By | Mr. Nirav Parekh, Director | Status | Confidential — Commercial |

Letter from the Director	2

Table of Contents	3

Executive Summary	8

Our Value Proposition at a Glance	8

About SPDC	9

Vision	9

Mission	9

Core Values	9

Company Profile & Capabilities	10

Firm Overview	10

Sectors We Serve	10

Core Service Capabilities	10

Why SPDC	11

Ten Reasons to Choose SPDC	11

Project Understanding	13

Key Project Facts	13

What the Project Demands	13

Project Objectives	14

Primary Objectives	14

Guiding Principles	14

Project Delivery Methodology	15

Stage 1 — Initiate	15

Stage 2 — Plan	15

Stage 3 — Execute	15

Stage 4 — Control	15

Stage 5 — Close	16

Complete Scope of Services	18

Service Matrix	18

Pre-Construction Services	19

1. Project Design, Management & Cost Estimation	19

2. Drawing Evaluation	19

3. Tender Evaluation	19

4. Enabling Works & Soil Filling Supervision	19

Construction Phase Services	21

1. Programme / Schedule Management	21

2. Design Management	21

3. Cost Management	22

4. Programme Monitoring and Control	22

5. Procurement Management	22

6. Construction Management	22

7. Communication Management	23

Post-Construction Services	24

1. Commissioning and De-Snagging	24

2. Final Handover	24

3. Defect Liability Period (DLP) Management	25

4. Stakeholder Coordination, Inspections & Defect Control	25

5. Retention, Warranty & Contractual Closure	25

Digital Project Management Platform	26

1. Document Management System (One Drive Cloud)	26

2. Live Monitoring & Project Progress Dashboard	26

3. Employee & Manpower Management System	26

Why This Matters	26

Organization Structure	28

Roles & Reporting Lines	28

Key Personnel	29

Resource Deployment Plan	31

Deployment Summary	31

Deployment Timeline (Quarterly View)	31

Project Execution Strategy	34

The SPDC Operating Rhythm	34

Execution Priorities	34

Quality Management	35

Key QMS Instruments	35

Safety Management	36

Safety Framework	36

Cost Control	37

Cost Control Instruments	37

Illustrative Monthly Cost Report Format	37

Schedule Management	38

Scheduling Approach	38

Indicative Milestone Framework	38

Procurement Management	40

SPDC's Procurement Support Services	40

Risk Management	41

Illustrative Risk Register	41

Communication Matrix	43

Stakeholder Communication Matrix	43

Escalation Ladder	43

Reporting System	44

Reporting Deliverables	44

Project Dashboard Samples	45

Dashboard Views Available to the Client	46

Value Engineering	47

Typical Value Engineering Opportunities	47

Commercial Proposal	49

A. Construction Phase — Technical Team Provided at Site	49

B. MEPF Construction Phase — Technical Team	49

C. Post-Construction Phase — Technical Team (Included)	50

Notes & Inclusions	51

Team Deployment Schedule	52

Construction Phase — Year 1 (Months 1–12)	52

Post-Construction Phase (6 Months)	52

Terms & Conditions	53

Assumptions	56

Exclusions	57

Additional Exclusions	57

1. Working Days Basis	57

2. Structural Finalization	58

3. Soil Filling – Option A: Not Part of Construction Scope (Chargeable Extra)	58

3A. Soil Filling – Option B: Included in Construction Scope (Same Fee Structure, Extended Duration)	58

4. Manpower Deployment	59

5. General Clarification	59

Annexures	60

Annexure A — Reimbursable Expenses Framework	60

Annexure B — Standard Report Formats	60

Annexure C — Documents Available on Request	60

Acceptance	62

Way Forward	62

PART 01 Introduction Executive summary and the firm behind this proposal ◆ Executive Summary ◆ About SPDC ◆ Company Profile & Capabilities ◆ Why SPDC

# Executive Summary

Sharnam Project Development Consultants & Co. (SPDC) is pleased to submit this comprehensive proposal to Arvind Limited end-to-end Project Development & Management Consultancy (PMC) services for the proposed Manufacturing Facility at Satej , Ahmedabad, together with its associated infrastructure works.

This document sets out our understanding of the project, our delivery methodology, the complete scope of services across the pre-construction, construction, and post-construction stages, our organisation and resource deployment plan, our management systems for quality, safety, cost, schedule, procurement, and risk, and our commercial proposal and terms of engagement.

| 3 Project Stages Covered End-to-End | 07 Months of Dedicated Site Deployment | 10 Days to Full Team Mobilisation | 100% Digital, Cloud-Based Project Controls |
| --- | --- | --- | --- |

## Our Value Proposition at a Glance

- Single point of accountability. SPDC acts as the Client's dedicated representative — coordinating designers, contractors, vendors, and agencies so that Arvind limited deals with one responsible partner.

- Full life-cycle coverage. From enabling works and soil-filling supervision, through construction management, to commissioning, handover, and Defect Liability Period (DLP) management.

- Experienced, dedicated site team. A full-time Project Manager, Senior and Junior Project Engineers, and a PEB specialist, backed by a Head-Office Co-ordinator and Director-level oversight.

- Proprietary digital ecosystem. An in-house, cloud-based Document Management System, live progress dashboard, and manpower management platform — delivering unmatched transparency at no additional cost.

- Transparent commercials. A clear man-month based fee structure of INR 03,40,000  Per Month basis (plus GST) & for the construction phase ( Civil ,  PEB ), for pre-construction and post-construction services included within the comprehensive fee. ( For Pre Construction Client Should Provide the Food & Travel Services )

Upon completion of ten (07) months from the effective date of this Agreement, Sharnam shall, before giving effect to any amendment to the Purchase Order, provide a reasonable and written justification for such amendment, including the revised amount payable per month. Any such amendment shall take effect only upon mutual acceptance by both parties in writing.

No Extra charges shall be payable for the initial period of Seven (07) months from the effective date of this agreements. Upon completion of the said Seven (07) month period, Sharnam shall be charged the monthly fees as described in the Commercial Offer, payable on a per-month basis thereafter

Our Commitment SPDC commits to delivering this project with precision, transparency, and uncompromising quality — protecting the Client's interests on cost, time, and quality at every stage of the project life cycle.

# About SPDC

Sharnam Project Development Consultants & Co. (SPDC) is a professional project development and management consultancy headquartered in Vadodara, Gujarat. Guided by our promise of “Assured Progress”, we partner with clients across industrial, institutional, and infrastructure sectors to plan, manage, and deliver capital projects with certainty.

Our teams combine hands-on site execution experience with structured project-controls discipline. We believe successful projects are built on three foundations: rigorous planning, transparent communication, and relentless quality and safety supervision. Every SPDC engagement is designed around these foundations.

## Vision

To be the most trusted project development partner in Western India — recognised for integrity, technical excellence, and the certainty of outcomes we deliver to our clients.

## Mission

- Deliver every project to the promised quality, on schedule, and within the approved budget.

- Protect our clients' interests as their independent, single point of accountability.

- Bring digital transparency to every stage of project delivery.

- Develop people and processes that raise the standard of project management practice.

## Core Values

| ◆ Integrity Independent, unbiased advice that always places the Client's interest first. | ◆ Excellence Industry-leading practices, rigorous quality control, and continuous improvement. |
| --- | --- |
| ◆ Transparency Open reporting, audit-ready records, and real-time visibility for every stakeholder. | ◆ Commitment Dedicated deployment, responsive support, and ownership of outcomes — not just activities. |

# Company Profile & Capabilities

## Firm Overview

| Particular | Details |
| --- | --- |
| Legal Name | Sharnam Project Development Consultants & Co. |
| Registered Office | First Floor, Status Plaza, FF 09, Plot No. 18, near Akshar Chowk, Munjmahuda, Vadodara, Gujarat 390007 |
| Leadership | Mr. Nirav Parekh — Director |
| Core Business | Project Development & Management Consultancy (PMC) Services |
| Contact | +91 81607 57201 ¦ nirav@spdc.in |
| Service Region | Pan-India, with focus on Gujarat, Rajasthan, and Western India |

## Sectors We Serve

| INDUSTRIAL Factories & PEB Sheds | ► | INSTITUTIONAL Colleges & Campuses | ► | COMMERCIAL Offices & Retail | ► | INFRASTRUCTURE Roads & Utilities | ► | LOGISTICS Warehousing & Parks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Core Service Capabilities

| ▣ Project Management Consultancy End-to-end PMC covering planning, execution supervision, controls, and closeout across all project stages. | ▣ Design Management Coordination of architectural, structural, MEP, and civil design disciplines; drawing scrutiny and approval management. |
| --- | --- |
| ▣ Cost & Contracts Management Estimation, budgeting, cash-flow planning, bill certification, variation and claims review, and cost reporting. | ▣ Planning & Scheduling Master schedules, milestone benchmarking, look-ahead programmes, and recovery planning. |
| ▣ Quality & Safety Supervision QMS/EHS implementation, inspections, testing witness, NCR management, and safety compliance monitoring. | ▣ Procurement Support Vendor evaluation assistance, PO tracking, material planning, and procurement documentation chains. |
| ▣ PEB & MEP Expertise Specialist engineers for pre-engineered buildings and mechanical, electrical, plumbing & fire services. | ▣ Digital Project Controls Proprietary cloud platform for documents, live dashboards, and manpower management. |

# Why SPDC

Selecting the right project management partner is the single most important decision after the decision to build. SPDC offers Arvind limited a rare combination of senior leadership attention, dedicated site presence, and digital transparency — at a fee structure that is simple, predictable, and fully aligned with the project's success.

## Ten Reasons to Choose SPDC

| # | Differentiator | What It Means for You |
| --- | --- | --- |
| 01 | Director-Led Engagement | The Director personally oversees the project throughout its duration not only at kick-off. |
| 02 | Dedicated Full-Time Site Team | Our engineers are deployed exclusively to your project, in addition to the contractor's own supervision staff. |
| 03 | End-to-End Scope | One partner from soil filling and enabling works to DLP closure and retention release. |
| 04 | Proprietary Digital Ecosystem | Exclusive cloud DMS, live dashboards, and geo-tagged manpower tracking — included at no extra cost. |
| 05 | PEB & MEP Specialisation | In-house pre-engineered building and MEPF engineering capability, critical for modern facilities. |
| 06 | Transparent Man-Month Commercials | Clear per-resource pricing; invoices based on actual deployment, verified by activity reports. |
| 07 | Rapid Mobilisation | Full team deputed within 40 calendar days of LOI / Work Order. |
| 08 | Independent, Client-First Advice | We hold no contractor or vendor interests; every recommendation protects the Client alone. |
| 09 | Structured Reporting Discipline | Daily updates, weekly progress reports, monthly management reviews — audit-ready at all times. |
| 10 | Value Engineering Mindset | Continuous cost, material, and system optimisation without compromising quality or performance. |

The SPDC Difference Most consultancies report on problems. SPDC anticipates them. Our look-ahead planning, daily design coordination, and live dashboards surface risks early — so decisions are made before delays and cost overruns occur, not after.

PART 02 Project Approach Understanding, objectives, and delivery methodology ◆ Project Understanding ◆ Project Objectives ◆ Project Delivery Methodology

# Project Understanding

Arvind Limited intends to develop a Manufacturing Building facility at Satej , Ahmedabad , together with associated infrastructure works. The development requires professional, independent project management to coordinate design consultants, contractors, and vendors, and to safeguard the Client's interests on quality, cost, and schedule from enabling works through to final handover.

## Key Project Facts

| Parameter | Description |
| --- | --- |
| Client | Arvind Limited , Ahmedabad, Gujarat |
| Project | Manufactring Building Facility with Associated Infrastructure Works |
| Location | Satej , Ahmedabad |
| Engagement | Project Development & Management Consultancy (PMC) Services |
| Coverage | Pre-Construction, Construction, and Post-Construction Stages |
| Construction Deployment | 07 months of dedicated site team deployment |
| Post-Construction Support | 6 months of handover and DLP management involvement |

## What the Project Demands

- Early quality assurance. Soil filling and enabling works at Satej must be rigorously supervised — levels, compaction, and test certifications — because the entire structure depends on them.

- Multi-disciplinary coordination. Civil, structural, PEB, and MEPF disciplines must be integrated through disciplined design management and coordinated drawings.

- Remote-site governance. With the Client based in Ahmedabad and the site in Satej, transparent digital reporting and a dependable on-site team are essential.

- Cost discipline. Budget adherence through bill verification, variation control, and cash-flow planning across a 10-month execution window.

- Structured handover. As-built documentation, O&M manuals, DLP administration, and retention management to protect long-term value.

Figure 1 — Indicative project delivery timeline across the three engagement stages

| PRE-CONSTRUCTION Enabling & Tender Support |  | CONSTRUCTION PHASE Execution Management ¦ 12 Months |  |  | POST-CONSTRUCTION Handover & DLP ¦ 6 Months |  |
| --- | --- | --- | --- | --- | --- | --- |
| ● LOI / Work Order | ● Site Mobilisation |  | ● Structure Complete | ● Substantial Completion |  | ● Project Closure |

# Project Objectives

SPDC's engagement will be governed by clear, measurable objectives agreed with the Client at project inception. Our performance will be reported against these objectives every month.

## Primary Objectives

| Objective | Success Measure | SPDC Instrument |
| --- | --- | --- |
| Timely Completion | Achievement of master-schedule milestones; substantial completion within the approved programme | Master schedule, look-ahead plans, recovery planning |
| Budget Adherence | Final cost within approved budget; variations justified and pre-approved | Cost tracking, bill certification, variance analysis |
| Quality Assurance | Zero major non-conformances at handover; all tests passed and documented | QMS implementation, inspections, NCR management |
| Safety Compliance | Zero lost-time incidents; full statutory compliance monitoring | Safety audits, toolbox coordination, compliance reviews |
| Transparent Governance | 100% of decisions, documents, and approvals digitally logged | Cloud DMS, live dashboard, structured reporting |
| Smooth Handover | Complete as-built, O&M, and warranty documentation; clean DLP closure | Handover strategy, snag management, DLP protocol |

## Guiding Principles

- Prevention over correction — issues are engineered out through planning and review before they reach site.

- Single source of truth — one integrated schedule, one budget, one document platform.

- Decisions with data — every recommendation is supported by records, analysis, and options.

- Client visibility — the Client should never need to ask for a status update; it is always available.

# Project Delivery Methodology

SPDC follows a structured, stage-gated delivery methodology. Each stage has defined inputs, activities, deliverables, and exit criteria, ensuring that the project advances only on a verified foundation of quality and approvals.

| 1. INITIATE Kick-off & Baselines | ► | 2. PLAN Schedule, Budget, QMS | ► | 3. EXECUTE Supervise & Coordinate | ► | 4. CONTROL Monitor & Correct | ► | 5. CLOSE Handover & DLP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Stage 1 — Initiate

- Project kick-off meeting; confirmation of objectives, stakeholders, and communication protocols.

- Review of all available drawings, specifications, BOQs, and contracts.

- Establishment of the document management system and reporting calendar.

## Stage 2 — Plan

- Master project schedule prepared in consultation with the Client, covering all phases and dependencies.

- Detailed budget, cash-flow projections, and procurement plan established.

- Quality Management System (QMS) and safety framework rolled out to all agencies.

## Stage 3 — Execute

- Full-time site supervision of all construction activities against approved drawings and method statements.

- Daily design review and coordination; approval management for samples, mock-ups, and shop drawings.

- Coordination meetings with contractors, vendors, and consultants; single-point communication.

## Stage 4 — Control

- Progress measurement against baseline; look-ahead programmes and recovery plans where required.

- Cost tracking, bill verification and certification, and review of extra works and claims.

- Quality inspections, testing witness, NCR tracking, and safety compliance monitoring.

## Stage 5 — Close

- Snag identification and clearance; testing & commissioning management.

- As-built verification, O&M compilation, final bill certification, and cost completion report.

- DLP administration, warranty enforcement, retention monitoring, and formal project closure report.

Stage-Gate Discipline No stage is considered complete until its deliverables are documented, reviewed, and formally accepted. This gate discipline is what converts good intentions into assured progress.

PART 03 Scope of Services Complete life-cycle services across all three stages ◆ Complete Scope of Services ◆ Pre-Construction Services ◆ Construction Phase Services ◆ Post-Construction Services ◆ Digital Project Management Platform

# Complete Scope of Services

SPDC's scope spans the full project life cycle. The matrix below summarises the services delivered in each stage; the following three sections describe each stage in detail.

| PRE-CONSTRUCTION Design, Estimation & Tender Support | ► | CONSTRUCTION Execution Management — 24 Months | ► | POST-CONSTRUCTION Handover, DLP & Closure |
| --- | --- | --- | --- | --- |

## Service Matrix

| Service Area | Pre-Con | Construction | Post-Con |
| --- | --- | --- | --- |
| Design Management & Coordination | ● | ● | — |
| Cost Estimation & Budgeting | ● | ● | — |
| Technical Specification & Tender Document Review | ● | — | — |
| Drawing Evaluation & Compliance Scrutiny | ● | ● | — |
| Tender Evaluation & Contractor Selection Support | ● | — | — |
| Soil Filling / Enabling Works Supervision | ● | — | — |
| Master Scheduling & Milestone Benchmarking | — | ● | — |
| Cost Tracking, Bill Verification & Claims Review | — | ● | ● |
| Procurement Management Support | — | ● | — |
| Construction Supervision & Quality Control | — | ● | — |
| Safety Management System Monitoring | — | ● | — |
| Communication, Reporting & Documentation | ● | ● | ● |
| Testing, Commissioning & De-Snagging | — | — | ● |
| Final Handover Documentation & Cost Report | — | — | ● |
| DLP, Warranty & Retention Management | — | — | ● |

Note Bills of Quantities (BOQ), technical specifications, and contracts will be provided by the project or design consultant and reviewed by SPDC accordingly.

# Pre-Construction Services

The pre-construction stage lays the technical and commercial foundation of the project. SPDC's services in this stage focus on design integration, realistic budgeting, tender rigour, and disciplined supervision of enabling works.

## 1. Project Design, Management & Cost Estimation

### 1.1 Design Management and Coordination

- Oversee and coordinate all design activities, ensuring alignment with Client requirements and project objectives.

- Facilitate multidisciplinary design integration across architectural, structural, MEP, and civil disciplines.

- Conduct periodic design review meetings to monitor progress and resolve design issues proactively.

### 1.2 Cost Estimation and Budgeting

- Develop detailed preliminary and detailed cost estimates covering all project components.

- Prepare a comprehensive project budget including direct and indirect costs, contingency, and escalation factors.

- Provide cost-control mechanisms to ensure budget adherence throughout project phases.

### 1.3 Review of Technical Specifications and Tender Documents

- Critically analyse technical specifications and tender documentation for completeness, accuracy, and compliance with applicable standards.

- Recommend amendments or clarifications to enhance clarity and reduce ambiguities.

## 2. Drawing Evaluation

- Perform thorough scrutiny and verification of all project drawings for technical accuracy, consistency, and compliance with approved design criteria.

- Ensure all drawings adhere to relevant codes, standards, and regulatory requirements.

- Identify potential conflicts or discrepancies and coordinate with design consultants for resolution.

## 3. Tender Evaluation

- Conduct detailed evaluation of received tender submissions, including technical capabilities, commercial terms, and delivery schedules.

- Prepare comparative analyses and risk assessments of bidding contractors.

- Provide well-justified recommendations for contractor selection based on project-specific criteria.

## 4. Enabling Works & Soil Filling Supervision

- Site mobilisation planning and coordination.

- Monitoring and supervision of soil filling activities — checking levels, soil quality, compaction methodology, and verifying test reports (Proctor density, moisture content, etc.).

- Ensuring proper documentation and quality assurance for the filling work.

- Coordinating with soil testing agencies/laboratories and ensuring proper certifications are received.

- Verifying the contractor's methodology for earthwork and ensuring compliance with design levels and slopes.

- Preparing and maintaining records, level sheets, and site photographs.

Deliverables — Pre-Construction Stage • Design review minutes and coordinated drawing registers • Preliminary and detailed cost estimates; approved project budget • Tender review reports and contractor recommendation note • Soil filling quality dossiers — level sheets, test certificates, photo records

# Construction Phase Services

During the construction stage, SPDC provides full-time site management and project controls across seven integrated work streams.

| SCHEDULE | ► | DESIGN | ► | COST | ► | MONITORING | ► | PROCUREMENT | ► | CONSTRUCTION | ► | COMMUNICATION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## 1. Programme / Schedule Management

### 1.1 Master Project Schedule Preparation

- Develop a comprehensive master project schedule in close consultation with the Client, covering all phases including pre-construction, construction, commissioning, and soft-start activities.

- Integrate key activities, dependencies, and timelines to provide a clear roadmap for project execution.

### 1.2 Milestone Identification and Benchmarking

- Identify critical project milestones and establish measurable benchmarks to monitor progress and ensure timely completion of each phase.

- Implement milestone tracking tools and set up alerts for proactive intervention if delays arise.

## 2. Design Management

### 2.1 Daily Design Review & Coordination

- Continuously review design documentation during construction to ensure alignment with project specifications and Client requirements.

- Coordinate with design consultants, vendors, and contractors to resolve design-related queries or discrepancies promptly.

### 2.2 Regular Issuance of Design Programme

- Provide periodic updates to the design programme, reflecting approved changes and revised schedules to all relevant stakeholders.

### 2.3 Value Engineering Recommendations

- Analyse opportunities to optimise costs, materials, and systems without compromising quality or performance.

- Propose alternative design solutions and materials to enhance project value and sustainability.

### 2.4 Facilitation of Coordination Meetings

- Schedule and moderate regular meetings between vendors, designers, and contractors to ensure smooth communication and timely decision-making.

### 2.5 Approval Management

- Oversee the submission, review, and approval process for samples, mock-ups, shop drawings, and coordinated drawings.

- Maintain comprehensive records of all approvals and revisions to ensure traceability and compliance.

## 3. Cost Management

- Detailed budget preparation — develop a detailed cost budget covering all aspects of the construction phase.

- Cash-flow management — prepare and update cash-flow statements on a quarterly or semi-annual basis to help the Client manage financial resources effectively.

- Cost tracking — monitor actual expenditure against the approved budget regularly and provide variance analysis reports to the Client.

- Bill verification and certification — verify bills and payment applications from contractors, suppliers, and vendors for accuracy and compliance with contractual terms before recommending certification.

- Review of extra works and claims — examine, analyse, and certify additional works, claims, and variations submitted by contractors, ensuring all claims are justified and properly documented.

## 4. Programme Monitoring and Control

- Project schedule coordination — collaborate with contractors to integrate their schedules into the overall project timeline, ensuring alignment and resource availability.

- Progress monitoring and reporting — conduct regular site inspections and meetings to monitor progress, identify bottlenecks, and report updates to the Client through detailed progress reports.

- Look-ahead and recovery planning — prepare forward-looking programme updates and develop recovery plans to mitigate delays, ensuring project milestones remain achievable.

## 5. Procurement Management

- Client procurement assistance — support the Client's designated procurement representative with vendor evaluation, comparative statements, and order finalisation inputs.

- Material planning — prepare and maintain a material planning schedule aligned to the construction programme, flagging long-lead items early.

- Material tracking and stock management — track delivery of materials against purchase orders and maintain accurate inventory records, including client-supplied materials.

- Contract administration and dispute resolution — manage procurement contracts, ensuring compliance and timely dispute resolution to avoid project delays.

- Material and equipment coordination — coordinate with contractors and suppliers to review equivalent materials and equipment for compliance with project specifications.

## 6. Construction Management

- Coordination and supervision — act as the central point of coordination among contractors, subcontractors, and agencies, supervising construction activities to ensure adherence to design and specifications.

- Logistics planning — develop and implement logistics plans to ensure timely delivery and storage of materials and equipment at site, minimising disruption.

- Construction sequencing and resource coordination — define the sequence of construction activities and coordinate availability of labour, equipment, and materials to optimise workflow.

- Quality control and testing — oversee and witness testing of materials and workmanship according to Quality Management System (QMS) standards; coordinate corrective actions for deviations.

- Mock-up identification — determine the necessity of on-site or off-site mock-ups for critical elements and oversee their approval.

- Quality and safety management systems — establish and monitor implementation of Quality Assurance and Safety Management Systems to ensure a safe and compliant work environment.

- Method statement review — review construction method statements submitted by contractors for adequacy, safety, and compliance before approval.

## 7. Communication Management

- Single point of contact — serve as the primary liaison between all project stakeholders, facilitating clear and timely communication.

- Reporting and documentation — prepare and distribute Weekly Progress Reports, Monthly Status Reports, meeting agendas, and Minutes of Meetings to keep all parties informed and aligned.

# Post-Construction Services

SPDC remains engaged after physical completion to secure a clean, complete, and well-documented handover — and to administer the Defect Liability Period so that the Client's contractual protections are fully enforced.

## 1. Commissioning and De-Snagging

- Handover strategy development — define and document a detailed handover strategy in consultation with the Client and key stakeholders, outlining sequence, documentation, timelines, and acceptance criteria.

- Review and clearance of snags — inspect all completed works, prepare snag lists, and coordinate with contractors/vendors for timely resolution of all outstanding works prior to handover.

- Monitoring equipment installation — oversee installation and integration of MEP systems, machinery, and plant equipment per final drawings and manufacturer guidelines.

- Testing & commissioning management — schedule and monitor T&C activities for all systems (HVAC, electrical, plumbing, fire-fighting, etc.), ensuring documentation of protocols, reports, test results, and vendor approvals.

- As-built documentation coordination — liaise with design consultants/contractors for submission of complete and correct as-built drawings, verified against site execution.

## 2. Final Handover

- Final bill verification and closure — check, verify, and certify final bills of all project stakeholders, including design consultants, vendors, suppliers, and contractors.

- Client material reconciliation — prepare a detailed reconciliation report of client-supplied materials, highlighting utilisation and balance quantities.

- Cost completion report — generate a comprehensive project cost report showing actual vs. budgeted expenditure across all heads, explaining major variations.

- O&M documentation compilation — collect and organise all Operations & Maintenance manuals, warranties, guarantees, and equipment datasheets from contractors/vendors.

### Final Project Closure & Handover Report

A structured, professional handover document including:

- Project Brief — overview of project scope, timeline, and deliverables.

- Project Directory — complete contact list of all project stakeholders.

- As-Built Drawings — for all architectural, structural, and services disciplines.

- Finishes Schedule & Spares List — detailing finishes used and available spares for the Client's maintenance use.

- Contractual Summary — highlighting retention amounts, DLP durations, and pending claims.

- O&M Schedules — maintenance schedules for equipment and services.

- Warranty / Guarantee Records — manufacturer and contractor warranties for all installed items.

## 3. Defect Liability Period (DLP) Management

- Contractual review for DLP obligations — analyse relevant clauses to understand scope, timelines, responsibilities, and penalties related to defect rectification.

- Identification of covered defects — classify defects as structural, non-structural, material-related, or workmanship-related, and identify exclusions.

- Defect Rectification Protocol (DRP) — a clear manual for identifying, reporting, and resolving defects, including escalation paths.

- Handover recordkeeping — maintain DLP records including exact handover date, DLP start/end period, and approved deliverables.

## 4. Stakeholder Coordination, Inspections & Defect Control

- Interface management — seamless communication between the Client, main contractor, consultants, and vendors on all DLP-related issues, with roles and responsibilities documented.

- Periodic DLP inspections using structured audit checklists, with standardised, photo-documented reports.

- Real-time defect log — tracking defect details, dates, assigned parties, status, and rectification notes.

- Prioritisation of defects (critical / major / minor) with recommended rectification timelines.

- Rectification notices, compliance tracking, escalation on delays, and re-inspection & certification of corrections.

## 5. Retention, Warranty & Contractual Closure

- Retention management — monitor contractual retention amounts and advise the Client on release based on successful DLP closure.

- Final clearance — retention released only after full DLP compliance and issue of the completion certificate.

- Warranty oversight — manage warranties for installed equipment, ensuring vendors fulfil repair, servicing, or replacement commitments; act as liaison for warranty claims.

- Penalty enforcement — advise the Client on initiating penalty clauses for delay or non-performance during the DLP, as per contract, and assist in dispute resolution and contractual closure with full documentation.

# Digital Project Management Platform

As part of our PMC services, SPDC offers a comprehensive, in-house developed, cloud-based digital ecosystem that is exclusive to our firm — delivering unmatched transparency, efficiency, and control to our clients. This integrated system is a genuine differentiator in the PMC landscape, and it is included within our fee at no additional cost.

| DOCUMENT MANAGEMENT One Drive | ► | LIVE DASHBOARD Progress & Analytics | ► | MANPOWER SYSTEM Geo-Tagged Attendance |
| --- | --- | --- | --- | --- |

## 1. Document Management System (One Drive Cloud)

- A centralised, secure, cloud-hosted platform to store, access, and manage all project-related documentation.

- Version control, real-time updates, and structured folder management.

- Accessible anytime, from any location — no dependency on physical files or email chains.

- Auto-tagging and smart search features for faster retrieval.

## 2. Live Monitoring & Project Progress Dashboard

- Real-time project tracking through an intuitive dashboard interface.

- Daily site updates, milestone tracking, and progress mapping.

- Visual analytics and reports tailored for clients, consultants, and top management.

- Alerts and notifications for delays, approvals, and pending decisions.

## 3. Employee & Manpower Management System

- Attendance tracking with geo-tagged, time-stamped entries via mobile login.

- Allocation of manpower per task/activity, linked to project progress.

- Resource utilisation analytics and productivity tracking.

- Leave records, shift planning, and labour compliance documentation — all digitally managed.

## Why This Matters

| ✓ Unmatched Transparency Clients are continuously updated without needing to follow up — status is always one click away. | ✓ Efficient Collaboration All stakeholders work on the same platform with role-based access. |
| --- | --- |
| ✓ Audit-Ready Data Every file, decision, and update is digitally logged and retrievable. | ✓ Eco-Friendly & Cost-Effective Reduces paperwork, redundant communication, and delays. |

PART 04 Team & Resources The people and deployment behind assured progress ◆ Organization Structure ◆ Key Personnel ◆ Resource Deployment Plan

# Organization Structure

SPDC deploys a lean, accountable structure with clear reporting lines. The site team is led by a full-time Project Manager reporting to the Director, supported by a Head-Office Co-ordinator who manages documentation, reporting, and back-office engineering support.

|  | DIRECTOR Overall Project Leadership |  |
| --- | --- | --- |

│

|  | PROJECT CO-ORDINATOR Head Office ¦ 10+ Yrs Experience |  |
| --- | --- | --- |

│

|  | PROJECT MANAGER Site (Full-Time) ¦ 10–12 Yrs Experience |  |
| --- | --- | --- |

│

| SR. PROJECT ENGINEER Quality & Co-ordination — 07–08 Yrs |  |  | SAFETY ENGINNER ( IF REQUIRED ) Pre-Engineered Building — 04–06 Yrs |  | MEPF ENGINEER MEP & Fire Services — 06–07 Yrs |
| --- | --- | --- | --- | --- | --- |

Figure 2 — Project organisation structure for the Satej engagement

## Roles & Reporting Lines

| Role | Base | Reports To | Primary Accountability |
| --- | --- | --- | --- |
| Director | HO / Site Visits | Client | Overall engagement leadership, escalation resolution, monthly reviews |
| Project Co-ordinator | Head Office | Director | Documentation, reporting, design & vendor coordination support |
| Project Manager | Site (Full-time) | Director | Site leadership, billing & planning, schedule and cost control |
| Sr. Project Engineer | Site (Full-time) | Project Manager | Quality engineering and site coordination |
| Safety Project Engineer | Site (If Required) | Project Manager | Quality inspections, records, and daily supervision |
| PEB Engineer | Site (if required) | Project Manager | Pre-engineered building erection quality and coordination |
| MEPF Engineer | Site (Optional module) | Project Manager | MEP & fire services installation supervision and T&C |

# Key Personnel

The following profiles represent the qualification and experience standards of the personnel SPDC will deploy on this engagement. Named CVs will be furnished for the Client's approval prior to mobilisation.

### Project Manager (Full-Time Site Deputation)

| Attribute | Details |
| --- | --- |
| Qualification | B.E. / B.Tech / M.Tech (Civil) |
| Experience | 10 – 11 years |
| Sector Exposure | Civil, Infrastructure, Pre-Engineered Buildings , Basic Knowledge of MEPF |
| Key Responsibilities | Site leadership; billing & planning; schedule, cost, and quality control; client and contractor coordination |

### Senior Project Engineer (Full-Time Site Deputation)

| Attribute | Details |
| --- | --- |
| Qualification | Diploma / B.E. / B.Tech / M.Tech |
| Experience | 07 – 08 years |
| Sector Exposure | Civil, Infrastructure |
| Key Responsibilities | Execution, Quality engineering and coordination; inspections; method statement and drawing compliance |

### Safety Project Engineer (Deployed As Required — Not Include)

| Attribute | Details |
| --- | --- |
| Qualification | Diploma in Safety |
| Experience | 04 – 05 years |
| Sector Exposure | Safety and Related Compliances |
| Key Responsibilities | Safety Awareness , Safety Instructions |

### PEB Engineer (Deployed As Required — Not Include)

| Attribute | Details |
| --- | --- |
| Qualification | B.E. / B.Tech / M.Tech |
| Experience | 04 – 06 years |
| Sector Exposure | Pre-Engineered Buildings |
| Key Responsibilities | PEB fabrication/erection review; bolt-torque and alignment checks; interface coordination |

### MEPF Engineer (Optional Module, If Required)

| Attribute | Details |
| --- | --- |
| Qualification | B.E. / B.Tech / M.Tech |
| Experience | 06 – 07 years |
| Sector Exposure | Electrical, Mechanical & Fire Services |
| Key Responsibilities | MEPF installation supervision; testing & commissioning coordination; services quality control |

### Project Co-ordinator (Head Office — Included)

| Attribute | Details |
| --- | --- |
| Qualification | B.Tech / M.Tech |
| Experience | 10 years |
| Sector Exposure | Civil, Infrastructure, PEB & MEP |
| Key Responsibilities | Back-office engineering support; documentation, reporting, and design coordination |

### Director — Engagement Leader

| Attribute | Details |
| --- | --- |
| Qualification | B.tech |
| Experience | Senior leadership |
| Sector Exposure | Civil, Infrastructure, PEB & MEP |
| Key Responsibilities | Overall direction, monthly management reviews, escalation and strategic decisions |

# Resource Deployment Plan

Resources are deployed in line with the construction programme, ensuring the right expertise is on site at the right time. The plan below covers the 24-month construction phase (June 2026 – May 2028 indicative) and the 6-month post-construction support period.

## Deployment Summary

| Resource | Phase | Mode | Duration |
| --- | --- | --- | --- |
| Director | Construction + Post-Construction | Periodic oversight & reviews | Entire engagement |
| Project Co-ordinator | Construction + Post-Construction | Head Office support | Entire engagement |
| Project Manager | Construction | Full-time at site | 10 months |
| Sr. Project Engineer | Construction | Full-time at site | 10 months |
| Jr. Project Engineer | Construction | If Required | 10 months |
| PEB Engineer | Construction (PEB works window) | If Required | Aligned to PEB programme |
| MEPF Engineer | Construction (services window) | Optional module | ≈ 3 months (if required) |
| Post-Construction Team | Handover & DLP | Involvement-based — included | 6 months |

## Deployment Timeline (Quarterly View)

| Resource | Q1 Aug–Oct 26 | Q2 Nov–Jan 26 | Q3 Feb 26–April 27 | Q4 May–July 27 | Q5 Jun–Aug 27 | Q6 Sep–Nov 27 | Q7 Dec 27–Feb 28 | Q8 Mar–May 28 | PC 6 Mo. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Director | ■ | ■ | ■ |  |  |  |  |  | ■ |
| Co-ordinator (HO) | ■ | ■ | ■ |  |  |  |  |  | ■ |
| Project Manager | ■ | ■ | ■ |  |  |  |  |  |  |
| Sr. Project Engineer | ■ | ■ | ■ |  |  |  |  |  |  |
| Safety Project Engineer | ■ | ■ | ■ |  |  |  |  |  |  |
| PEB Engineer |  |  |  |  |  |  |  |  |  |
| MEPF Engineer (opt.) |  | ■ | ■ |  |  |  |  |  |  |

Mobilisation Commitment The SPDC team shall be deputed within 40 calendar days from the date of issuance of the Letter of Intent (LOI) or Work Order. Director and Co-ordinator involvement continues at 25% intensity through the 6-month post-construction period.

PART 05 Management Systems Execution, quality, safety, cost, schedule, procurement & risk ◆ Project Execution Strategy ◆ Quality Management ◆ Safety Management ◆ Cost Control ◆ Schedule Management ◆ Procurement Management ◆ Risk Management

# Project Execution Strategy

Our execution strategy converts the methodology into a day-to-day operating rhythm on site — combining disciplined routines, early-warning controls, and decisive escalation.

## The SPDC Operating Rhythm

| Cadence | Activity | Output |
| --- | --- | --- |
| Daily | Site walk, quality checks, design coordination, dashboard update | Daily progress log & photo records |
| Weekly | Progress review with contractors; look-ahead planning; snag review | Weekly Progress Report & MOM |
| Fortnightly | Design coordination meeting; procurement status review | Drawing/approval tracker; material plan update |
| Monthly | Management review with Client; cost & schedule performance analysis | Monthly Status Report; variance analysis; invoices |
| Quarterly | Cash-flow update; risk register refresh; VE workshop | Updated cash flow, risk register, VE log |

## Execution Priorities

- Front-load the critical path. Enabling works, foundations, and PEB procurement are sequenced and tracked as the project's backbone.

- Lock quality at source. Material approvals, mock-ups, and method statements are cleared before work begins — not inspected after.

- Protect decisions velocity. Every pending approval is tracked with an owner and due date; ageing items are escalated weekly.

- Keep commercial hygiene. Bills, variations, and claims are processed monthly so there are no year-end surprises.

- Plan the handover from day one. As-built, O&M, and warranty documentation requirements are embedded in contractor obligations early.

# Quality Management

SPDC implements a project-specific Quality Management System (QMS) that governs materials, workmanship, and documentation across all agencies. Quality is engineered into the process through approvals and inspections — and verified through testing and audits.

| PLAN QMS & ITPs | ► | APPROVE Materials & Methods | ► | INSPECT Stage Checks | ► | TEST Witness & Verify | ► | CORRECT NCR & Close-out |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Key QMS Instruments

- Inspection & Test Plans (ITPs) for all major activities, defining hold, witness, and review points.

- Material approval registers — no material is incorporated without prior sample/datasheet approval.

- Method statement reviews before commencement of each critical activity.

- Stage-wise checklists (pour cards, alignment checks, torque records, level sheets) maintained digitally.

- Third-party testing coordination — cube tests, soil compaction/Proctor density, moisture content, weld/bolt checks, and services T&C.

- Non-Conformance Reports (NCRs) with root-cause analysis, corrective action, and verified close-out.

- Monthly quality audits and a live quality dashboard shared with the Client.

Responsibility Clarification The appointed civil contractor remains fully responsible for concrete mix design and strength achieved on site, and for steel reinforcement tying and related workmanship. SPDC communicates quality-control procedures to the contractor well in advance and monitors compliance, but does not assume the contractor's execution responsibility.

# Safety Management

SPDC monitors the implementation of a structured Safety Management System across all site agencies, promoting a zero-incident culture through planning, training coordination, inspection, and reporting.

## Safety Framework

| Element | SPDC's Role |
| --- | --- |
| Safety Plan & Statutory Compliance | Review contractor HSE plans; monitor compliance with applicable statutory requirements |
| Method Statements & Risk Assessments | Review high-risk activity method statements and job safety analyses before approval |
| Site Inspections | Daily safety observations during site walks; formal weekly safety inspections |
| Toolbox Talks & Inductions | Coordinate and verify contractor-led inductions and daily toolbox talks |
| PPE & Housekeeping Monitoring | Monitor PPE discipline, working-at-height controls, electrical safety, and site housekeeping standards |
| Incident Reporting | Ensure incidents and near-misses are reported, investigated, and corrective actions tracked to closure |
| Safety Reporting | Safety statistics and observations included in weekly and monthly reports |

Responsibility Clarification While the SPDC team monitors site activities for safety compliance, the ultimate responsibility for site safety lies with the contractors and/or the Client, as per their respective contractual obligations.

# Cost Control

SPDC's cost-control framework gives the Client continuous visibility of committed, incurred, and forecast cost — and subjects every rupee of variation to scrutiny before it is certified.

| BUDGET Baseline & Contingency | ► | COMMIT Orders & Contracts | ► | VERIFY Bills & Claims | ► | REPORT Variance & Forecast |
| --- | --- | --- | --- | --- | --- | --- |

## Cost Control Instruments

- Approved cost baseline with direct/indirect heads, contingency, and escalation provisions.

- Cash-flow statements updated quarterly / semi-annually so funding is planned, never reactive.

- Bill verification & certification — quantity checks against measurements, rate checks against contract, deduction and recovery tracking.

- Variation & claims control — extra works examined, analysed, and certified only when justified and documented.

- Monthly cost report — budget vs. committed vs. incurred vs. forecast, with variance explanations and corrective recommendations.

- Cost completion report at closure, reconciling final cost against the approved budget.

## Illustrative Monthly Cost Report Format

| Cost Head | Budget | Committed | Incurred | Forecast Final | Variance |
| --- | --- | --- | --- | --- | --- |
| Civil & Structure | — | — | — | — | — |
| PEB Works | — | — | — | — | — |
| MEP Services | — | — | — | — | — |
| Finishes & External Works | — | — | — | — | — |
| Total | — | — | — | — | — |

Values are populated monthly from certified records and the live cost ledger.

# Schedule Management

The master project schedule is the single integrated timeline for the project. SPDC prepares it with the Client, embeds every contractor's programme within it, and manages progress against it with look-ahead and recovery planning.

## Scheduling Approach

- Master schedule covering pre-construction, construction, commissioning, and soft-start activities, with dependencies and float analysis.

- Critical milestones identified and benchmarked; milestone alerts configured for proactive intervention.

- Contractor schedules integrated and reconciled with the master programme; resource availability verified.

- Weekly progress measurement; 2-week and 4-week look-ahead programmes issued to all agencies.

- Recovery plans prepared wherever slippage threatens a milestone, with catch-up actions assigned and tracked.

Figure 3 — Illustrative planned vs. actual progress S-curve used for monthly performance reporting

## Indicative Milestone Framework

| Milestone | Indicative Timing | Gate Criteria |
| --- | --- | --- |
| LOI / Work Order & Mobilisation | Month 0 – 1.5 | Team deputed within 40 days; baselines approved |
| Enabling & Soil Filling Complete | Early phase | Compaction tests passed; levels certified |
| Foundations & Structure Complete | Mid phase | Pour cards, cube tests, and alignment records closed |
| PEB Erection Complete | Mid phase | Torque/alignment checks; erection certification |
| MEP Services & Finishes Complete | Late phase | Installations inspected; pre-commissioning checks done |
| Testing, Commissioning & Handover | Month 12 | Snags cleared; as-built and O&M submitted |
| DLP Closure | + DLP period | Defects rectified; retention release recommended |

# Procurement Management

Procurement activities are managed by a designated representative appointed by the Client. SPDC coordinates closely with this representative on the basis of the material planning schedule, and establishes a robust documentation chain — while not being directly responsible for procurement execution.

## SPDC's Procurement Support Services

- Preparation and maintenance of the material planning schedule, aligned to the construction programme.

- Early identification of long-lead items and procurement triggers.

- Assistance in vendor evaluation, technical comparative statements, and order finalisation inputs.

- Tracking of deliveries against purchase orders; inventory records including client-supplied materials.

- Review of equivalent materials and equipment proposed by contractors/suppliers for specification compliance.

- Procurement contract administration support and timely dispute resolution to avoid project delays.

| PLAN Material Schedule | ► | EVALUATE Vendors & Offers | ► | ORDER Client Approval | ► | TRACK PO & Delivery | ► | RECONCILE Stock & Usage |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

Division of Responsibility SPDC assists in setting up a proper documentation chain for procurement and coordinates regularly with the Client's procurement representative, but procurement execution — ordering, payment, and supplier contracting — remains with the Client's organisation.

# Risk Management

SPDC maintains a live project risk register from day one. Risks are identified, scored for probability and impact, assigned owners, and reviewed monthly with the Client. The illustrative register below shows typical risks for a project of this nature and our standard mitigation approach.

## Illustrative Risk Register

| Risk | Impact | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- |
| Delay in soil filling / enabling works quality | High | Medium | Full-time supervision, compaction test verification, level certification before release of subsequent works |
| Design changes during execution | High | Medium | Daily design coordination, change-control protocol, impact assessment before approval |
| Long-lead material delays (PEB, MEP) | High | Medium | Early material planning schedule, procurement triggers, delivery tracking against POs |
| Contractor resource shortfall | Medium | Medium | Weekly resource reviews, look-ahead planning, recovery plans with contractual escalation |
| Cost overrun through variations/claims | High | Medium | Strict variation control, pre-approval of extra works, monthly variance reporting |
| Quality non-conformance | Medium | Medium | ITPs, material approvals, stage inspections, NCR close-out discipline |
| Safety incident | High | Low | Safety plan monitoring, inspections, toolbox coordination, incident protocols |
| Monsoon / weather disruption | Medium | Medium | Weather-sensitive sequencing, protective measures, schedule float management |
| Approval/decision delays | Medium | Medium | Approval tracker with owners and due dates; weekly escalation of ageing items |
| Force majeure / unforeseen events | High | Low | Contingency planning; contractual provisions; prompt Client advisories |

Risk Governance The risk register is reviewed in every monthly management meeting. New risks can be raised by any stakeholder; each risk carries a named owner, a mitigation action, and a review date.

PART 06 Governance & Reporting Communication, reporting, dashboards & value engineering ◆ Communication Matrix ◆ Reporting System ◆ Project Dashboard Samples ◆ Value Engineering

# Communication Matrix

Clear communication protocols prevent confusion, delay, and dispute. SPDC serves as the single point of contact between the Client and all project agencies, operating within the matrix below.

## Stakeholder Communication Matrix

| Communication | From → To | Frequency | Mode |
| --- | --- | --- | --- |
| Daily Progress Update | SPDC Site Team → Client / HO | Daily | Digital dashboard & photo log |
| Weekly Progress Report (WPR) | SPDC → Client | Weekly | Report + review meeting |
| Site Coordination Meeting | SPDC + Contractors + Vendors | Weekly | Meeting + Minutes of Meeting |
| Design Coordination Meeting | SPDC + Design Consultants | Fortnightly | Meeting + drawing tracker |
| Monthly Status Report (MSR) | SPDC → Client Management | Monthly | Formal report + management review |
| Cost & Cash-Flow Review | SPDC → Client | Monthly / Quarterly | Cost report + variance analysis |
| Escalations & Urgent Issues | Any → SPDC Director | As required | Phone / e-mail — response within 24 hrs |
| Approvals & RFIs | Contractors ↔ SPDC ↔ Consultants | Continuous | DMS workflow with due-date tracking |

## Escalation Ladder

| LEVEL 1 Site Engineer — Daily Issues | ► | LEVEL 2 Project Manager — 24 hrs | ► | LEVEL 3 Co-ordinator / HO — 48 hrs | ► | LEVEL 4 Director ↔ Client — Strategic |
| --- | --- | --- | --- | --- | --- | --- |

# Reporting System

SPDC's reporting system converts site data into decision-ready information. Every report is generated from the same digital records — so the Client's daily dashboard, weekly reports, and monthly reviews always agree.

## Reporting Deliverables

| Report | Contents | Frequency |
| --- | --- | --- |
| Daily Site Log | Manpower, activities executed, materials received, weather, photos, safety observations | Daily |
| Weekly Progress Report | Physical progress vs. plan, look-ahead, drawings/approvals status, quality & safety summary, hindrances | Weekly |
| Minutes of Meetings | Decisions, actions, owners, and due dates for all coordination meetings | Per meeting |
| Monthly Status Report | Executive summary, S-curve, milestone status, cost report, NCR/snag status, risk register, next-month plan | Monthly |
| Cash-Flow Statement | Projected vs. actual outflows by cost head | Quarterly / Semi-annual |
| Quality Dossiers | Test certificates, pour cards, checklists, NCR log | Continuous |
| Handover & Closure Reports | Snag closure, as-built verification, O&M compilation, cost completion report, DLP records | At closure stages |

Activity-Linked Invoicing Each monthly invoice is submitted together with the corresponding activity report, so payment is always linked to demonstrated, documented service delivery.

# Project Dashboard Samples

The visuals below illustrate the live dashboard views available to the Client through SPDC's cloud platform. All figures shown are illustrative samples; the live dashboard is updated daily from site records.

Figure 4 — Sample executive dashboard: discipline-wise progress, cost performance, and quality observation status

Figure 5 — Sample cumulative progress S-curve with baseline comparison

## Dashboard Views Available to the Client

| ▦ Executive Overview Overall % complete, milestone RAG status, key decisions pending, and headline risks. | ▦ Schedule View S-curve, look-ahead activities, critical path status, and delay alerts. |
| --- | --- |
| ▦ Cost View Budget vs. committed vs. incurred, certified bills, and variation log. | ▦ Quality & Safety View Inspections done, NCR/snag status, test results, and safety observations. |
| ▦ Documents View Drawing register, approval tracker, and complete searchable project archive. | ▦ Manpower View Geo-tagged attendance, deployment vs. plan, and productivity analytics. |

# Value Engineering

Value engineering (VE) at SPDC is a continuous, structured discipline — not a one-time exercise. Throughout design and construction, we analyse opportunities to optimise costs, materials, and systems without compromising quality, performance, or the project's design intent.

| IDENTIFY Cost / Function Analysis | ► | EVALUATE Alternatives & Impact | ► | PROPOSE VE Recommendation | ► | APPROVE Client Decision | ► | TRACK Savings Realised |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Typical Value Engineering Opportunities

| Area | Typical VE Opportunity | Benefit |
| --- | --- | --- |
| Structure | Optimised structural schemes, rationalised member sizes, concrete grade optimisation | Material savings without strength compromise |
| PEB Works | Bay-spacing and section optimisation; standardised connections | Steel tonnage and erection time reduction |
| MEP Systems | Equipment right-sizing; energy-efficient alternatives; routing optimisation | Lower capital and life-cycle cost |
| Finishes | Equivalent materials with better availability and durability | Cost and schedule advantage |
| Construction Methods | Sequencing and formwork alternatives; prefabrication where viable | Time savings and quality consistency |
| Site Infrastructure | Phased external works; optimised utility corridors | Reduced rework and interface conflicts |

VE Governance Every VE proposal is documented with cost impact, schedule impact, quality implications, and risk assessment. No VE change is implemented without the Client's written approval, and all realised savings are tracked in a VE log reported monthly.

PART 07 Commercials & Terms Fee structure, deployment schedule, and terms of engagement ◆ Commercial Proposal ◆ Team Deployment Schedule ◆ Terms & Conditions ◆ Assumptions ◆ Exclusions ◆ Annexures

# Commercial Proposal

As per the detailed scope of work described in this proposal for Pre-Construction, Construction Phase, and Post-Construction Stage services, we are pleased to submit our professional fee quotation for providing comprehensive Project Development Consultancy Services. The fee is structured on a transparent man-month basis, invoiced against actual resource deployment at site.

## A. Construction Phase — Technical Team Provided at Site

| Sr. | Description of Team | Qualification | Experience & Sector | Per Month Manpower Cost | Deputation |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Manager (Full-time deputation) Role: Billing & Planning | B.E / B.Tech / M.Tech | 08-10 Years — Civil, Infra, Pre-Engineered Building | ₹ 01,35,000 | 07 Months |
| 2 | Sr. Project Engineer (Full-time deputation) Role: Quality Engineer & Coordinator | Diploma / B.E / B.Tech / M.Tech | 05–06 Years — Civil, Infra, Pre-Engineered Building | 01,05,000 | 07 Months |
| 3 | Safety Project Engineer (Full-time deputation) Role: Safety | Diploma | 04–05 Years — Safety | 01,00,000 | 0 Months |
| 4 | PEB Engineer Role: PEB Engineer | B.E / B.Tech / M.Tech | 04–06 Years — Pre-Engineered Building | If Needed | 0 Months |
| 5 | Co-Ordinator (Back Office, HO) | M.Tech / B.Tech | 10 Years — Civil, Infra, PEB & MEP | Included | — |

| Construction Phase — Fee Summary | Amount (INR) | Basis |
| --- | --- | --- |
| Total Monthly Fee | ₹ 03,40,000 | Per Month |
| Total Monthly Fee with GST @ 18% | ₹ 04,01,200 | Per Month |
| Total Fee for Deployment Period | ₹ 23,80,000 | For 07 Months |
| Total Fee with GST @ 18% | ₹ 28,08,400 | For 07 Months |

## B. MEPF Construction Phase — Technical Team – If Required

| Sr. | Description of Team | Qualification | Experience & Sector | Per Month Manpower Cost | Deputation |
| --- | --- | --- | --- | --- | --- |
| 1 | MEPF Engineer (Full-time deputation) | B.E / B.Tech / M.Tech | 06–07 Years — Electrical, Mechanical & Fire Services | ₹ 01,15,000 | 3 Months |
| 2 | MEPF Engineer (Full-time deputation) | B.E / B.Tech / M.Tech | 06–07 Years — Mechanical & Fire Services | - | Per Month |

| MEPF Module — Fee Summary | Amount (INR) | Basis |
| --- | --- | --- |
| Total Monthly Fee | ₹ 1,15,000 | Per Month |
| Total Monthly Fee with GST @ 18% | ₹ 1,35,700 | Per Month |
| Total Fee for Deployment Period | ₹ 3,45,000 | For 3 Months |
| Total Fee with GST @ 18% | ₹ 4,07,100 | For 3 Months |

## C. Post-Construction Phase — Technical Team (Included)

Post-construction services are rendered within the comprehensive fee at no additional monthly charge, through involvement-based deployment of the following resources:

| Sr. | Description of Team | Qualification | Experience & Sector | Fee |
| --- | --- | --- | --- | --- |
| 1 | Project Manager | B.E / B.Tech / M.Tech | 08–10 Years — Civil, Infra, PEB & MEP | Included |
| 2 | Sr. Project Engineer | Diploma / B.E / B.Tech / M.Tech | 05–07 Years — Civil, Infra, PEB | Not Included |
| 3 | Junior / Quality Engineer | Diploma / B.E / B.Tech / M.Tech | 04–06 Years — Civil, Infra, PEB & Documentation | Not Included |
| 4 | Co-Ordinator (From Back Office, HO) | B.E / B.Tech / M.Tech | 06 Years — Civil, Infra, PEB & MEP | Included |
| 5 | Director | M.Tech | Civil, Infra, PEB & MEP | Included |

During the 6-month post-construction period, the Director and Co-ordinator remain engaged at approximately 25% involvement each month to steer DLP administration, handover documentation, and closure.

## Notes & Inclusions

- The above fee is inclusive of the comprehensive scope across construction project stages & post construction stages (Construction, and Post-Construction). For Pre construction stage SPDC Can serve as per Scope of work but related all travel and another expense subject to client which should Reimbursement.

- Supervision and quality monitoring of soil filling work is included as part of the Construction phase.

- The monthly fee includes: deployment of experienced PMC personnel for site coordination and supervision; participation in site review meetings and coordination with all agencies; and preparation and submission of technical reports, schedules, and records.

- The fee is payable monthly, post submission of invoice and activity report.

- Any additional major scope not listed will be addressed separately after mutual discussion.

- Travel, lodging, or other reimbursable expenses outside the main project site (if required) will be claimed at actuals, with prior consent.

Disclaimer 1. The consultancy charges mentioned in this proposal are preliminary estimates and may be subject to revision based on the final scope, duration, site conditions, and overall complexity of the project. These estimates are provided to offer a transparent understanding of the expected investment for the outlined services. 2. All consultancy fees are exclusive of applicable taxes, including Goods and Services Tax (GST) and any other statutory levies as mandated by law; these will be added to the invoice amount as applicable at the time of billing. 3. A detailed formal agreement outlining the final commercial terms, payment milestones, deliverables, and timelines will be issued for mutual review and acceptance upon confirmation of our appointment. 4. Any service or deliverable not explicitly covered in the scope outlined in this proposal shall be considered additional work, undertaken upon a separate written request and quoted and billed separately on mutually agreed terms.

# Team Deployment Schedule

The month-wise allocation below reflects the planned deployment across the 12-month construction phase (indicative: Aug 2026 – July 2027) and the 6-month post-construction period. '1' denotes full-month deployment; fractional values denote proportional involvement.

## Construction Phase — Year 1 (Months 1–12)

| Resource | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | June 27 | July 27 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Director | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| Co-ordinator (HO) | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| Project Manager | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| Sr. Project Engineer | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| Safety Project Engineer | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| MEPF Engineer |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |

## Post-Construction Phase (6 Months)

| Resource | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Director | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |
| Co-ordinator (HO) | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |
| Project Manager | 0 | 0 | 0 | 0 | 0 | 0 |
| Sr. Engineer | 0 | 0 | 0 | 0 | 0 | 0 |

Note The calendar months shown are indicative and will be re-baselined from the actual joining date of the first deployed resource, following issuance of the LOI / Work Order. PEB Engineer deployment is aligned to the PEB erection window within the construction phase and is included in the monthly fee.

# Terms & Conditions

### 1. Site Infrastructure Provision

- The Client shall provide a weatherproof, air-cooled site container cabin measuring 20 ft. × 10 ft., equipped with toilet facilities, to ensure a comfortable working environment for the deputed team.

### 2. Stationery and Office Supplies

- All basic stationery and office supplies required for routine reporting and documentation shall be arranged and provided by the Client.

### 3. Weekly Off and Holidays

- All Sundays, National Holidays, and Religious Holidays will be considered non-working days.

- In case of urgent site requirements, our team will remain available on Sundays, if duly informed in advance.

### 4. Leave Policy

- The deployed team (per employee) shall be entitled to one and a half (1.5) days of leave per calendar month, which will not be deducted from the payable monthly bill. Any leave beyond this shall be mutually discussed.

### 5. Working Hours

- Standard working hours will be 08:30 AM to 06:30 PM, Monday to Saturday.

- In case of work urgency or extended site requirements, the team will remain available beyond working hours, including Sundays.

- If work extends into late hours due to unforeseen circumstances, adjustments in the following day's schedule will be made accordingly to ensure team efficiency and well-being.

### 6. Service Period

- The consultancy and deployment period shall be as per the approved scope of work, and may be extended or modified upon mutual agreement between both parties.

### 7. Emergency Support

- In the event of emergencies or critical project requirements, prompt deputation of an engineer or qualified personnel will be ensured based on availability and need.

### 8. Billing Cycle & Payment Terms

- Advance payment: An advance of 5% of the total agreed consultancy fees shall be payable upon issuance of the Letter of Appointment.

- Monthly billing: Consultancy fees shall be paid in monthly instalments, with invoices raised on the 1st day of each month. Each monthly invoice shall be based on the man-month fee structure as per actual resource deployment at site.

- Extension of project timelines / increase in man-months: The Consultancy Period shall initially be for a duration of twelve (12) months, effective from the joining date of the first deployed resource. In the event of an extension in project timelines or an increase in the required man-months beyond the initially agreed period, an escalation of 12% per annum shall be applicable on the previously agreed consultancy rates. Revised rates shall be calculated on a pro-rata basis, and such extensions shall be mutually discussed and formally approved in writing by both parties.

### 9. Payment Timeline

- All invoices raised shall be due and payable within 7 (seven) days from the date of receipt by the Client.

### 10. Deployment Timeline

- The team from SPDC (Sharnam Project Development Consultancy) shall be deputed within 42 calendar days from the date of issuance of either the Letter of Intent (LOI) or the Work Order.

### 11. Site Staffing Clarification

- The PMC team deployed by us is in addition to the normal site staff of the contractor.

- The Project Management Consultant shall not compensate for or replace the contractor's site supervision requirements.

### 12. Procurement Coordination

- Procurement activities shall be managed by a designated representative appointed by the Client.

- Our team will coordinate regularly with this representative based on the material planning schedule.

- We will assist in setting up a proper documentation chain for procurement but will not be directly responsible for procurement execution.

### 13. Termination Clause

- Either party may terminate this agreement by providing a written notice of one (1) month.

- In case of such termination, all due payments for the notice period shall be settled as per the monthly billing cycle.

### 14. LiaisoniIng & Government Approvals

- All liaisoniIng activities with local bodies and government authorities shall remain the sole responsibility of the Client and shall not be part of the PMC's scope.

### 15. Concrete Quality and Reinforcement Responsibility

- The appointed civil contractor shall be fully responsible for concrete mix design and strength achieved on site, and for steel reinforcement tying and related workmanship.

- The PMC shall not be held responsible for any non-conformance in these aspects; however, quality-control procedures will be communicated to the contractor well in advance.

### 16. Safety Responsibility

- While our team will monitor site activities for safety compliance, the ultimate responsibility for site safety lies with the contractors and/or the Client.

### 17. Unforeseen Circumstances

- In the event of major design alterations, contractor insolvency, property disputes, force majeure, or any other unforeseen issues causing delays, the PMC shall be compensated for additional time and effort spent on the project.

### 18. Employee Non-Poaching Clause

- The Client agrees that it shall not, either directly or indirectly, recruit, hire, engage, offer employment to, or otherwise induce any employee, consultant, or representative of the Consultant during the Project Period and for a period of forty-eight (48) months thereafter.

- Any violation of this provision shall constitute a material breach of the Agreement, and the Consultant shall have the right to pursue legal remedies, including injunctive relief, damages, and recovery of all associated costs and legal expenses.

### 19. Early Termination Compensation Clause

- In the event that the Client terminates or discontinues the Consultant's services without any Contract breach, default, or valid reason attributable to the Consultant, the Client shall provide a minimum of three (3) months' prior written notice or, in lieu thereof, pay compensation equivalent to three (3) months of the Consultant's agreed service fees.

- Such payment shall become due immediately upon termination and shall be payable irrespective of the remaining Project duration.

# Assumptions

This proposal has been prepared on the basis of the following assumptions. Should any of these change materially, the scope, programme, and commercials will be reviewed jointly with the Client.

- Bills of Quantities (BOQ), technical specifications, and contracts will be provided by the project or design consultant; SPDC's role is limited to their review.

- Design consultants (architectural, structural, MEP) are appointed directly by the Client; SPDC coordinates and manages their deliverables.

- Construction contractors and vendors are contracted directly by the Client; SPDC administers and supervises their performance on the Client's behalf.

- The construction phase deployment is planned for 24 months; the initial consultancy period of 12 months and any extensions are governed by the escalation terms in Section 32.

- Site access, power, water, and working permissions are made available by the Client/contractor as required for uninterrupted supervision.

- The Client provides the site cabin and basic office supplies described in the Terms & Conditions.

- Statutory approvals, liaisoniIng, and government fees are handled and borne by the Client.

- The month-wise deployment calendar is indicative and will be re-baselined from the joining date of the first deployed resource.

- The MEPF engineering module is optional and will be activated only on the Client's written confirmation, at the rates quoted.

- Reimbursable expenses are payable as per the framework detailed in the Annexures, subject to prior approval and supporting documents.

# Exclusions

The following activities do not fall under the scope of services provided by our deployed resources. These responsibilities shall be managed either by the Civil Contractor or the Client's internal team:

- Direct coordination with material suppliers.

- Material unloading, physical verification, or weight checks.

- Tracking or managing JCB hours, dumper counts, or coordination for excavation/backfilling works.

- Daily labour deployment management at site.

- Labour colony setup, operation, or routine maintenance.

- Housekeeping or site cleanliness-related activities.

## Additional Exclusions

- Design authorship — preparation of architectural, structural, or MEP designs and drawings (SPDC reviews and coordinates; it does not design).

- LiaisoniIng with local bodies and government authorities, and payment of statutory/authority fees.

- Procurement execution — ordering, payment, and contracting of suppliers (SPDC provides coordination and documentation support only).

- Contractor's site supervision obligations — the PMC team supplements, and does not replace, the contractor's own supervision staff.

PROJECT TIMELINE – EXCLUSIONS, TERMS & CLARIFICATIONS

(Forming an integral part of our Offer / Quotation)

The following exclusions, terms and clarifications are made in the interest of complete transparency, so that both parties have a clear and common understanding of the scope of work, project timeline and commercial terms before commencement of work. These terms shall be read together with, and shall form an integral part of, our offer.

## 1. Working Days Basis

The project completion timeline mentioned in this offer is calculated on the basis of net working days only, and not calendar days. The following shall stand excluded from the timeline and shall extend the completion date accordingly:

- Rainy days or days affected by adverse weather conditions where site work is not feasible or safe;

- All major government / public / national holidays and locally declared holidays;

- Any day on which work is stopped or delayed due to reasons beyond our control, such as non-availability of site access, power / water supply issues, statutory restrictions, local disturbances, or delay in approvals / decisions from the client's side.

Any such lost days shall be duly recorded and the project timeline shall be extended on a day-to-day basis, without any penalty or liability on our part.

## 2. Structural Finalization

Finalization of any structural design, drawing or structural work shall be subject to the actual commencement of construction at site. Any changes, revisions or additions requested after finalization / commencement shall be treated as a variation, and its impact on both cost and timeline shall be intimated and mutually agreed before execution.

## 3. Soil Filling – Option A: Not Part of Construction Scope (Chargeable Extra)

It is expressly clarified that manpower deputed specifically for soil filling work shall not be considered part of the main construction activity or the quoted scope of work. Soil filling shall be treated as a preliminary / supporting service carried out prior to the main construction, on the following basis:

- Charges for such manpower and related services shall be billed extra, over and above the quoted amount;

- The rates / fees for the same shall be as mutually discussed and decided between both parties before deployment;

- The duration spent on soil filling shall not be counted within the main project timeline.

## 3A. Soil Filling – Option B: Included in Construction Scope (Same Fee Structure, Extended Duration)

In case the client desires that soil filling work be included as part of our construction scope under the same fee structure as quoted, the following shall apply:

- Soil filling shall then be executed by us as part of the overall scope of work, without any separate / extra charge for manpower, subject to the same terms of this offer;

- It is expressly clarified that soil filling is a time-consuming preliminary activity, and its inclusion shall proportionately extend the overall project duration;

- The additional time required for soil filling shall be assessed based on the actual quantum of filling work, site conditions and availability of soil / material, and shall be added over and above the quoted project timeline;

- The extended duration on account of soil filling shall not be treated as a delay on our part, nor shall it attract any penalty or liability;

- Commencement of the main construction activity shall be reckoned only after completion of soil filling, and the quoted project timeline shall start counting from that point.

Note: The client may opt for either Option A (Clause 3) or Option B (Clause 3A) for soil filling. The applicable option shall be confirmed in writing prior to commencement of work. In the absence of written confirmation, Option A shall be deemed applicable.

## 4. Manpower Deployment

Manpower at site shall be deployed strictly as per the actual requirement and stage of work. The strength of manpower may vary from time to time depending upon the nature and progress of activities, and shall be planned at our discretion so as to ensure timely and quality completion of the work.

## 5. General Clarification

The above exclusions and clarifications are made to ensure full transparency between both parties. Any item, activity or service not expressly mentioned in this offer shall be deemed excluded from the scope, unless specifically agreed in writing by both parties. Acceptance of this offer shall be construed as acceptance of the above terms in full.

Additional Work Any service or deliverable not explicitly covered in this proposal shall be considered additional work, undertaken upon a separate written request and quoted and billed separately on mutually agreed terms.

# Annexures

## Annexure A — Reimbursable Expenses Framework

The following expenses shall be reimbursed by the Client, subject to prior approval and submission of appropriate supporting documents:

### A.1 Travel and Accommodation

- Economy-class air travel or train (2 AC) for outstation visits; hotel accommodation for the project team during outstation visits.

- Out-of-pocket expenses such as meals and local transportation incurred during such travel.

### A.2 Site Visit-Related Expenses

- Laundry and local conveyance expenses incurred during outstation travel undertaken specifically at the Client's request (e.g., for inspections, meetings, or supervision), with prior approval.

### A.3 Third-Party & Government Fees

- Any fees paid to other consultants (e.g., structural, MEP, landscape) engaged on behalf of the Client.

- Any statutory or authority fees paid for submissions, approvals, or clearances required during the project.

### A.4 Local Travel for Project Work

- Local conveyance charges within the city for site visits, client meetings, coordination with vendors, or other project-related tasks.

Head-Office Visits Site visits from the Head Office (HO) to the project site will not be considered reimbursable expenses; however, up to one or two such visits per month may be considered from the Head Office.

## Annexure B — Standard Report Formats

Formats for the Daily Site Log, Weekly Progress Report, Monthly Status Report, NCR, Snag List, and Material Approval Request will be shared and finalised with the Client at project kick-off. All formats are maintained digitally on SPDC's cloud platform.

## Annexure C — Documents Available on Request

- LLP registration and statutory documents (PAN, GST).

- Detailed CVs of the proposed key personnel.

- Reference list of completed and ongoing engagements.

- Sample Weekly Progress Report and Monthly Status Report.

- Digital platform demonstration (walkthrough available on request).

PART 08 Closure Acceptance and the way forward ◆ Acceptance Page ◆ Thank You

# Acceptance

## Way Forward

We trust the contents of this proposal are in line with our mutual understanding and expectations.

As part of standard protocol, we kindly request the Client to review and confirm acceptance of this proposal by signing and returning a copy to the undersigned. This signed document shall serve as formal approval and confirmation of our appointment as Project Management Consultant for the said project.

We sincerely appreciate the consideration extended by M/s. Arvind limited for this prestigious assignment. We are committed to providing strategic, timely, and value-driven consultancy services, and are confident in our ability to deliver exceptional outcomes aligned with your project objectives.

| ACCEPTED FOR & ON BEHALF OF THE CLIENT |  | FOR SHARNAM PROJECT DEVELOPMENT CONSULTANTS & CO. |
| --- | --- | --- |
| Arvind Limited Authorised Signatory (Name & Designation) Signature & Company Seal Date Place |  | Mr. Nirav Parekh — Director Signature & Company Seal Date 29th July 2026 Place Vadodara |

Formal Agreement Upon acceptance, a detailed formal agreement outlining the final commercial terms, payment milestones, deliverables, and timelines will be issued for mutual review and execution. That agreement will serve as the governing document for our services.

THANK YOU We look forward to a successful collaboration and assure you of our commitment to delivering quality and value throughout the project duration. SHARNAM PROJECT DEVELOPMENT CONSULTANTS & CO. First Floor, Status Plaza, FF 09, Plot No. 18, near Akshar Chowk, Munjmahuda, Vadodara, Gujarat 390007 ✆ +91 81607 57201 ✉ nirav@spdc.in Assured Progress.